Document – 1

- Why is this project initiated?

- The Project is initiated for the follow reasons:

Identify and Assess Health Risk Efficiency : The project aims to develop a system that can classify individuals or patients based on their Health risk levels. This helps healthcare providers to prioritize care and interventions effectively

Improve Preventive Care: By identifying high risk patients early, the system enables timely preventive measures, reducing the chances of serious health complications

Support Clinical Decision Making: Healthcare professionals often deal with large amounts of patient data. This classifier will assist by automating risk assessment making the decision making process faster and more accurate

Optimize Resource Allocation: Hospitals and clinics can better allocate resources ( staff, equipment, attention) based on risk classifications, improving overall healthcare efficiency

Comply with Healthcare Standards and Regulations: There may be a regulatory or organizational requirements to monitor and manage patient risk levels systematically

Data Driven Insights: Use available health data to generate insights that were previously difficult or time consuming to obtain

- What are the current problems?

- Current problems in Health Risk Assessment is follows:

Manual and Time consuming Risk Evaluation: Health professionals often rely on manual assessment of patient data, which can be slow and prone to human error, delaying critical interventions

Inconsistent Risk Classification: Different clinical may classify risk levels differently due to subjective judgment, leading to inconsistent patient care

Large Volume of Patient data: Increasing amounts of patient data make it difficult for healthcare providers to analyze and interpret all relevant information quickly

Delayed Identification of High Risk Patients without automated Tools, high risk patients may be identified too late, increasing the chance of complications of hospital readmissions

Inefficient Resource Allocation: Without accurate risk classification, healthcare resources may not be optimally allocated, potentially neglecting patients who need urgent care

Lack of Standardized Tools: Many healthcare facilities lack standardized data driven tools to support clinical decision making regarding patient risk

Privacy and Security Concerns: Handling sensitive health data manually increases the risk of breaches or non compliance with healthcare regulations

- With this project how many problems could be solved?

- Problems that solved by this Project is follows:

Automation of Risk Assessment: The classifier automates health risk evaluation, drastically reducing manual effort and human errors

Consistent and objective Classification: Using a standardized algorithm or model ensures consistent risk classification across all patients

Efficient Data Handling: The system can analyze large volumes of patient data quickly, enabling timely insights

Early Identification of High Risk Patients Automated alerts and classifications help healthcare providers act promptly to prevent complications

Better Resource Allocation: Accurate risk levels help hospitals prioritize resources like staff attention and equipment for those who need it most

Standardized Decision Support: The classifier acts as a reliable tool supporting clinicians in their decisions, improving overall care quality

Improved Data Security and Compliance: With built in data privacy and security features, the system helps ensure compliance with healthcare regulations

- What are the resources required?

- Human Resources:

Project Manager: To oversee the project phases and coordinate activities

Business Analyst: To gather and document requirements

Data Scientists/ Machine Learning Engineers: To develop and train the Health risk classification model

Software Developers: To build the application/ system around the classifier

Health Care Domain Experts: To provide domain knowledge and validate risk criteria

Quality Assurance/ Testers: To design and execute test cases

UI/UX Designers: To create user friendly interfaces for clinicians

Data Privacy & Security Experts: To ensure compliance with healthcare regulations

Maintenance Team: For ongoing support after development

Technical Resources:

Computing Infrastructure : Servers or cloud services for data storage, model training and hosting the application

Development Tools: IDESs, version control(Git), frameworks for ML (like Tensor flow), and software development

Databases: For storing patient data and risk classification results securely

Testing Tools: For automated and manual testing

Security Tools: Encryption, access control and monitoring tools

Data Resources:

Patient Medical Resources: Access to historical and real time patient data for training and testing

Health Risk Guidelines: Clinical guidelines or rules that define risk levels

Anonymized Datasets: For initial model training if live data is restricted

Financial Resources:

Budge for staff salaries, software licences, cloud computing costs, and any external consultations

Time Resources : Adequate project timeline allocated for each Waterfall phase: Requirements, design, development, testing, depoloyment and maintenance