Document 1: Definition of Done As Per Agile Extension to the BABOK® Guide v2, Definition of Done is a technique where the team agrees on, and prominently displays, a list of criteria which must be met before a backlog item is considered done. That is the team has to create a well-defined, unambiguous, measurable, agreed-upon, and shared Definition of Done between all team members. Nurturing Process – Agile Deliverables –V2D2 August 2024 www.coepd.com nurtureba@coepd.com CONFIDENTIAL Page 2 of 9 The best form of Definition of Done representation is a checklist of activities that has to demonstrate the agreed value and quality of a user story. So, this checklist should include: § acceptance criteria (to satisfy customer requirements for a product) § quality criteria (to satisfy quality requirements for a product) Definition of Done may be defined for different levels of project work. For example, in Agile / Scrum framework these levels of work could be user story, sprint, and release. Checklist for DOD: · Produced code for presumed functionalities · Assumptions of User Story met · Project builds without errors · Unit tests written and passing · Project deployed on the test environment identical to production platform · Tests on devices/browsers listed in the project assumptions passed · Feature ok-ed by UX designer · QA performed & issues resolved · Feature is tested against acceptance criteria · Feature ok-ed by Product Owner · Refactoring completed · Any configuration or build changes documented · Documentation updated · Peer Code Review performed

Answer: The Definition of Done (DoD) is the agreed set of criteria that must be met before a backlog item is considered complete. It ensures transparency, quality, and shared understanding across the Scrum team.

1. Produced code for presumed functionalities

- Features like automated ticket assignment, escalation rules, and dashboards are coded and working.

2. Assumptions of User Story met

- Each user story (e.g., “As a user, I want real-time ticket tracking…”) is fully satisfied.

3. Project builds without errors

- Code compiles and deploys

4. Unit tests written and passing

- Automation scripts ensure ticket routing, SLA timer, and reporting modules pass unit tests.

5. Project deployed on test environment identical to production

- Ticket system tested on cloud-hosted environment matching production setup.

6. Tests on devices/browsers listed in project assumptions passed

- Dashboards verified on Chrome, Edge, and mobile view (per stakeholder requirements).

7. Feature ok-ed by UX designer

- New ticket dashboard and interfaces validated by UX team for user-friendliness.

8. QA performed & issues resolved

- QA team verifies workflows: ticket creation, escalation, closure, and reporting.

9. Feature is tested against acceptance criteria

- Example: “Resolution time reduced by 30%” and “SLA ≥ 95% compliance” are validated.

10. Feature ok-ed by Product Owner

- Product Owner confirms functionality matches backlog priorities and sprint goals.

11. Refactoring completed

- Code optimized for maintainability (especially automation logic and integration APIs).

12. Any configuration or build changes documented

- LDAP/email integration steps, dashboard configuration, and deployment procedures documented.

13. Documentation updated

- User manuals, training guides, and support documents updated for adoption support.

14. Peer Code Review performed

- Developers review each other’s code for automation scripts, dashboard modules, and API integration.

Document 2- Product Vision

Answer:

Target group: Internal IT Teams (Support & Ops)

- Business users who raise tickets

- Customers needing timely resolutions

Needs: Current system is slow, manual, and lacks automation

- Poor visibility of ticket progress - High downtime

- Users dissatisfied with delays

Product: - Optimized Ticket Management System

- Features: automation, dashboards, SLA monitoring

- Desirable because it reduces downtime & improves transparency

- Feasible with Agile sprints, CI/CD, and stakeholder feedback

Value: - 30% faster ticket resolution

- SLA compliance ≥ 95% - Downtime reduced by 40%

- Scalable and cost-effective system

- Business model: improved productivity, higher customer satisfaction, and reduced operational costs

Document 3: User stories

User Stories

| User story No: 1 | Tasks: Implement auto-assignment rules for tickets Priority: High |
| --- | --- |
| Value statement: As a support manager, I want tickets to be automatically assigned to available agents so that I can reduce delays in response. |  |
| BV: 500 | CP: 8 |
| Acceptance criteria: System assigns tickets automatically based on agent availability and skillset. Manual reassignment by manager is possible. Assignment logic tested with at least 3 scenarios (new, reassigned, bulk). |  |

| User story No: 2 | Tasks: Enable ticket escalation workflow Priority: High |
| --- | --- |
| Value statement: As a user, I want tickets to escalate automatically if unresolved within SLA so that I can ensure timely resolution. |  |
| BV: 400 | CP: 5 |
| Acceptance criteria: Tickets escalate automatically when SLA breach occurs. Escalation triggers notifications to next level support and manager. Escalation time is configurable by admin. |  |

| User story No: 3 | Tasks: Create SLA compliance dashboard Priority: High |
| --- | --- |
| Value statement: As a manager, I want a dashboard showing SLA compliance so that I can track performance in real time. |  |
| BV: 500 | CP: 8 |
| Acceptance criteria: Dashboard shows SLA compliance percentage with drill-down by category. Data refreshes at least every 5 minutes. Filters available by agent, team, and time period. |  |

| User story No: 4 | Tasks: Build intuitive ticket submission form Priority: Medium |
| --- | --- |
| Value statement: As a user, I want a simple form to submit tickets so that I can quickly log issues. |  |
| BV: 200 | CP: 3 |
| Acceptance criteria: Form captures essential fields: title, description, category, and priority. Validation ensures mandatory fields cannot be skipped. Confirmation email sent to user after submission. |  |

| User story No: 5 | Tasks: Enable LDAP login integration Priority: High |
| --- | --- |
| Value statement: As an employee, I want to log in with my company credentials so that I don’t need to remember multiple passwords. |  |
| BV: 400 | CP: 8 |
| Acceptance criteria: Users can log in using LDAP credentials. Fallback login available for non-LDAP users. LDAP integration tested with multiple user roles. |  |

| User story No: 6 | Tasks: Provide ticket search and filters Priority: Medium |
| --- | --- |
| Value statement: As a user, I want to search and filter tickets so that I can find past issues easily. |  |
| BV: 200 | CP: 5 |
| Acceptance criteria: Users can search tickets by ID, status, or keywords. Filters include category, priority, and date range. Search results displayed within 2 seconds. |  |

| User story No: 7 | Tasks: Implement ticket history tracking Priority: Medium |
| --- | --- |
| Value statement: As an agent, I want to see full history of a ticket so that I can resolve it effectively. |  |
| BV: 200 | CP: 5 |
| Acceptance criteria: All ticket updates are recorded with timestamp and user details. History is visible as a timeline view. Changes are not editable after being logged. |  |

| User story No: 8 | Tasks: Develop email-to-ticket conversion Priority: High |
| --- | --- |
| Value statement: As a user, I want my emails to auto-convert into tickets so that I can save time. |  |
| BV: 400 | CP: 8 |
| Acceptance criteria: Incoming emails create tickets automatically with subject as title. Duplicate prevention ensures no multiple tickets for the same email. Attachments are preserved in the ticket. |  |

| User story No: 9 | Tasks: Build mobile-responsive UI Priority: Medium |
| --- | --- |
| Value statement: As a user, I want to access the system from mobile so that I can track tickets on the go. |  |
| BV: 100 | CP: 8 |
| Acceptance criteria: System adapts to mobile, tablet, and desktop screen sizes. All critical functions (submit, update, close) are mobile accessible. UI tested across iOS and Android browsers. |  |

| User story No: 10 | Tasks: Add ticket categorization & priority levels Priority: High |
| --- | --- |
| Value statement: As a manager, I want tickets categorized and prioritized so that I can allocate resources better. |  |
| BV: 400 | CP: 5 |
| Acceptance criteria: Tickets can be categorized into predefined categories. Priority levels (Low, Medium, High, Critical) are selectable. Categorization and priority shown in ticket list and reports. |  |

| User story No: 11 | Tasks: Build agent workload dashboard Priority: Medium |
| --- | --- |
| Value statement: As a manager, I want to see each agent’s workload so that I can balance assignments. |  |
| BV: 200 | CP: 5 |
| Acceptance criteria: Dashboard displays open, in-progress, and closed tickets per agent. Workload data refreshes in real-time. Export option available in CSV/Excel. |  |

| User story No: 12 | Tasks: Integrate reporting module (Excel export) Priority: Medium |
| --- | --- |
| Value statement: As a stakeholder, I want to export ticket reports so that I can analyze them offline. |  |
| BV: 100 | CP: 3 |
| Acceptance criteria: Reports can be exported in Excel and CSV formats. Exports respect applied filters (date, category, SLA). Generated reports are downloadable within 10 seconds. |  |

| User story No: 13 | Tasks: Enable role-based access control Priority: High |
| --- | --- |
| Value statement: As an admin, I want to define roles so that I can control access securely. |  |
| BV: 400 | CP: 8 |
| Acceptance criteria: Roles include Admin, Manager, Agent, and User. Permissions are enforced based on roles. Unauthorized access attempts are logged. |  |

| User story No: 14 | Tasks: Provide notification system (email/SMS) Priority: Medium |
| --- | --- |
| Value statement: As a user, I want notifications on ticket updates so that I stay informed. |  |
| BV: 100 | CP: 3 |
| Acceptance criteria: Email/SMS notifications triggered on ticket creation, update, and closure. Users can configure notification preferences. Notifications tested for different user roles. |  |

| User story No: 15 | Tasks: Add feedback & rating system Priority: Low |
| --- | --- |
| Value statement: As a user, I want to rate ticket resolution so that I can give feedback. |  |
| BV: 50 | CP: 2 |
| Acceptance criteria: Feedback form appears automatically after ticket closure. Ratings are stored and linked to ticket records. Reports can show average ratings per agent/team. |  |

Document 4: Agile PO Experience

Agile Product Owner (PO) Experience

The Product Owner (PO) plays a central role in Agile projects by bridging business needs and development teams. Their experience is built on domain/industry knowledge, understanding of market demand, and ability to translate vision into actionable backlog items.

Key Responsibilities of a Product Owner

- Market Analysis

  - Analyzes market demand and user needs.

  - Benchmarks against existing/similar products in the market.

- Enterprise Analysis

  - Performs due diligence on market opportunities.

  - Ensures product investment is viable and strategically aligned.

- Product Vision & Roadmap

  - Defines the product vision based on need and market analysis.

  - Creates a roadmap with high-level features and timelines.

- Managing Product Features

  - Balances stakeholder expectations.

  - Prioritizes epics, stories, and features based on criticality and ROI.

- Managing Product Backlog

  - Prioritizes user stories in the backlog.

  - Re-prioritizes based on evolving stakeholder needs.

  - Plans and maintains epics for long-term visibility.

- Managing Iteration Progress

  - Reviews sprint progress.

  - Re-prioritizes sprints/epics as needed.

  - Conducts retrospectives with the Business Analyst.

Agile Ceremonies Learned (PO Participation)

- Sprint Planning → Defining sprint goals and selecting backlog items.

- Daily Scrum → Staying aligned on sprint progress.

- Sprint Review → Demonstrating increment and gathering stakeholder feedback.

- Sprint Retrospective → Reflecting on improvement opportunities.

- Backlog Refinement → Reviewing and updating backlog items with details.

User Story Creation (PO Practice)

Each user story includes:

- Story No.

- Tasks.

- Priority.

- Acceptance Criteria.

- BV (Business Value) & CP (Complexity Points).

Summary of PO Role

The Product Owner:

- Acts as a liaison between business stakeholders and Scrum teams.

- Develops the product vision and breaks it into backlog items.

- Ensures the Scrum team builds maximum value features aligned to business goals.

- Continuously manages and refines the backlog, roadmap, and priorities to deliver ROI.

Document 5: Product and sprint backlog and product and sprint burndown charts

| User story ID | User story (Value statement) | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | As a support manager, I want tickets to be automatically assigned to available agents so that I can reduce delays in response. | Implement assignment rules, testing reassignment | High | 500 | 8 | Sprint 1 |
| 2 | As a user, I want tickets to escalate automatically if unresolved within SLA so that I can ensure timely resolution. | Configure SLA rules, escalation triggers | High | 400 | 5 | Sprint 1 |
| 3 | As a manager, I want a dashboard showing SLA compliance so that I can track performance in real time. | Build dashboard UI, integrate metrics | High | 500 | 8 | Sprint 2 |
| 4 | As a user, I want a simple form to submit tickets so that I can quickly log issues. | Design UI, add validations, send confirmation email | Medium | 200 | 3 | Sprint 1 |
| 5 | As an employee, I want to log in with my company credentials so that I don’t need to remember multiple passwords. | Connect with LDAP, test fallback login | High | 400 | 13 | Sprint 2 |
| 6 | As a user, I want to search and filter tickets so that I can find past issues easily. | Implement search API, add filters in UI | Medium | 200 | 5 | Sprint 2 |
| 7 | As an agent, I want to see full history of a ticket so that I can resolve it effectively. | Add log feature, display timeline | Medium | 200 | 5 | Sprint 2 |
| 8 | As a user, I want my emails to auto-convert into tickets so that I can save time. | Configure email listener, create tickets from emails | High | 400 | 8 | Sprint 3 |
| 9 | As a user, I want to access the system from mobile so that I can track tickets on the go. | Apply responsive design, test on devices | Medium | 100 | 8 | Sprint 3 |
| 10 | As a manager, I want tickets categorized and prioritized so that I can allocate resources better. | Implement categories, add priority tags | High | 400 | 5 | Sprint 1 |
| 11 | As a manager, I want to see each agent’s workload so that I can balance assignments. | Build workload dashboard | Medium | 200 | 5 | Sprint 2 |
| 12 | As a stakeholder, I want to export ticket reports so that I can analyze them offline. | Implement export to Excel/CSV | Medium | 100 | 3 | Sprint 3 |
| 13 | As an admin, I want to define roles so that I can control access securely. | Implement role-based access control | High | 400 | 8 | Sprint 3 |
| 14 | As a user, I want notifications on ticket updates so that I stay informed. | Build email/SMS notification system | Medium | 100 | 3 | Sprint 2 |
| 15 | As a user, I want to rate ticket resolution so that I can give feedback. | Add feedback form and rating system | Low | 50 | 2 | Sprint 3 |

Sprint Backlog (example for Sprint 1)

| User story ID | User story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| 1 | Auto-assign tickets | Build assignment rules | Dev A | In progress | 5 days |
| 1 | Auto-assign tickets | Testing & validation | QA 1 | Pending | 2 days |
| 2 | Ticket escalation workflow | Configure SLA triggers | Dev B | In progress | 4 days |
| 2 | Ticket escalation workflow | Notifications setup | Dev C | Pending | 2 days |
| 4 | Ticket submission form | Build form UI | Dev D | Done | 3 days |
| 4 | Ticket submission form | Add validation rules | Dev D | In progress | 2 days |
| 4 | Ticket submission form | Send confirmation email | Dev A | Pending | 2 days |
| 10 | Ticket categorization & priority | Implement categories | Dev B | In progress | 3 days |
| 10 | Ticket categorization & priority | Add priority tagging | Dev C | Pending | 2 days |

Document 6: Sprint meetings Meeting

Type 1: Sprint Planning meeting

| Date | 01-Oct-2025 |
| --- | --- |
| Time | 10:00 AM – 11:30 AM |
| Location | COEPD Project Room / MS Teams |
| Prepared By | Scrum Master |
| Attendees | Product Owner, Scrum Master, Developers (5), QA (2), Business Analyst |

Agenda Topics

| Topic | Presenter | Time allotted |
| --- | --- | --- |
| Review prioritized product backlog | Product Owner | 20 mins |
| Define Sprint Goal | Scrum Master | 15 mins |
| Select user stories for Sprint 1 | Development Team | 30 mins |
| Break down stories into tasks & estimation | Developers/QA | 25 mins |

Other Information

| Observers | Stakeholders (optional) |
| --- | --- |
| Resources | Product backlog, Jira board, Sprint planning tool |
| Special Notes | Sprint duration: 2 weeks; Definition of Ready applied |

Meeting Type 2: Sprint Review Meeting

| Date |  | 14-Oct-2025 |  |
| --- | --- | --- | --- |
| Time |  | 4:00 PM – 5:00 PM |  |
| Location |  | MS Teams |  |
| Prepared By |  | Scrum Master |  |
| Attendees |  | Product Owner, Scrum Team, Key Stakeholders |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| Sprint Goal achieved (auto-assignment + escalation working) | Ticket auto-assignment, SLA-based escalation | Stakeholder feedback captured | Prepare backlog items for Sprint 2 (SLA dashboard, LDAP login) |

Meeting Type 3: Sprint retrospective meeting

| Date | 15-Oct-2025 |
| --- | --- |
| Time | 11:00 AM – 12:00 PM |
| Location | COEPD Room / MS Teams |
| Prepared By | Scrum Master |
| Attendees | Scrum Team |

| Agenda | What went well | What didn’t go well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Team collaboration | Active participation, stories completed on time | Some dependencies delayed | How to improve cross-team dependency handling? | Sprint board |
| Tools & process | Jira boards effective, CI/CD pipeline stable | Few build failures | Need training on automation testing? | Confluence, Jira |

4. Daily Stand-up Meeting

| Question | Name/Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Developer 1 Developer 2 Developer 3 |  |  |  |  |  |  |  |
| What will you do today? | Developer 1 Developer 2 Developer 3 |  |  |  |  |  |  |  |
| What (if any) is blocking your progress? | Developer 1 Developer 2 Developer 3 |  |  |  |  |  |  |  |