## Slide 1
SKAGIT COUNTY WEBSITE DESIGN, DEVELOPMENT, AND HOSTING
Presentation by
Aswitha T C
10/3/2025

## Slide 2: Introduction
The current website is difficult to use and does not meet the County's goals for e-government, public communication, and streamlined operations. Skagit County wants to modernize its digital presence and provide a more user-friendly, feature-rich website for citizens. This is the County's initiative to find a vendor that can design, migrate, and host a new, user-friendly website that better serves the community.

## Slide 3: Goal of the Project
Skagit County (County) is requesting four (4) services related to the County website: (1)Professional design of the site; (2) Implementation of an infrastructure that allows County offices and departments to maintain their specific information within a common framework; (3) Ability to conduct business with the public; () Hosting of the County websites.
Provide simple and intuitive electronic access to public services, serve as a public communications tool, and streamline business operations.
Support e-government transactions such as online forms and applications, social media interconnectivity, and hosting videos to offer a more streamlined experience for the community and visitors.
Develop a welcoming, friendly, and professional website theme that allows designated staff to contribute, update, or manage the new site, while ensuring no web design company indicators are present on the website or in the underlying code.

## Slide 4: Project Objectives:
Enhance User Experience and Accessibility:
  90% of users rate the website as visually appealing, user-friendly, and intuitive, providing simple and easy access to public services.
  85% of citizens successfully complete online forms and applications, streamlining business operations and citizen interactions.
Improve Information Management and Collaboration
  95% of County offices and departments effectively maintain their specific information within the common website framework.
  80% of designated staff report ease of use and confidence in contributing, updating, and managing the new website content.
Expand Digital Capabilities and Engagement:
  75% of website visitors engage with the social media integration and video hosting capabilities.
  90% of citizens perceive the website as welcoming, friendly, and professional, while maintaining the County's branding and ownership.

## Slide 5: Success Criteria:
Improved Citizen Access and User Experience:
  90% of citizens report easy access to a wide range of public records, informational collateral, online forms, and downloadable documents.
  85% of users rate the website's user-friendly interface and intuitive navigation as "good" or "excellent" in enabling quick and efficient retrieval of required information and resources.
High Availability and Reliable Performance:
  99.9% uptime for the website platform, with minimal downtime and fast response times for users.
  80% reduction in average page load times compared to the existing website, ensuring consistent, low-latency access even during periods of high traffic.
  Enhanced Citizen Satisfaction:
    75% of citizens express an overall improvement in their satisfaction with the County's website and digital services, compared to the previous website.
    65% reduction in wait times and complaints related to accessing information or completing online transactions on the new website. 4.Efficient Internal Collaboration and Content Management:
      90% of County offices and departments report effective collaboration and seamless maintenance of their specific information within the common website framework.
      80% of designated staff indicate ease of use and confidence in contributing, updating, and managing the new website content.

## Slide 6: Waterfall Methodology and Approach for Skagit County Website Project:
5
Phase | Duration | Key Activities
Requirement Gathering | 2 Months | Conduct comprehensive stakeholder interviews and workshops to understand the County's requirements, goals, and expectations. Gather detailed functional and non-functional requirements, including user personas, use cases, and technical specifications. Establish clear project objectives, success criteria, and key performance indicators (KPIs).
Design | 3 Months | Develop the website's information architecture, navigation structure, and user interface design. Create wireframes, prototypes, and visual design mockups to capture the desired look and feel. Finalize the website theme and branding elements to ensure a welcoming, friendly, and professional appearance.
Development | 4 Months | Implement the website's content management system (CMS) and backend infrastructure to support County departments. Develop the frontend using responsive web design principles and accessible coding standards. Integrate e-government features such as online forms, social media connectivity, and video hosting capabilities.
Testing | 1 Month | Conduct comprehensive functional, usability, performance, and security testing. Validate that all system components and integrations perform as expected. Document and resolve any issues identified during testing.
User Acceptance Testing (UAT) | 1 Month | Engage County staff to perform user acceptance testing (UAT). Verify that the website meets business and user requirements. Address feedback and make final refinements before go-live.

## Slide 7: Resources
Project Manager (1)
Business Analyst (1)
UX/UI Designer (1)
Web Developer (2)
Quality Assurance Tester (1)
Technical Architect (1)
The timeline would be 1 year for this project
Project Timeline Budget Members
6
No more than $150,000.

## Slide 8: Website Building Needs
Programming Language
Based on the details provided, the primary programming language used for the Skagit County website project is PHP, as they are proposing to implement the Drupal content management system, which is built on PHP.
Since the solution is focused on creating a modern, user-friendly website for Skagit County, it can be inferred that the website will be accessible and compatible with all major web browsers, such as Google Chrome, Mozilla Firefox, Microsoft Edge, and Safari.
Text Editor
Text editor mentioned for the Skagit County website project is Visual Studio Code.
Web Browser

## Slide 9: Website Building Needs
Web Server
Apache HTTP Server
Nginx
Microsoft Internet Information Services (IIS)
Database
MySQL:
Drupal has extensive support and integration for MySQL, which is a popular open- source relational database.
Domain Hosting
AWS GovCloud is a specific AWS region designed to host sensitive data and regulated workloads for government agencies and contractors. This ensures the website will be hosted in a secure, government-compliant cloud environment.

## Slide 10: Risk and Dependencies
3
Risks: Inaccurate requirements could lead to scope creep and delays, especially in design and development phases, potentially increasing costs beyond the
$150,000 budget.
Risks: Technical integration issues with e-government features like online forms and video hosting might cause performance problems, affecting reliability and user experience.
Dependencies: Availability of County staff for requirement gathering, UAT, and content management is crucial, as delays in stakeholder input could halt progress in the Waterfall sequence.
Dependencies: Successful project execution relies on third-party tools for hosting and social media integration, as well as timely budget approvals, to ensure the 1-year timeline is met without compromising quality.

## Slide 11
Question
If you have any questions, you are welcome to ask now
Thank You