Mr. Henry a successful businessman wishes to develop an online agriculture products store to facilitate farmers to buy seeds, pesticides, and fertilizers from anywhere through internet connectivity. For the application, Mr Henry collaborate with Mr. Pandu and Mr. Doku. The website should be easily accessible on the online web / mobile application so that farmers and companies shall communicate with each other in order to facilitate fertilizers, seeds, pesticides. Mr. Henry has given this project through his company Soony to APT IT Solutions for a Budget of INR 2 Crores with a project timeline of 18 months under CSR Initiative.

Current problems faced by Mr. Henry and other farmers are:

- Procuring fertilizers which are important for farms.

- Difficulty in buying seeds for farming certain crops.

- Difficulty in buying pesticides as they reduce pests in crop.

Looking at current problems, Mr. Henry has team pulled in on-board.

Mr. Henry (Company – SOONY) has the following team:

- Mr. Pandu – Financial head.

- Mr. Dooku – Project Coordinator

- Mr. Peter – Stakeholder for project requirements

- Mr. Kevin – Stakeholder for project requirements

- Mr. Ben - Stakeholder for project requirements

Mr. Henry has allotted this project to APT It Solutions team:

APT It solutions has the following team:

- Mr. Karthik – Delivery Head

- Mr. Vandanam – Project Manager

- Ms. Juhi – Senior Java Developer

- Mr. Teyson – Java Developer 1

- Ms. Lucie - Java Developer 2

- Mr. Trucker - Java Developer 3

- Me. Bravo - Java Developer 4

- Mr. Mike -Network Admin

- Mr. John – DB Admin

- Mr. Jason – Testor

- Ms. Alekya – Testor

- Me (Shiva) – Business Analyst

BPM

- Goal – To bridge the gap between farmers and companies for convenience of buying quality seeds, fertilizers and pesticides and provide customer satisfaction.

- Inputs – Online buying platform like website and mobile app, market research and data about the particular product demand, marketing campaigns, legal requirement for selling agricultural products online.

- Resources – Software, Office, warehouse.

- Outputs – Revenue generation, customer reach & satisfaction.

- Activities – Customer service, branding of product, online advertisement, monitoring sales performance.

- Value – Customer satisfaction, Customer centric product delivery, availability of multiple products at a single place online.

Swot Analysis

Strengths							Weakness

One place to order all agricultural products online.	Dependencies on external vendors.

Strong delivery network.	Supply chain disruption.

User friendly application	Inventory management related issue

Opportunities	Threats

Add new products categories                                                       Entry of another big player in industry.

Market expansion by promotions                                                Situation like flood may impact demand

Feasibility Study

Technology – Java, payment gateways, security and API’s.

Hardware – web servers, Data servers, Load Balancers, Storage Devices.

Software – content management system, e-commerce platform, payment gateway, security application.

Resources – PM, BA, Developers, UI/UX Designers, Network engineers.

Budget – 2 Crores

Time Frame – 18 Months

Gap Analysis

Current State –

It’s just an idea of building a website and online application for delivering seeds, fertilizers and pesticides to farmers across India. There is no application / Website available as of now.

Desired State -

To build a website / Mobile app in order to to facilitate farmers to buy seeds, pesticides, and fertilizers from anywhere through internet connectivity.

Since new users are involved, Application should be user friendly. This new application should be able to accept the product (fertilizers, seeds, pesticides) details from the manufacturers and should be able to display them to the Farmers.

Farmers will browse through these products and select the products what they need and request to buy them and deliver them to farmers location.

All this has to be done within a budget of 2 Cr with a timeline of 18 months.

Risk Analysis

Internal Risks:

External vendors dependency risk.

Variable demand of fertilizers & pesticides could lead to Inventory management risk.

Technical issue / App downtime may result in bad customer experience.

External Risks:

Entry of a big player in market may result in sales volume contraction.

Changes in govt regulations in e-commerce industry might put an impact.

Poor internet connectivity and logistics infra in rural area could impact delivery.

BA Risks:

Inexperience in agricultural product domain.

Incomplete requirements.

Change in requirements.

Project Based Risks:

Scope creep risk.

Stakeholder communication gap.

Quality issues.

RACI MATRIX

| R / A / C / I | Name of the responsible person | Designation | Details |
| --- | --- | --- | --- |
| Responsible | Juhi | Senior Java Developer | Email -juhi@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Teyson, Lucie,Tucker, Bravo | Java Developer | Email -abc@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Doku | Project Coordinator | Email -doku@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Kartik | Delivery Head | Email -kartik@aptitsolutions.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Vandanam | Project Manager | Email -vandanam@aptitsolutions.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Mike | Network Administrator | Email -mike@aptitsolutions.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | John | Database Administrator | Email -john@aptitsolutions.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Jason, Alekya | Testor | Email -jason@aptitsolutions.com, Alekya@aptitsolutions.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Shiva | Business Analyst | Email - Shiva@aptitsolutions.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
| Accountable | Henry | Project Initiator & Sponsor | Email -henry@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Pandu | Financial Head | Email -pandu@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Vandanam | Project Manager | Email -vandanam@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Doku | Project Coordinator | Email -doku@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Shiva | Business Analyst | Email - Shiva@aptitsolutions.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Karthik | Delivery Head | Email -doku@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
| Consulted | Henry | Project Initiator & Sponsor | Email -henry@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Pandu | Financial Head | Email -pandu@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Doku | Project Coordinator | Email -doku@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Peter, Kevin, Ben | Stakeholders (Farmers) | Email -abc@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Vandanam | Project Manager | Email -vandanam@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
| Informed | Henry | Project Initiator & Sponsor | Email -henry@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Pandu | Financial Head | Email -pandu@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Doku | Project Coordinator | Email -doku@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Peter, Kevin, Ben | Stakeholders (Farmers) | Email -abc@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Kartik | Delivery Head | Email -doku@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Vandanam | Project Manager | Email -vandanam@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Juhi | Senior Java Developers | Email -juhi@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Teyson, Lucie,Tucker, Bravo | Java Developers | Email -abc@soony.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Mike | Network Administrator | Email -mike@aptitsolutions.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | John | Database Administrator | Email -john@aptitsolutions.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Jason | Testor | Email -jason@aptitsolutions.com Ph No- 9999999999 Reach out time – 9 am to 2pm |
|  | Alekya | Testor | Email -alekya@aptitsolutions.com Ph No- 9999999999, Reach out time – 9am to 12pm |

Business case document

- Why is this Project initiated?

This project is initiated to develop online agriculture products store so that farmers and companies shall communicate with each other in order to facilitate farmers to buy seeds, pesticides, and fertilizers from anywhere through internet connectivity.

- What are the current problems?

The farmers are finding it difficult to procure fertilizers which are very important for farm.

They are also facing problem in-case of buying seeds for farming certain crops. 
Further, lack of pesticides availability is also a concern as it reduces pests in crops.

- With this project, how many problems could be solved?

With this project we may solve various products availability concerns of the farmers and         provide them all the items at one place that too online where they could buy the required items and place the order as per their requirements at any given point of time with their mobile phone application or browser.

- What are the resources required?

We would require a dedicated team to build the online website and mobile application.

Further, staff, tele-callers, office, warehouse and inventory would be required for order management.

Logistical support and delivery partners would be required to support the shipment.

Trainers would be required to train the staff and handle online escalations.

- How much organizational change is required to adopt this technology?

We may require a significant organizational change as the company would require to adapt the e-commerce culture and would require trainers to train the tele-sales and other office staff for online sales and handle customer queries / escalations as farmers are often used to buy offline and may require help in making their purchases online.

There would be a shift towards more technology-driven and customer-centric approach and the company may have to invest more in logistical, and payment gateway integration etc.

- What is the time frame to recover ROI?

The timeframe to recover ROI would be 1 year.

- How to identify stakeholders?

We will be using a detailed RACI matrix to identify stakeholders and to see who is Responsible, who is accountable, who should be consulted and who should be informed during and after the project.

SDLC Methodologies

Dear Mr. Henry, there are four methodologies which we generally use, let me share some key pointers of them one by one with you -

- Sequential (Waterfall) –

Sequential or waterfall methodology is a liner and step-by-step approach where we must complete the current step before moving forward to next one.

It is best suited for Projects with well-defined, unchanging requirements

It is easy to understand and manage and it helps with clear documentations.

However, it has few drawbacks like it is Rigid to changes and the testing happens late in the project.

- Iterative (RUP) –

The iterative model is built on an approach in which we build a smaller version of the system, test it, get feedback and then improve it in repeated cycles.

It is best suited for projects where requirements are somewhat known but expected to evolve.

It provides early working models, change requirements are easy to handle in this model but it could be more resource-intensive. It requires careful planning for multiple iterations

- Evolutionary (Spiral) –

This model combines iterative cycles with risk management. Each cycle includes planning, risk analysis, development, and evaluation.

It is ideal for complex, high-risk projects where flexibility and risk assessment are critical.

- Agile (Scrum) –

Agile is an evolution of the iterative model. The Development in agile happens in short cycles (sprints, usually 2–4 weeks) with continuous feedback and collaboration.

It is highly flexible and adaptive and the work is broken into short sprints with continuous feedback and collaboration. Perfect for projects with changing requirements and fast delivery needs. It is best suited for projects with rapidly changing requirements, start-ups, or customer-driven products.

This model requires active customer participation and emphasis less on formal documentation.

SDLC Model

- Waterfall- The Waterfall model is a traditional software development methodology that follows a linear and sequential flow of phases, where each phase must be completed before moving to the next. It is named "Waterfall" because the process flows steadily downwards like a waterfall through different stages.

Requirement → Design → Development → Testing → Deployment.

It is best suited for Projects with well-defined, unchanging requirements

It is easy to understand and manage and it helps with clear documentations.

- V Model – The V model is an extension of the Waterfall model that emphasizes verification and validation processes alongside each development phase. It is characterized by its “V” shape, where the left side represents the development activities (verification) and the right side represents the corresponding testing activities (validation).

This model has some character sticks like Waterfall, the project progresses step-by-step, but with a testing phase planned for every development phase.

- Spiral – The Spiral model is a risk-driven, iterative, software development process that combines elements of both the Waterfall and Iterative models. It was introduced by Barry Boehm to address risks by breaking the project into smaller phases, called spirals, each involving planning, risk analysis, development, and evaluation.

- Scrum – The Scrum model is an Agile framework used for managing and completing complex projects through iterative and incremental development. It breaks work into small, manageable time-boxed cycles called Sprints (usually 2-4 weeks), allowing teams to deliver functional parts of the product frequently. The key features of this mode include fast delivery, responsiveness to change and frequent validation and involvement of stakeholders.

- RUP – The Rational Unified Process (RUP) is an iterative and incremental software development framework created by Rational Software (now IBM). It focuses on disciplined project management and development, emphasizing risk management, use-case driven design, and architecture-centric development.

Therefore, as a BA I suggest that Waterfall Methodology is best suited for this project.

Difference between Waterfall and V-Model

| Waterfall | V-Model |
| --- | --- |
| Linear approach, one phase after other. | Extension of waterfall where testing is planned in parallel with each development phase. |
| Testing is a separate phase after development. | Testing is done at every stage. |
| More rigid, changes are hard to incorporate once a phase is completed. | Slightly more flexible since defects/requirements issues are caught earlier due to early test planning. |
| Risks are often discovered late in the testing phase. | Risks are identified earlier due to verification at every stage |
| Water model is cost effective as compared to V-Model. | Expensive than waterfall model. |

* Reasons to choose Waterfall model over V-Model for this particular project –

- Waterfall model is best suited for small projects.

- Every process is well reviewed.

- If the e-commerce project has clear goals (e.g., listing products, adding cart, checkout, payment), requirements are fixed and predictable. Waterfall works best here since changes are unlikely and processes can be followed step by step.

- Since there is no existing website / App for this project and we have to build this project from scratch, Waterfall ensures that the entire system is designed end-to-end before development starts, which avoids messy reworks and gives a solid foundation for building a scalable platform.

Therefore, considering the above reasons, I as a Business Analyst will choose the Waterfall models for this project.

| Week 1 | Week 10 | Week 20 | Week 29 | Week 38 | Week 46 | Week 55 | Week 65 | Week 73 | Week 78 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RA |  |  |  |  |  |  |  |  |  |
|  | RG |  |  |  |  |  |  |  |  |
|  |  |  |  | Design |  |  |  |  |  |
|  |  |  |  |  | Coding |  |  |  |  |
|  |  |  |  |  |  |  | Testing |  |  |

GANTT Chart – Waterfall Model

| Resources | Week 1 | Week 10 | Week 20 | Week 29 | Week 38 | Week 46 | Week 55 | Week 65 | Week 73 | Week 78 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Business Analyst |  |  |  |  | 2 |  |  |  |  |  |
| Project Manager |  |  |  |  | 1 |  |  |  |  |  |
| Java Developers |  |  |  |  | 4 |  |  |  |  |  |
| Database Admin |  |  |  |  | 1 |  |  |  |  |  |
| Network Engineer |  |  |  |  | 1 |  |  |  |  |  |
| Operations/Support_Head |  |  |  |  | 2 |  |  |  |  |  |
| Testers |  |  |  |  | 2 |  |  |  |  |  |

GANTT CHART V-MODEL

Difference between fixed Bid and Billing Project

| Fixed Bid Project | Billing Project |
| --- | --- |
| In a fixed bid project, a price is agreed upon at the initiation for the entire project. | In a Billing project, payment is billed on actual hours worked. |
| Cost is known before the project starts. | Cost depends on efforts and time spent. |
| Client involvement is generally low in a Fixed bid project. | Client involvement is generally high in billing project. |
| Vendor bears more risk of cost overruns or delay. | Client bears risk of increased time/costs if scope changes. |
| Changes can be costly and require contract amendments. | Changes handled flexibly with ongoing adjustments. |
| Usually fixed and contractual. | Flexible based on progress and requirements. |
| Well-defined, smaller projects with clear requirements. | It is best suited for complex, evolving projects or long-term engagements. |

Daily Schedule - Design phase of a BA

| Time | Activity / Work Done |
| --- | --- |
| 9:00 AM - 10:00 AM | Review and validate requirement documents |
| 10:00 AM - 11:00 AM | Attend design walkthroughs and stakeholder meetings |
| 11:00 AM - 2:00 PM | Document design impacts and prepare specifications |
| 2:00 PM - 3:00 PM | Lunch break |
| 3:00 PM - 4:00 PM | Analyse business impact, update documentation |
| 4:30 PM - 5:00 PM | Communicate updates and clarify design queries |
| 5:00 PM - 6:00 PM | Final reviews and prepare for next day |

Daily Schedule - Development phase of a BA

| Time | Activity / Work Done |
| --- | --- |
| 9:00 AM - 10:00 AM | Participate in daily stand-ups, clarify dev questions |
| 10:00 AM - 12:00 PM | Review and clarify user stories |
| 12:00 PM - 2:00 PM | Evaluate & document change requests |
| 2:00 PM - 3:00 PM | Lunch break |
| 3:00 PM - 4:30 PM | Update requirements traceability and communicate |
| 4:30 PM - 6:00 PM | Attend sprint demos & provide feedback |

Daily Schedule - Testing phase of a BA

| Time | Activity / Work Done |
| --- | --- |
| 9:00 AM - 10:30 AM | Collaborate with QA, review test cases |
| 10:30 AM - 12:00 PM | Support testers, clarify requirements |
| 1:00 PM - 2:00 PM | Participate in defect triage meetings |
| 2:00 PM - 3:00 PM | Lunch break |
| 3:00 PM - 5:30 PM | Validate fixes and updated test results |
| 4:00 PM - 5:30 PM | Prepare test reports and progress tracking |

Daily Schedule - UAT phase of a BA

| Time | Activity / Work Done |
| --- | --- |
| 9:00 AM - 10:00 AM | Prepare and distribute UAT plans and instructions |
| 10:00 AM - 12:00 PM | Facilitate UAT test sessions with end users |
| 12:00 PM - 2:00 PM | Collect user feedback and log issues |
| 2:00 PM - 3:00 PM | Lunch break |
| 3:30 PM – 6:00 PM | Coordinate with teams on defect fixes |

Daily Schedule – Deployment and implementation phase of a BA

| Time | Activity / Work Done |
| --- | --- |
| 9:00 AM - 10:30 AM | Prepare deployment checklists and documentation |
| 10:30 AM - 12:00 PM | Coordinate deployment activities with teams |
| 12:00 PM - 2:00 PM | Provide post-deployment support and troubleshoot issues |
| 2:00 PM - 3:00 PM | Lunch break |
| 3:00 PM - 5:30 PM | Monitor adoption and gather user feedback |