## Slide 1: PROJECT BESCOM (Bangalore Electricity Supply Company Limited)
PREPARED BY: VENKATESH DHANANA
DATE: 16-06-2025

## Slide 2
Situation: BESCOM (Bangalore Electricity Supply Company Limited) currently uses an old SAP-based application to manage its electricity distribution operations across four zones in Karnataka, including Bangalore Urban and Rural. The application has been in place for years and lacks modern features, resulting in inefficiencies in handling consumer demands and operational processes. Recognizing the limitations of the legacy system, BESCOM has decided to upgrade its application using Java technology. They have partnered with Fluentgrid Ltd., a company with 20+ years of expertise in utility domain software, to implement a new Disconnection & Dismantling (D&D) module in Bangalore Urban.
Problem:
Legacy Technology: The existing SAP system is outdated and no longer meets the performance, stability and functionality requirements of BESCOM.
Operational Inefficiencies: Handling large volumes of consumer interactions and defaulters is challenging due to system instability and lack of automation.
Revenue Risk: Ineffective tracking of payment defaulters and delayed actions on non-payment leads to revenue leakage.
Manual Interventions: The current process involves significant manual effort for identifying defaulters, issuing notices, and tracking disconnection/reconnection, which is error-prone and time-consuming.
Opportunity:
System Modernization: Replacing the outdated SAP system with a robust Java-based application will enhance performance, scalability and reliability.
Automated D&D Process: Implementing the new D&D module will automate critical actions like defaulter identification, notice generation, disconnection, reconnection, dismantling, and arrear transfer—reducing manual errors and delays.
Improved Revenue Assurance: Timely disconnections and follow-ups on overdue payments will ensure better revenue collection.
Data-Driven Decisions: The new system will provide analytical reports for monitoring consumer behaviour, aiding in quicker and informed decision-making.
Scalability Across Zones: Once successful in Bangalore Urban, the module can be rolled out to other BESCOM zones, ensuring uniform and efficient operations state-wide.

## Slide 3
Purpose Statement:
The purpose of this project is to modernize BESCOM’s existing legacy SAP system by developing and implementing a robust, scalable, and efficient Java-based Disconnection & Dismantling (D&D) module for Bangalore Urban. The D&D module aims to streamline and automate the end-to-end process of handling defaulting consumers—right from defaulter identification to disconnection, reconnection, dismantling, and recovery of dues—thus improving operational efficiency, ensuring revenue assurance, and enabling data-driven decision-making across the utility domain.
The project aims to:
Modernize Legacy System: Replace the outdated SAP application with a more stable and technologically advanced Java-based platform.
Automate D&D Processes: Enable automated generation of defaulters list, issuance of payment notices, disconnection/reconnection, dismantling of services, and arrear recovery.
Ensure Revenue Collection: Improve payment compliance by enforcing timely actions on non-paying consumers to secure consistent revenue inflow.
Enhance Operational Efficiency: Reduce manual workload, errors, and delays through workflow automation and system-generated alerts/actions.
Provide Analytical Reporting: Deliver real-time reports and dashboards to monitor consumer status and operational KPIs for better strategic control.
Enable Scalable Deployment: Create a reusable and scalable module architecture that can be rolled out across other BESCOM zones in future phases.

## Slide 4
Project Objectives:
The objective of the BESCOM D&D (Disconnection & Dismantling) Module Implementation project is to design, develop, and deploy a modern, Java-based application to replace the legacy SAP system currently used by BESCOM, specifically targeting the automation of disconnection and dismantling processes across the Bangalore Urban region. The system aims to streamline and digitize critical workflows such as defaulter identification, notice issuance, disconnection, reconnection, dismantling of electricity connections, and arrear recovery.
The project intends to:
Enhance operational efficiency by minimizing manual interventions.
Improve revenue assurance by ensuring timely action on payment defaults.
Enable seamless consumer data management and enforce business rules consistently.
Provide actionable insights through real-time dashboards and reports for monitoring defaulters and service actions.
Establish a scalable framework that can be extended to other BESCOM zones in the future.

## Slide 5
Success Criteria:
To determine the successful completion of the BESCOM D&D (Disconnection & Dismantling) Module project, the following key success criteria will be used:
Functional Success Criteria:
Accurate Defaulter Identification
  System automatically generates defaulter lists based on predefined rules and billing data with 100% accuracy.
2. Automated Notice Generation & Tracking
  Notices for overdue payments are system-generated and delivered within SLA timelines, with status tracking enabled.
3. Execution of D&D Workflow
  Disconnection, reconnection, dismantling, and arrear transfer processes are successfully executed via system workflows, minimizing manual intervention.
4. User Acceptance Testing (UAT) Completion
  All test cases approved by BESCOM stakeholders during UAT phase without critical defects.
5. Compliance with BESCOM's Business Rules
  The system adheres to BESCOM’s internal policies and regulatory requirements.

## Slide 6
Technical Success Criteria:
System Performance & Stability
  The new Java-based system handles expected load with no crashes or performance degradation during peak hours.
Data Migration Accuracy
  Legacy SAP data (if applicable) is migrated accurately to the new system with validation reports.
Security & Access Control
  Proper authentication, role-based access, and audit trails are implemented as per IT security standards.
Business Success Criteria:
Improved Operational Efficiency
  At least 50% reduction in time taken for disconnection and arrear recovery processes compared to legacy system.
Revenue Recovery Increase
  Notable improvement in payment compliance and recovery rate of dues from defaulting consumers.
Stakeholder Satisfaction
  Positive feedback from BESCOM field officers, billing staff, and operations management on usability and reliability of the system.
On-Time, On-Budget Delivery
  Project completed within the planned 12-month timeline and approved budget.

## Slide 7
Agile Method/Approach:
For the BESCOM D&D Module Implementation Project, an Agile methodology would be a strong fit, especially considering the complexity of utility workflows, the need for iterative development, and frequent stakeholder feedback. Here's a recommended Agile Approach tailored to the scenario:
Agile Framework: Scrum
Given the structured team and long project timeline (12 months), the Scrum framework is ideal. It allows for:
  Incremental development of functional modules.
  Regular stakeholder reviews.
  Early identification and correction of issues.
  Better adaptability to regulatory or requirement changes.
Scrum Roles
Role | Responsibility
Product Owner (PO) | Represents BESCOM’s business interests, defines priorities, and manages product backlog. Likely a senior BESCOM officer or BA.
Scrum Master | Facilitates the process, removes blockers, ensures Agile principles are followed (can be from Fluentgrid Ltd).
Development Team | Java developers, DB team, testers, solution architects from Fluentgrid who deliver working software in sprints.

## Slide 8
Key Agile Artefacts:
  Product Backlog: Maintained by PO with prioritized user stories (e.g., Generate Defaulter List, Issue Notice, Disconnect Service, etc.)
  Sprint Backlog: Selected stories/tasks to be completed in a sprint.
  Increment: Working, testable features delivered at the end of each sprint.
  Definition of Done (DoD): Clearly defined conditions for story completion (coded, tested, documented, reviewed).
Agile Ceremonies:
Ceremony | Purpose
Sprint Planning | Plan 2–3 week sprints based on priority and team capacity.
Daily Stand-ups | 15-minute daily meetings to track progress and remove impediments.
Sprint Review | Demo of completed work to BESCOM stakeholders at end of each sprint.
Sprint Retrospective | Team reflects on what went well and identifies improvements.
Sprint Strategy
  Sprint Duration: 2 or 3 weeks.
  Number of Sprints: Approx. 18–24 sprints (for a 12-month project).
  Release Plan: Deliver in phases, for example:
    Sprint 1–4: Defaulter Identification & Notice Generation
    Sprint 5–8: Disconnection & Reconnection
    Sprint 9–12: Dismantling & Arrear Transfer
    Sprint 13–16: Admin & Reporting
    Sprint 17–20: Integration, UAT, and Deployment

## Slide 9
Agile Tools (Optional):
  JIRA: For backlog grooming, sprint tracking, and burndown charts.
  Confluence: For documentation and meeting notes.
  Slack/MS Teams: For quick team communication.
Benefits of Agile in This Project:
  Early delivery of functional features to BESCOM.
  Regular feedback from BESCOM stakeholders for better alignment.
  Improved quality due to continuous testing.
  Flexibility to adapt to regulatory changes or new feature requests.

## Slide 10
Resources for BESCOM Project
1. People (Human Resources):
From Fluentgrid Ltd.:
5 Java Developers – For coding and implementing core logic and integration.
1 Project Manager – Overall project coordination, scheduling, risk management.
2 Solution Architects – Designing system architecture and workflow blueprints.
3 Database Engineers – For DB schema design, performance tuning, and integration.
2 Admin (Infra/Deployment) Engineers – For environment setup, server management, and deployment.
3 Testers (QA Team) – Manual and automated testing, UAT support, and defect tracking
From BESCOM Stakeholders:
Business Analysts/Product Owner – To define and manage requirements.
Functional Heads – Provide D&D process insight and validate business flows.
IT Coordinators – Support from BESCOM side for data access, reviews, etc.
2. Time (Duration & Timeline):
Project Duration: 12 Months (1 Year)
Development Phases:
  Requirements & Planning: 1 month
  Design & Architecture: 1 month
  Incremental Development (Sprints): 7–8 months
  System Integration & Testing: 1.5 months
  UAT & Feedback Iterations: 1 month
  Final Deployment & Support Handover: 0.5 month
Sprint Cycle: 2 or 3-week sprints (Estimated ~20 sprints)

## Slide 11
3. Budget: Since the exact financials aren’t provided, we’ll estimate based on standard project costs for such utility-scale enterprise applications.
Total Estimated Budget: ₹2.5 to ₹4 Crores INR (approx.)
  Development Costs: ₹1.5–2 Cr
  Testing, Deployment, Support: ₹50–75 Lakhs
  Licenses/Tools/Infrastructure: ₹25–50 Lakhs
  Contingency/Change Requests: ₹25–50 Lakhs
4. Other Resources:
Tools/Software:
Development: Java, Spring Boot, Hibernate, IntelliJ/Eclipse
Database: Oracle/PostgreSQL
Version Control: Git, Bitbucket
Project Management: JIRA, Confluence
Testing Tools: Selenium, Postman, JMeter
Infrastructure:
Servers for Development, Testing, and Production Environments (Cloud or On-Prem)
Backup & Disaster Recovery setup
Training & Documentation:
User Manuals
Technical Documentation
BESCOM Staff Training Workshops

## Slide 12
Risks and Dependencies
Risks:
Risk | Description | Impact | Mitigation Strategy
Legacy System Data Complexity | Migrating from old SAP to the new Java-based system may involve complex, unstructured data. | High | Perform early data profiling, plan phased data migration with validation, involve DB experts from the start.
Requirement Volatility | BESCOM stakeholders may change or expand requirements mid-project. | High | Adopt Agile methodology for flexibility; maintain a well-prioritized product backlog.
Integration Issues | Integration with existing BESCOM systems or external payment systems may cause delays. | Medium | Identify all integration points early; use mock interfaces during development.
User Resistance to Change | Field staff or back-office users may resist adopting the new system. | Medium | Plan training programs, create user-friendly interfaces, involve key users early.
Performance Bottlenecks | New system might underperform during high load if not optimized. | High | Perform performance/load testing in advance; optimize DB queries and APIs.
Security and Access Risks | Unauthorized access or data leakage may occur if security controls are weak. | High | Implement role-based access, encryption, audit trails, and comply with IT security standards.
Delayed Feedback from BESCOM | Delays in UAT or requirement clarifications may impact timelines. | Medium | Set clear communication SLAs, schedule regular demos and stakeholder reviews.
Resource Unavailability | Key developers, testers, or business users may become unavailable. | Medium | Maintain a backup resource plan and knowledge transfer logs.

## Slide 13
Dependencies:
Dependency | Description | Impact if Delayed
BESCOM Stakeholder Availability | Continuous feedback and sign-offs are needed during sprints and UAT. | Delays in sprint delivery or requirement finalization.
Access to Existing SAP System | Required for understanding workflows and extracting legacy data. | Delays data migration and business logic design.
Fluentgrid Product Base | The new module may depend on existing Fluentgrid frameworks and APIs. | Integration or feature reuse may be delayed.
Infrastructure Readiness | Server provisioning, network setup, and staging environment availability. | Postpones development and testing activities.
External Regulatory/Policy Changes | Any new government guidelines or compliance rules (e.g., KERC regulations). | May lead to scope changes or rework.
Availability of BESCOM Field Users for UAT | UAT depends on real-world feedback from actual end-users. | UAT may be delayed or incomplete without end-user testing.

## Slide 14
Thank You !