## Slide 1: Conversion Canvas
Prepared By: K. Sai Mohan Krishna
Date:: 25 – 08 – 2025

## Slide 2: Situation
The organization has a digital product or platform (e.g., website, landing page, or app) that is receiving user traffic, but the conversion rate is lower than expected. This means visitors are not taking the desired actions — such as signing up, purchasing, or filling out a form — at a rate that aligns with business goals.
There is existing data (from analytics tools like Google Analytics, Hotjar, etc.) and qualitative feedback from users, but insights are scattered, and decisions lack a centralized strategy for improving conversions.

## Slide 3: Problem
Low Conversion Rates: Users are visiting the site/app but not converting, leading to poor ROI on marketing and traffic-generation efforts
Lack of Alignment: Stakeholders (product, marketing, UX, dev) are not aligned on what changes will have the biggest impact.
No Systematic Framework: There's no structured method in place to identify, prioritize, and test conversion improvements
Decisions Based on Assumptions: Optimization efforts are often based on opinions or isolated metrics, rather than validated user behavior or hypotheses

## Slide 4: Opportunity
Centralize Hypotheses and Testing: Use the Conversion Canvas as a collaborative framework to align teams on user behaviors, pain points, and high-impact ideas
Adopt Agile for Continuous Improvement: Apply Agile methodology (sprints, iterations, retrospectives) to rapidly test and evolve conversion hypotheses with data-backed learning's
Improve User Experience and Business Metrics: By identifying friction points and systematically improving them, increase conversions, user satisfaction, and ultimately revenue or other key goals
Cross-functional Collaboration: Foster shared ownership of conversion goals across design, development, and marketing teams

## Slide 5: Purpose Statement (Goals)
The purpose of the Conversion Canvas project is to systematically improve the conversion rate of our digital product by aligning cross-functional teams around user-centric insights, testing hypotheses through iterative Agile sprints, and making data-driven decisions that enhance both user experience and business performance

## Slide 6: Project Objectives
Identify and Understand User Pain Points: Use data (quantitative and qualitative) to uncover friction in the user journey that negatively impacts conversion
Develop a Conversion Hypothesis Backlog: Build and maintain a prioritized backlog of testable hypotheses using the Conversion Canvas framework
Run Iterative A/B or Multivariate Tests: Design and execute controlled experiments in Agile sprints to test hypotheses and measure their impact on conversion metrics
Enhance Cross-functional Collaboration: Foster better communication and shared responsibility between design, development, marketing, and analytics teams

## Slide 7: Success Criteria
Measurable Increase in Conversion Rate: Increase primary conversion metric (sign-ups, purchases, etc.) by 15% within 3 months
Validated Hypotheses with Positive ROI: At least X% of tested hypotheses result in statistically significant improvements
Established and Used Conversion Canvas Framework: Teams consistently use the Conversion Canvas to identify, prioritize, and track optimization ideas
Agile Sprint Cadence Maintained: Regular sprints are completed on time with conversion-focused deliverables

## Slide 8: Approach
We have to create User Stories and also assign BV and CP Values to it
Sprint: Be available to the development team to clarify user stories, business rules, and edge cases during the sprint.. Help testers understand the acceptance criteria and business expectations to validate stories. Help avoid adding unplanned features during the sprint.
Product Backlog: Work with stakeholders to gather and document business needs. Draft detailed user stories with clear acceptance criteria. Assist the Product Owner in prioritizing backlog items based on business value, urgency, and dependencies
Sprint Backlog: Help the team understand selected stories. Provide answers and additional documentation during the sprint.
Impediments Log: Identify business-related blockers e.g., missing decisions from stakeholders, unclear requirements, dependencies on other teams. Track and raise systemic blockers that may require process improvement.
Team Velocity: Help ensure that user stories are well-understood and estimated properly. Help analyze trends to understand scope feasibility and manage stakeholder expectations . Use velocity data to guide realistic planning for future sprints/releases
Product Grooming : Continuously update and clarify stories based on stakeholder feedback. Make sure stories are Independent, Negotiable, Valuable, Estimable, Small, and Testable. Lead or support grooming sessions with the dev team and PO. Maintain user flows, process maps, mockups, and business rules that support the stories

## Slide 9: Resources:
People: Project Manager; Product Owner; UX/UI Designers; Front-End & Back-End Developers; Data Analysts; QA/Testers
Time: The time taken to complete the project expected time for this project is 18 months
Budget: The estimated amount that taken to complete the project
Other – third party software evaluation, site visits, Dataquest reports – around $8000

## Slide 10: Risks and Dependencies :
Current platform and user experience have been in place for over 5 years and are familiar to existing users
Risk: Resistance to change from both internal stakeholders and returning users
Dependency: Clear communication, training, and gradual rollout of UX changes
Cost justification based on ease of use, improved conversion, and user behavior is difficult to quantify in traditional ROI terms
Risk: Management may struggle to see short-term tangible returns
Dependency: Need to present value through data-driven A/B test results, case studies, and cumulative gains
Cross-functional collaboration is essential, but conflicting team priorities may cause delays
Risk: Product, marketing, dev, and analytics teams may not align on timelines or goals
Dependency: Strong project leadership and clear sprint planning to manage shared responsibilities
Agile process adoption may be new or underutilized within the team
Risk: Teams unfamiliar with Agile may struggle with sprint planning, retrospectives, and iterative testing
Dependency: Initial Agile training and regular coaching by Scrum Master or Project Manager