Agile Documents

Document 1: Definition of Done

In Agile, the Definition of Done (DoD) is an agreed set of criteria that must be completed before any backlog item (user story, sprint, or release) can be considered as finished. It ensures transparency, consistent quality, and a common understanding of “Done” across the Scrum Team. A backlog item is not marked complete unless it meets both the acceptance criteria (business needs) and the quality criteria (technical standards).

Purpose of DoD:

- To avoid ambiguity about when a task is complete.

- To maintain high quality of deliverables.

- To build trust with stakeholders by ensuring increments are potentially shippable.

Checklist for SD Testing Project:
A backlog item will be considered “Done” only when the following checklist items are satisfied:

- Produced code for presumed functionalities
→ The required functionality (feature or user story) is coded and implemented in the system.

- Assumptions of User Story met
→ All conditions and assumptions mentioned in the user story are fulfilled.

- Project builds without errors
→ The software compiles and runs successfully without any technical errors.

- Unit tests written and passing
→ Unit test cases are created for the feature, and all tests pass successfully.

- Project deployed on the test environment identical to production platform
→ The feature is deployed in a testing environment that matches the production setup.

- Tests on devices/browsers listed in the project assumptions passed
→ Cross-device and cross-browser testing has been done and all tests are passed.

- Feature ok-ed by UX designer
→ The User Experience (UX) designer has reviewed the feature for usability and approved it.

- QA performed & issues resolved
→ Quality Assurance testing is completed and all identified issues are fixed.

- Feature is tested against acceptance criteria
→ The feature is verified against the acceptance criteria defined in the user story.

- Feature ok-ed by Product Owner
→ The Product Owner reviews the feature and gives approval.

- Refactoring completed
→ The code is optimized, cleaned, and improved without changing its functionality.

- Any configuration or build changes documented
→ All changes related to build or configuration are properly documented.

- Documentation updated
→ User manuals, system documentation, or analyst guides are updated with the new changes.

- Peer Code Review performed
→ The code is reviewed by another developer for quality, correctness, and best practices.

Document 2: Product Vision

| Scrum Project Name: | SD Testing |  |  |
| --- | --- | --- | --- |
| Venue: | APT IT Solution |  |  |
| Date: 11/09/2025 | Start Time: 10:00 AM | End Time: 01:00 PM | Duration: 3 Hours |
| Client: | SD Geotesting & Solutions |  |  |
| Stakeholder List: | Report Analyst, Inward Department, Quality Manager, Technical Manager, Senior Management |  |  |
| Scrum Team |  |  |  |
| Scrum Master: | Mr. Karthik |  |  |
| Product Owner: | Mr. Chetan |  |  |
| Scrum Developer 1: | Mrs. Vaishnavi |  |  |
| Scrum Developer 2: | Mr. Rushikesh |  |  |
| Scrum Developer 3: | Mrs. Neha |  |  |
| Scrum Tester 4: | Mrs. Shreya |  |  |
| Scrum Tester 5: | Mr. Pratik |  |  |

| Vision: What is your vision, your overarching goal for creating the product? |  |  |  |
| --- | --- | --- | --- |
| Target Group | Needs | Product | Value |
| Market Segment: Geotechnical testing industry, construction and engineering companies needing certified test reports. Target Users: Report Analysts, Quality Managers, Inward Staff, Managers, and Customers. | Problem Solved: Manual reporting is repetitive, error-prone, time-consuming, and old reports are hard to find. Benefit Provided: Quick and accurate report generation, instant retrieval, bulk printing, real-time dashboards, and digital approval. | Product: Centralized SD Testing software to manage letters, inward entries, reports, approval, and dashboards. Special Features: Bulk printing, instant search, digital approval, eco-friendly operations, real-time dashboards. Feasibility: Technically feasible, Agile Scrum used, budget ₹45,00,000, timeline 5–6 months. | Company Benefit: Saves time and resources, improves efficiency, enables urgent report delivery, and enhances customer satisfaction. Business Goals: Increase productivity, reduce manual errors, go paperless, and deliver timely reports. Business Model: Initially in-house use for SD Geotesting; scalable for other testing labs |

Document 3: User Stories

| User Story No.: 1 | Tasks: 2 |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a Staff, I want to create quotations after receiving letters so that I can record and track customer requests properly. |  |  |  |
| BV: 200 |  | CP: 3 |  |
| Acceptance Criteria: System should allow creating quotations linked with letters, store details correctly, and make them accessible for tracking and approval. |  |  |  |

| User Story No.: 2 | Tasks: 2 |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As an Inward Staff, I want to record customer letter details once so that I can avoid repetitive manual entries. |  |  |  |
| BV: 500 |  | CP: 4 |  |
| Acceptance Criteria: Inward entry must capture project, client, and letter details; generate unique inward number; and display data to Report Analysts instantly. |  |  |  |

| User Story No.: 3 | Tasks: 2 |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a Report Analyst, I want to generate reports by entering only readings so that I can save time and improve accuracy. |  |  |  |
| BV: 500 |  | CP: 5 |  |
| Acceptance Criteria: Report must be generated with correct client, project, and inward details; show accurate results; and save without needing repeated data entry. |  |  |  |

| User Story No.: 4 | Tasks: 2 |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a Quality Manager, I want to digitally approve or reject reports so that I can avoid draft prints and speed up approval. |  |  |  |
| BV: 200 |  | CP: 4 |  |
| Acceptance Criteria: Report must allow digital approval or rejection, save comments, update status instantly, and restrict further steps until approved. |  |  |  |

| User Story No.: 5 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Report Analyst, I want bulk printing so that I can save time and reduce paper usage. |  |  |  |
| BV: 50 |  | CP: 3 |  |
| Acceptance Criteria: Bulk printing must allow selecting multiple approved reports, generate them on official letterheads, and print successfully without manual repetition. |  |  |  |

| User Story No.: 6 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Staff/Manager, I want to search and retrieve reports so that I can fulfil urgent requests quickly. |  |  |  |
| BV: 100 |  | CP: 2 |  |
| Acceptance Criteria: System must allow searching by inward number, client, or date; display results within seconds; and open/download reports instantly. |  |  |  |

| User Story No.: 7 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Manager, I want a real-time dashboard so that I can monitor workload, productivity, and pending reports easily. |  |  |  |
| BV: 50 |  | CP: 4 |  |
| Acceptance Criteria: Dashboard must display real-time data on letters, reports, pending work, and analyst productivity with clear visual charts and filters. |  |  |  |

| User Story No.: 8 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As an Admin, I want to handle all data and check user profiles, so that I can manage system records easily. |  |  |  |
| BV: 100 |  | CP: 5 |  |
| Acceptance Criteria: - Admin can view all profiles. - Admin can edit/update/delete data. - All changes must be logged for security. |  |  |  |

| User Story No.: 9 | Tasks: 4 |  | Priority: Low |
| --- | --- | --- | --- |
| Value Statement: As a Report Analyst, I want to export reports into PDF, so that I can share reports with clients easily. |  |  |  |
| BV: 20 |  | CP: 1 |  |
| Acceptance Criteria: - Reports can be exported as PDF. - Exported file should keep correct formatting. - Export option should be available on dashboard. |  |  |  |

| User Story No.: 10 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Staff, I want to generate invoices, so that billing is accurate and easy. |  |  |  |
| BV: 100 |  | CP: 4 |  |
| Acceptance Criteria: - Staff can create invoices. - System saves invoices automatically. |  |  |  |

| User Story No.: 11 | Tasks: 3 |  | Priority: Low |
| --- | --- | --- | --- |
| Value Statement: As a Staff, I want to scan and upload letters, so that records are digital and safe. |  |  |  |
| BV: 10 |  | CP: 2 |  |
| Acceptance Criteria: - Staff can scan/upload letter images. - Uploaded files must be linked to entries. |  |  |  |

| User Story No.: 12 | Tasks: 3 |  | Priority: Low |
| --- | --- | --- | --- |
| Value Statement: As an Admin, I want QR codes on reports, so that reports can be verified digitally. |  |  |  |
| BV: 20 |  | CP: 1 |  |
| Acceptance Criteria: - QR code generated for each report. - Code links to digital copy. |  |  |  |

| User Story No.: 13 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Staff, I want to generate proforma invoices, so that I can share preliminary cost details. |  |  |  |
| BV: 100 |  | CP: 4 |  |
| Acceptance Criteria: - Proforma invoice can be created. - It is marked as “provisional.” |  |  |  |

| User Story No.: 14 | Tasks: 3 |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As an Accounts Staff, I want to update paid/unpaid amounts, so that financial records are accurate. |  |  |  |
| BV: 200 |  | CP: 3 |  |
| Acceptance Criteria: - Payment entries updated in system. - Unpaid amounts flagged automatically. |  |  |  |

| User Story No.: 15 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As an Admin, I want to see paid and unpaid amounts in one click, so that I can track finances quickly. |  |  |  |
| BV: 50 |  | CP: 4 |  |
| Acceptance Criteria: - Dashboard shows summary. - Data refreshes in real time. |  |  |  |

| User Story No.: 16 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Report Analyst, I want to correct printed reports, so that errors are fixed without rework. |  |  |  |
| BV: 100 |  | CP: 5 |  |
| Acceptance Criteria: - Analyst can request corrections. - Version history is stored |  |  |  |

| User Story No.: 17 | Tasks: 3 |  | Priority: Low |
| --- | --- | --- | --- |
| Value Statement: As a Manager, I want reports digitally signed, so that authenticity is ensured. |  |  |  |
| BV: 10 |  | CP: 4 |  |
| Acceptance Criteria: - Reports carry secure digital signatures. - Signatures verified on download. |  |  |  |

| User Story No.: 18 | Tasks: 3 |  | Priority: High |
| --- | --- | --- | --- |
| Value Statement: As a Staff, I want instant search for old reports, so that I can retrieve data quickly. |  |  |  |
| BV: 500 |  | CP: 3 |  |
| Acceptance Criteria: - Search by client/project/date. - Results shown instantly |  |  |  |

| User Story No.: 19 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Manager, I want a real-time dashboard so that I can monitor workload, productivity, and pending reports easily. |  |  |  |
| BV: 10 |  | CP: 4 |  |
| Acceptance Criteria: Dashboard must display real-time data on letters, reports, pending work, and analyst productivity with clear visual charts and filters. |  |  |  |

| User Story No.: 20 | Tasks: 3 |  | Priority: Low |
| --- | --- | --- | --- |
| Value Statement: As an Admin, I want role-based access, so that users only see their tasks. |  |  |  |
| BV: 10 |  | CP: 4 |  |
| Acceptance Criteria: - Roles defined (Admin, Staff, Analyst). - Permissions applied automatically. |  |  |  |

| User Story No.: 21 | Tasks: 3 |  | Priority: Low |
| --- | --- | --- | --- |
| Value Statement: As a Staff, I want notifications for tasks, so that I don’t miss updates. |  |  |  |
| BV: 10 |  | CP: 2 |  |
| Acceptance Criteria: - Notifications shown in system. - Alerts for pending tasks. |  |  |  |

| User Story No.: 22 | Tasks: 3 |  | Priority:Medium |
| --- | --- | --- | --- |
| Value Statement: As an Admin, I want an audit log, so that all activities are tracked. |  |  |  |
| BV: 50 |  | CP: 3 |  |
| Acceptance Criteria: - All changes logged with date/time. - Admin can view logs anytime. |  |  |  |

| User Story No.: 23 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Quality Manager, I want to approve digital reports, so that quality is assured. |  |  |  |
| BV: 100 |  | CP: 3 |  |
| Acceptance Criteria: - Manager can approve reports. - Approval status visible to team. |  |  |  |

| User Story No.: 24 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Manager, I want a real-time dashboard, so that I can monitor progress instantly. |  |  |  |
| BV: 100 |  | CP: 3 |  |
| Acceptance Criteria: - Dashboard updates in real time. - Key metrics displayed clearly. |  |  |  |

| User Story No.: 25 | Tasks: 3 |  | Priority: Medium |
| --- | --- | --- | --- |
| Value Statement: As a Staff, I want to track letters, so that no document is lost. |  |  |  |
| BV: 50 |  | CP: 3 |  |
| Acceptance Criteria: - Letters have tracking IDs. - Status updated automatically. |  |  |  |

Document 4: Agile PO Experience

- Market Analysis
The Product Owner performs market analysis to identify the current market demand and customer needs. This involves understanding industry trends, analyzing the availability of similar products, and recognizing potential gaps that the product can fulfill. The PO ensures that the product being developed will stay competitive in the market and provide real business value.

- Enterprise Analysis
The PO also engages in enterprise analysis by conducting due diligence on the market opportunity. This includes validating whether the business opportunity is worth pursuing, estimating potential revenue, and aligning the product with organizational strategy. This step helps to confirm that the product is not only technically feasible but also financially and strategically viable.

- Product Vision and Roadmap
A critical responsibility of the Product Owner is to define the Product Vision. The vision is created by keeping in mind the results of market and enterprise analysis. It outlines the overarching goal and the purpose of the product. Along with vision, the PO also creates the Product Roadmap, which provides a high-level timeline and lists the key features and milestones of the product. This roadmap acts as a guiding document for the team and stakeholders.

- Managing Product Features
The PO is responsible for managing stakeholder expectations and ensuring that the right features are developed in the right order. Since not all features can be delivered at once, the PO prioritizes epics, features, and user stories based on business criticality, customer importance, and Return on Investment (ROI). This ensures that the Scrum Team works on the highest-value features first, maximizing the benefit to the business.

- Managing the Product Backlog
The Product Backlog is the heart of Agile development, and the PO has complete responsibility for it. The PO manages the backlog by:

- Adding new user stories as requirements emerge.

- Prioritizing stories based on business value.

- Re-prioritizing items when stakeholder needs or market conditions change.

- Planning epics and breaking them down into smaller, manageable user stories.
This continuous backlog refinement ensures that the Scrum Team always has a clear and prioritized list of work.

- Managing Overall Iteration Progress
The PO is actively involved in monitoring and guiding the progress of the team during sprints. This includes:

- Sprint Progress Review: Tracking the work completed during the sprint and checking alignment with the sprint goal.

- Re-prioritization of Sprints/Epics: If stakeholder needs change or urgent requirements arise, the PO may re-prioritize backlog items even during the project.

- Sprint Retrospectives with the Business Analyst: Working closely with the BA to capture lessons learned, identify improvements, and ensure continuous improvement in the next sprint.

From this project, as a Product Owner, I have learned how to handle and participate effectively in all the major Scrum meetings. Each meeting has a clear purpose and helps ensure transparency, collaboration, and continuous improvement. Below is a detailed explanation:

### 1. Sprint Planning Meeting

- Purpose: To define the Sprint Goal and decide which Product Backlog items should be selected for the sprint.

- PO’s Role:

  - Explain the prioritized backlog items and their business value.

  - Clarify doubts from the Development Team regarding scope or acceptance criteria.

  - Collaborate with the team to break user stories into tasks.

- Learning: I learned how to balance business priorities with team capacity, ensuring that realistic commitments are made.

### 2. Daily Scrum Meeting (Daily Stand-up)

- Purpose: A short 15-minute meeting held daily to align the team and identify obstacles.

- PO’s Role: Normally the PO does not lead the meeting, but when invited, the PO listens to team updates and clarifies requirements if needed.

- Three Key Questions asked by each team member:

  - What did you do yesterday?

  - What will you do today?

  - Are there any impediments blocking your progress?

- Learning: I understood the importance of short, focused communication and how daily updates help in early identification of risks or blockers.

### 3. Sprint Review Meeting

- Purpose: To demonstrate the working product increment to stakeholders and collect feedback.

- PO’s Role:

  - Accept or reject completed backlog items based on the Definition of Done and acceptance criteria.

  - Facilitate stakeholder feedback and ensure that new requirements are added to the Product Backlog.

- Learning: I learned how to evaluate increments, engage stakeholders, and ensure the product is moving in the right direction.

### 4. Sprint Retrospective Meeting

- Purpose: To reflect on the sprint and identify improvements for the next sprint.

- PO’s Role:

  - Collaborate with the Scrum Master and team to analyze what went well and what needs improvement.

  - Support action items for process improvements.

- Learning: I experienced how retrospectives build a culture of openness, continuous learning, and teamwork.

### 5. Backlog Refinement Meeting

- Purpose: To prepare and refine the Product Backlog for future sprints.

- PO’s Role:

  - Break down epics into smaller user stories.

  - Add acceptance criteria and clarify details for each item.

  - Prioritize items by business value, ROI, and stakeholder needs.

- Learning: I learned that continuous refinement keeps the backlog updated, reduces uncertainty, and ensures the team always has clear and well-defined stories to work on.

User Stories Creation

As a Product Owner, one of the most important responsibilities is the creation and management of User Stories. User Stories are the smallest units of work in Agile-Scrum, which describe a requirement from the perspective of the end-user. They follow the format:

“As a [user], I want to [do something], so that [I get benefit].”

Each User Story is detailed enough to give clarity to the Development Team, but flexible enough to allow collaboration and discussion.

### Key Elements Included in User Stories

- Story Number

  - Each story is given a unique identifier (e.g., US-01, US-02).

  - This makes tracking, referencing, and backlog management easier.

- Tasks

  - Each User Story is broken down into smaller technical or functional tasks.

  - These tasks describe how the story will be implemented during the sprint.

- Priority

  - Every User Story is assigned a priority based on business needs and customer urgency.

  - High-priority stories are taken in earlier sprints to deliver maximum value quickly.

- Acceptance Criteria

  - Clearly defined conditions that must be satisfied for the story to be considered complete.

  - It ensures transparency between Product Owner, team, and stakeholders.

- BV (Business Value) and CP (Complexity Points)

  - BV (Business Value): Assigned using techniques like the 100$ allocation method to indicate the relative importance of each story.

  - CP (Complexity Points): Assigned using estimation techniques like Planning Poker to measure the effort and complexity of completing the story.

In Scrum, the Product Owner (PO) plays a crucial role as the liaison between different areas of the organization. The PO ensures smooth communication and alignment across all stakeholders, management, and the Scrum Team.

- Liaison Between Business Stakeholders and Scrum Team

- The Product Owner continuously communicates with business stakeholders such as managers, customers, and end-users to understand their requirements, pain points, and priorities.

- At the same time, the PO works closely with the Scrum Team, including Developers, Testers, and the Scrum Master, to clarify requirements, answer questions, and ensure that the team is always working on the most valuable items.

- By acting as the single point of contact, the PO keeps all areas of the business informed about the project’s progress, upcoming releases, and product roadmap.

- This bridging role reduces misunderstandings, aligns business goals with technical implementation, and ensures transparency throughout the project.

- Developing Vision of the Product

- Another important responsibility of the Product Owner is to develop a clear vision of the product’s function, purpose, and operation.

- The vision serves as the guiding principle for the Scrum Team and helps them understand why a feature is being built, not just what needs to be built.

- A well-defined vision also inspires the team and keeps stakeholders aligned with long-term objectives.

- Defining Product Features and Creating Product Backlog Items

- Based on the product vision and stakeholder input, the PO defines high-level product features.

- These features are then broken down into smaller, actionable Product Backlog Items (PBIs) such as epics and user stories.

- Each backlog item is prioritized based on business value, urgency, and technical feasibility, ensuring that the most important features are delivered first.

- The PO also ensures that backlog items are refined with acceptance criteria, estimated effort (CP), and clear definition of done.

Document 5: Product and sprint backlog and product and sprint burndown charts

Product Backlog:

| User Story ID | User Story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US01 | Create Quotation from customer letter | Create quotation form, link with letter | High | 15 | 3 | Sprint 1 |
| US02 | Inward Entry | Record client/project details, generate inward number | High | 20 | 4 | Sprint 1 |
| US03 | Report Generation | Enter readings, auto-generate report | High | 20 | 5 | Sprint 1 |
| US04 | Digital Approval | Approve/reject report with comments | High | 15 | 4 | Sprint 2 |
| US05 | Bulk Printing | Print multiple approved reports together | Medium | 10 | 3 | Sprint 2 |
| US06 | Search Reports | Search by inward no., client, or date | Medium | 10 | 2 | Sprint 3 |
| US07 | Dashboard | Show productivity, pending work, reports | Medium | 10 | 4 | Sprint 3 |

Sprint Backlog:

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US01 | Create Quotation from customer letter | Create quotation form, link with letter | Mr. Rushikesh | In Progress | 8 Hrs. |
| US02 | Inward Entry | Record client/project details, generate inward number | Mrs. Neha | Done | 12 Hrs. |
| US03 | Report Generation | Enter readings, auto-generate report | Mrs. Vaishanavi | Pending | 16 Hrs. |

Document 6: Sprint Meetings

Meeting type 1: Sprint planning meeting

| Date | 11/09/2025 |
| --- | --- |
| Time | 10:00 AM - 12:00 PM |
| Location | Conference room (APT IT Solution) |
| Prepared By | Scrum Master |
| Attendees | Product owner, Scrum master, Development team |

Agenda Topics

| Topic | Presenter | Time Alloted |
| --- | --- | --- |
| Introduction & Sprint Goal Discussion | Product Owner | 15 Min. |
| Review of Product Backlog Items | Product Owner | 30 Min. |
| Estimation of User Stories | Development Team | 30 Min. |
| Task Breakdown and Assignment | Development Team | 20 Min. |
| Capacity Planning and Final Commitment | Scrum Master | 20 Min. |

Other Information

| Observer | Stakeholders |
| --- | --- |
| Resources | Product Backlog, Estimation Card, Sprint Board |
| Special Notes | Team committed to 6 backlog items, Sprint goal finalized and agreed by all |

Meeting Type 2: Sprint review meeting

| Date | 25/09/2025 |
| --- | --- |
| Time | 03:00 PM – 4:30 PM |
| Location | Conference room/Zoom (APT IT Solution) |
| Prepared By | Product Owner |
| Attendees | Product Owner, Scrum Master, Development Team, Key Stakeholders, QA |

| Sprint Status | Things to Demo | Quick Updates | What’s Next |
| --- | --- | --- | --- |
| 3 out of 7 backlog items completed, 4 carried forward to next sprint | - Generate Quotation functionality - Demonstration of new Reporting Feature - Inward Entry Module | Stakeholders suggested adding export-to-PDF option; minor UI changes required | Add pending backlog item to Sprint 2; prioritize export-to-PDF feature; backlog reprioritization planned |

Meeting Type 3: Sprint retrospective meeting

| Date | 27/09/2025 |
| --- | --- |
| Time | 04:00 PM – 5:00 PM |
| Location | Conference room/Zoom (APT IT Solution) |
| Prepared By | Scrum Master |
| Attendees | Product Owner, Scrum Master, Development Team, QA |

| Agenda | What went well | What didn’t go well | Questions | Reference |
| --- | --- | --- | --- | --- |
| Sprint Reflection & Process Improvement | 3 out of 7 user stories completed successfully Team collaboration was good Communication with PO was clear and timely | 1 story (Report Generation ) carried forward Testing faced delays due to environment issues | 1. How can we plan better for complex stories like report generation? 2. How to ensure test environment is stable from day one? | Action items noted in Confluence; Environment fixes assigned to QA Re-estimation process improved for Sprint 2 |

Meeting Type 4: Daily Stand-up Meeting

| Question | Name/Role | Week 1 (01/09/2025 to 07/09/2025) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| What did you do yesterday? | Mr. Rushikesh(Developer | Completed quotation form design | Linked quotation with letter | Fixed quotation validation errors | Updated UI for quotation | Reviewed completed stories | - | - |
|  | Mrs. Neha(Developer) | Entered inward details for 3 clients | Generated inward numbers | Validated client/project entries | Updated inward module | Peer tested inward entries | - | - |
|  | Mr. Pratik(Developer) | Created draft report template | Entered test readings | Auto-generated sample report | Fixed formatting issues | Coordinated with QA for review | - | - |
| What will you do today? | Mr. Rushikesh(Developer | Link quotation with inward module | Test quotation workflow | Finalize quotation feature | Support QA in testing | Close pending quotation story | - | - |
|  | Mrs. Neha(Developer) | Validate inward entries | Prepare inward test data | Document inward workflow | Assist QA for defects | Close inward module | - | - |
|  | Mrs. Shreya(Developer) | Refine report template | Add approval option | Integrate with dashboard | Prepare for demo | Support sprint review | - | - |
| What(if any) is blocking your progress | Mr. Rushikesh(Developer | None | Testing environment issue | Resolved environment issue | None | None | - | - |
|  | Mrs. Neha(Developer) | Waiting for test data | Dependency on report module | None | None | None | - | - |
|  | Mrs. Vaishnavi(Developer) | Dependency on QA test environment | Delay in sample data | Fixed data issue | None | None | - | - |