## Sheet1
Task | person involved | start date | end date | Week 12 to 18 | person name
complete responsibility of the project end to end | project manager | 2025-01-11 | 2027-01-05 | 1 to 72 | Vandanam
complete responsibility of the project end to end | Business analyst | 2025-01-11 | 2027-01-05 | 1 to 72 | me
to develop the functionality of the project | JAVA developer | 2026-10-01 | 2027-10-03 | 10 to 65 | Teyson, Lucie, Tucker, Bravo and Juhi senior
support and fecilitate the develppers and testers with the applications, backup etc.. | operation/support | 14/12/2025 | 2027-01-05 | 7 | network admin Mike DB admin John
test the work done by the developers | Testers | 19/7/2026 | 2027-01-05 | 38 | Jason, Alekya
he will design the complete website with the functionality given by the developers | network setup | 2025-01-11 | 2027-01-05 | 1 to 72 | network admin Mike DB admin John

## Sheet2
Team members | week 1 | week 10 | week 20 | week 29 | week 38 | week 46 | week 55 | week 65 | week 70 | week 75 | Number people involved | Task
project manager | [10 empty] | 1 | complete responsibility of the project end to end
Business analyst | [10 empty] | 1 | complete responsibility of the project end to end
JAVA developer | [10 empty] | 4 | to develop the functionality of the project
operation/support | [10 empty] | 1 | support and fecilitate the develppers and testers with the applications, backup etc..
Testers | [10 empty] | 2 | test the work done by the developers
network setup | [10 empty] | 1 | he will design the complete website with the functionality given by the developers