# Document 1: Definition of Done

# Project:

Delta Sales Operations Management Portal (DSOMP)

# Prepared By:

CR Barath Narayanan – Lead Business Analyst & Scrum Master

# Date:

13 August 2025

# Purpose:

The Definition of Done ensures that all project deliverables — at the User Story, Sprint, and Release levels — meet agreed-upon, measurable, and unambiguous completion criteria. This guarantees the quality, usability, and value of the product to stakeholders, while aligning with Delta Healthcare’s strategic goal of digitizing and optimizing sales operations.

# Levels of DoD:

## User Story Level:

A User Story is considered “Done” when:

- All acceptance criteria are met and verified by QA.

- All assumptions documented in the story are satisfied.

- Code for the story’s functionalities is produced.

- Code builds without errors in the CI/CD pipeline.

- Unit tests are written, pass successfully, and have sufficient coverage.

- Peer Code Review is performed and approved.

- Feature is deployed to the test environment identical to the production environment.

- Tests on all targeted browsers/devices listed in project assumptions are passed.

- UX Designer has reviewed and approved the feature.

- Documentation (user guide, technical notes) is updated.

- Any configuration or build changes are documented.

- Product Owner has formally approved the story.

## Sprint Level:

A Sprint is considered “Done” when:

- All committed User Stories for the Sprint meet the User Story DoD.

- Regression testing is completed across all relevant modules.

- Sprint deliverables are integrated into the main codebase without build errors.

- The working increment is demonstrated during Sprint Review and accepted by stakeholders.

- Any defects found during Sprint QA are resolved or added to the backlog with stakeholder awareness.

- Relevant operational and release notes are prepared.

## Release Level:

A Release is considered “Done” when:

- All included Sprints meet the Sprint DoD.

- End-to-end testing is completed and passed in a staging environment identical to production.

- All non-functional requirements (performance, scalability, security) are met.

- All compliance and audit requirements are satisfied.

- Product Owner and key stakeholders sign off for release.

- Deployment to production is completed without critical issues.

- User documentation and training materials are delivered.

- Post-release monitoring plan is in place.

# DoD Checklist:

## Produced Code for Presumed Functionalities

All development tasks for the User Story are completed, and the code delivers the intended functionality described in the story. No partial or placeholder code is left behind.

## Assumptions of User Story Met

Any stated assumptions (technical, business, or environmental) in the User Story are validated and satisfied before marking it complete.

## Project Builds Without Errors

The build process in the CI/CD pipeline completes successfully with no compilation errors or unresolved dependencies.

## Unit Tests Written and Passing

Unit tests are created for all new or modified code and pass consistently. The test coverage meets the agreed team standard.

## Project Deployed on the Test Environment Identical to Production Platform

The functionality is deployed in a staging/test environment that mirrors production in configuration and setup to ensure accurate validation.

## Tests on Devices/Browsers Listed in the Project Assumptions Passed

The feature is tested across all devices and browsers specified in project requirements, and all tests pass without critical issues.

## Feature OK-ed by UX Designer

The UX designer reviews the implementation to ensure alignment with approved wireframes, style guides, and user experience standards.

## QA Performed & Issues Resolved

Quality Assurance testing is conducted, all defects found are resolved, and retesting confirms the fixes before moving forward.

## Feature is Tested Against Acceptance Criteria

The feature meets every acceptance criterion documented in the User Story, as validated by the QA and Product Owner.

## Feature OK-ed by Product Owner

The Product Owner reviews and approves the delivered feature as “done” during Sprint Review or prior to release.

## Refactoring Completed

Any necessary refactoring identified during development or review is carried out to maintain code quality and reduce technical debt.

## Any Configuration or Build Changes Documented

Changes in environment settings, build parameters, or system configuration are recorded for future maintenance and deployment.

## Documentation Updated

Both technical documentation and user-facing materials are updated to reflect the new feature and any changes in workflows.

## Peer Code Review Performed

The code is reviewed by at least one other developer, feedback is addressed, and the review is approved before merging into the main branch.

# Visibility & Governance:

- The DoD will be prominently displayed in the team’s Jira/Azure DevOps board.

- The Scrum Master will ensure DoD compliance during Sprint Reviews.

- Any exceptions to the DoD will require documented approval from the Product Owner.

# Document 2: Product Vision

| Scrum Project Name | Delta Sales Operations Management Portal (DSOMP) |  |  |
| --- | --- | --- | --- |
| Venue | Delta Healthcare Headquarters, Vadodara |  |  |
| Start Date | 13 Aug. 25 | Start time | 10:00 AM |
| End Date | 30 Nov. 25 | End Time | 5:00 PM |
| Duration | 3 Months, 21 Days |  |  |
| Client | Delta Healthcare – Sales & Operations Division |  |  |
| Stakeholder list | - Director of Sales & Operations – Mr. Ramesh - National Sales Head – Mr. Mithun - IT & Support Team Lead – Mr Jayanth - Regional Sales Managers - Field Sales Representatives |  |  |
| Scrum Team |  |  |  |
| Scrum Master |  | Barath Narayanan |  |
| Product Owner |  | Mr. Ramesh |  |
| Scrum Developer 1 |  | Arjun Menon |  |
| Scrum Developer 2 |  | Ravi Prakash |  |
| Scrum Developer 3 |  | Sameer Kulkarni |  |
| Scrum Developer 4 |  | Karthik Iyer |  |
| Scrum Developer 5 |  | Mohit Sharma |  |
| Vision | To create an agile, user-friendly, and scalable Sales Operations Management Portal that replaces manual workflows, enhances operational efficiency, and empowers Delta Healthcare’s sales teams with real-time data for faster, smarter decision-making. |  |  |
| Target Group | Needs | Product | Value |
| - Primary segment: product sales team, management, operations team. - Target users: Field Sales Representatives, Sales Managers, and Operations & finance managers | - Eliminate inefficiencies caused by manual reporting and fragmented communication. - Provide a single source of truth for sales operations. - Improve approval turnaround times. | - Agile-based, modular Sales Operations Portal (web + mobile). - Features: Meeting reporting, quotation generation, leave & expense workflows, demo product booking, dashboards. - Designed for high scalability and adaptability to future enhancements. | - 50% reduction in reporting time. - Real-time data access improves decision-making speed. - Supports digital transformation goals. - Business model: SaaS-style internal deployment with minimal operational downtime. |

# Document 3: User Stories

| User story No | 1 | Tasks | Design and develop meeting reporting module | Priority | High |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a sales representative, I want to submit my meeting details digitally so that I can avoid manual reporting and save time. |  |  |  |  |
| BV | 9 |  | CP | 5 |  |
| Acceptance criteria |  |  |  |  |  |
| - Sales rep can log meeting details from web and mobile - Data auto-saves in real-time to the system. - Confirmation message shown after successful submission. |  |  |  |  |  |

| User story No | 2 | Tasks | Implement quotation generator feature | Priority | High |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a sales manager, I want to generate quotations instantly so that I can respond faster to customer. |  |  |  |  |
| BV | 10 |  | CP | 6 |  |
| Acceptance criteria |  |  |  |  |  |
| - System fetches product details automatically. - Quotation can be exported as PDF. - Approval workflow is triggered after creation. |  |  |  |  |  |

| User story No | 3 | Tasks | Create leave request workflow | Priority | Medium |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a field sales representative, I want to apply for leave online so that I can get faster approval from my manager. |  |  |  |  |
| BV | 7 |  | CP | 3 |  |
| Acceptance criteria |  |  |  |  |  |
| - Leave request form available in portal. - Notifications sent to manager instantly. - Status visible to requester in real-time. |  |  |  |  |  |

| User story No | 4 | Tasks | Add expense claim submission | Priority | High |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a sales representative, I want to submit expense claims with receipts so that I can get reimbursements quickly. |  |  |  |  |
| BV | 10 |  | CP | 6 |  |
| Acceptance criteria |  |  |  |  |  |
| - Expense form accepts scanned receipts. - Approval workflow auto-initiated. - Status tracking available in dashboard. |  |  |  |  |  |

| User story No | 5 | Tasks | Implement demo product booking module | Priority | High |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a sales representative, I want to book demo products so that I can ensure availability during client visits. |  |  |  |  |
| BV | 9 |  | CP | 6 |  |
| Acceptance criteria |  |  |  |  |  |
| - Calendar-based booking view. - Real-time availability check. - Confirmation notification sent to user. |  |  |  |  |  |

| User story No | 6 | Tasks | Build manager dashboards | Priority | High |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a sales manager, I want to view real-time KPIs so that I can monitor team performance effectively. |  |  |  |  |
| BV | 10 |  | CP | 7 |  |
| Acceptance criteria |  |  |  |  |  |
| - Dashboard updates automatically every 5 minutes. - Graphs and charts display key KPIs. - Drill-down to individual team member reports. |  |  |  |  |  |

| User story No | 7 | Tasks | Implement role-based access control | Priority | High |
| --- | --- | --- | --- | --- | --- |
| Value statement | As an administrator, I want to control access levels so that sensitive data is protected. |  |  |  |  |
| BV | 10 |  | CP | 8 |  |
| Acceptance criteria |  |  |  |  |  |
| - Role definitions configurable by admin. - Users see only relevant features. - Access logs maintained. |  |  |  |  |  |

| User story No | 8 | Tasks | Create automated approval notifications | Priority | Medium |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a manager, I want to get instant notifications for approvals so that I can respond quickly. |  |  |  |  |
| BV | 8 |  | CP | 3 |  |
| Acceptance criteria |  |  |  |  |  |
| - Notifications sent via email and mobile. - One-click approval/rejection option. |  |  |  |  |  |

| User story No | 9 | Tasks | Enable offline mode for mobile app | Priority | Medium |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a sales representative, I want to log data offline so that I can work in areas with no internet connectivity. |  |  |  |  |
| BV | 8 |  | CP | 7 |  |
| Acceptance criteria |  |  |  |  |  |
| - Data stored locally until internet is available. - Automatic sync without data loss. |  |  |  |  |  |

| User story No | 10 | Tasks | Develop training material section | Priority | Low |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a new team member, I want to access training materials so that I can learn to use the portal effectively. |  |  |  |  |
| BV | 6 |  | CP | 3 |  |
| Acceptance criteria |  |  |  |  |  |
| - Materials accessible via web and mobile. - Progress tracking available. |  |  |  |  |  |

| User story No | 11 | Tasks | Implement advanced search functionality | Priority | Medium |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a sales manager, I want to search by customer, date, or product so that I can quickly find relevant records. |  |  |  |  |
| BV | 9 |  | CP | 5 |  |
| Acceptance criteria |  |  |  |  |  |
| - Search returns results in under 2 seconds. - Filters available for refining results. |  |  |  |  |  |

| User story No | 12 | Tasks | Add real-time chat support | Priority | Low |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a user, I want to chat with support so that I can get help instantly. |  |  |  |  |
| BV | 6 |  | CP | 5 |  |
| Acceptance criteria |  |  |  |  |  |
| - Chat available during working hours. - Response time under 5 minutes. |  |  |  |  |  |

| User story No | 13 | Tasks | Develop analytics for expense trends | Priority | Low |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a finance manager, I want to analyze expense trends so that I can control costs better. |  |  |  |  |
| BV | 7 |  | CP | 4 |  |
| Acceptance criteria |  |  |  |  |  |
| - Monthly and quarterly trend reports available. - Export to Excel option provided. |  |  |  |  |  |

| User story No | 14 | Tasks | Implement digital signature feature | Priority | Medium |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a manager, I want to sign approvals digitally so that I can avoid paperwork delays. |  |  |  |  |
| BV | 8 |  | CP | 6 |  |
| Acceptance criteria |  |  |  |  |  |
| - E-signature stored securely. - Legally compliant storage format. |  |  |  |  |  |

| User story No | 15 | Tasks | Add push notification for meeting reminders | Priority | Medium |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a sales representative, I want to get meeting reminders so that I don’t miss important appointments. |  |  |  |  |
| BV | 7 |  | CP | 3 |  |
| Acceptance criteria |  |  |  |  |  |
| - Reminder sent 30 minutes before meeting. - Configurable reminder settings. |  |  |  |  |  |

| User story No | 16 | Tasks | Implement performance review tracking | Priority | Low |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a manager, I want to track performance reviews so that I can support employee development. |  |  |  |  |
| BV | 6 |  | CP | 4 |  |
| Acceptance criteria |  |  |  |  |  |
| - Review forms stored digitally. - Yearly performance summaries available. |  |  |  |  |  |

| User story No | 17 | Tasks | Create multi-language support | Priority | Low |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a regional sales rep, I want the portal in my local language so that I can use it more effectively. |  |  |  |  |
| BV | 7 |  | CP | 5 |  |
| Acceptance criteria |  |  |  |  |  |
| - Languages selectable in settings. - All UI text translated accurately. |  |  |  |  |  |

| User story No | 18 | Tasks | Add product catalogue with images | Priority | Medium |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a sales rep, I want to view the product catalogue with images so that I can present them to customers easily. |  |  |  |  |
| BV | 8 |  | CP | 4 |  |
| Acceptance criteria |  |  |  |  |  |
| - High-quality images load under 2 seconds. - Searchable product list. |  |  |  |  |  |

| User story No | 19 | Tasks | Implement audit log tracking | Priority | High |
| --- | --- | --- | --- | --- | --- |
| Value statement | As an administrator, I want to track all user activities so that I can ensure compliance and accountability. |  |  |  |  |
| BV | 10 |  | CP | 6 |  |
| Acceptance criteria |  |  |  |  |  |
| - Logs stored for at least 1 year. - Filterable by user, date, and activity type. |  |  |  |  |  |

| User story No | 20 | Tasks | Develop automated report generation | Priority | High |
| --- | --- | --- | --- | --- | --- |
| Value statement | As a sales manager, I want automated weekly reports so that I can track progress without manual effort. |  |  |  |  |
| BV | 9 |  | CP | 5 |  |
| Acceptance criteria |  |  |  |  |  |
| - Reports generated every Monday morning. - Sent automatically to manager’s email. |  |  |  |  |  |

# Document 4: Agile PO Experience

# Product Owner Role Overview

The Product Owner (PO) in the Delta Sales Operations Management Portal (DSOMP) project holds the vision for the product by leveraging industry expertise and understanding market needs. The PO bridges the gap between stakeholders, the Scrum Team, and the business goals, ensuring that the product delivers maximum value.

# Key Responsibilities of the Product Owner

## Market Analysis

- Conduct thorough research on market needs and demand.

- Assess the availability of similar products in the market and their features.

- Identify competitive advantages and market positioning opportunities.

## Enterprise Analysis

- Perform due diligence to validate the market opportunity.

- Evaluate alignment with Delta Healthcare’s strategic objectives.

## Product Vision and Roadmap

- Define a clear product vision based on need analysis.

- Prepare a product roadmap highlighting high-level features, deliverables, and timelines.

- Align roadmap milestones with business priorities and ROI.

## Managing Product Features

- Engage with stakeholders to gather and manage expectations.

- Prioritize epics, stories, and features based on criticality and ROI.

- Oversee daily Scrum meetings to stay updated on development progress.

- Conduct Sprint Review meetings to demonstrate deliverables to stakeholders.

- Participate in Sprint Retrospective meetings to gather feedback and improve processes.

- Lead Backlog Refinement meetings to ensure user stories are ready for upcoming sprints.

# User Stories Creation

Each user story created by the Product Owner includes:

- Story Number

- Tasks

- Priority

- Acceptance Criteria

- BV (Business Value) – numeric value on a 1–10 scale

- CP (Complexity Points) – numeric value on a 1–10 scale

These stories are structured to be clear, actionable, and aligned with the product vision.

# Liaison Between Teams

In Scrum, the Product Owner serves as the link between business stakeholders and the Scrum Team:

- Communicates project vision and updates to business units.

- Collaborates with developers, testers, and designers to clarify requirements.

- Ensures transparency on the project’s progress and priorities.

# Managing the Product Backlog

- Maintain and prioritize the product backlog based on business goals.

- Reprioritize items according to evolving stakeholder needs.

- Plan epics and ensure their decomposition into actionable user stories.

# Managing Overall Iteration Progress

- Review sprint progress regularly.

- Adjust sprint scope and epic priorities when necessary.

- Collaborate with the Business Analyst during retrospectives to refine processes.

# Lessons Learned from the Project

From the DSOMP project, I have learned to:

- Effectively conduct Sprint Planning Meetings to align the team with sprint goals.

- Manage Sprint Reviews to demonstrate progress and gather feedback.

- Lead Backlog Refinement sessions to ensure clarity and readiness of user stories.

- Use Sprint Retrospectives to identify improvement opportunities and enhance team performance.

# Document 5 – product and sprint backlog & product and sprint burndown charts

# Product Backlog

| User Story ID | User Story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US01 | Meeting reporting module | Design form, integrate with DB, QA testing | High | 9 | 5 | Sprint 1 |
| US02 | Quotation generator | UI design, connect to product DB, PDF export | High | 10 | 6 | Sprint 1 |
| US03 | Leave request workflow | Build form, add notifications, QA testing | Medium | 7 | 3 | Sprint 2 |
| US04 | Expense claim submission | UI design, receipt upload, approval workflow | Medium | 8 | 4 | Sprint 2 |
| US05 | Demo product booking | Booking calendar, inventory integration | High | 9 | 6 | Sprint 3 |
| US06 | Manager dashboards | Data aggregation, charts, KPI logic | High | 10 | 7 | Sprint 3 |
| US07 | Role-based access control | Role definition, permission logic, access logs | High | 10 | 8 | Sprint 4 |
| US08 | Automated approval notifications | Email & push notifications, quick actions | Medium | 8 | 3 | Sprint 4 |
| US09 | Offline mode for mobile app | Local storage, sync logic, conflict handling | Medium | 8 | 7 | Sprint 5 |
| US10 | Training material section | Content upload, progress tracking | Low | 6 | 3 | Sprint 5 |
| US11 | Advanced search functionality | Search filters, DB optimization | Medium | 9 | 5 | Sprint 6 |
| US12 | Real-time chat support | Integrate chat API, UI design | Low | 6 | 5 | Sprint 6 |
| US13 | Expense trend analytics | Data aggregation, chart creation | Low | 7 | 4 | Sprint 7 |
| US14 | Digital signature feature | E-signature API integration, storage | Medium | 8 | 6 | Sprint 7 |
| US15 | Meeting reminder push notifications | Reminder scheduling, mobile integration | Medium | 7 | 3 | Sprint 8 |
| US16 | Performance review tracking | Review form, summary reports | Low | 6 | 4 | Sprint 8 |
| US17 | Multi-language support | Language packs, translation UI | Low | 7 | 5 | Sprint 9 |
| US18 | Product catalog with images | Image upload, optimization, search | Medium | 8 | 4 | Sprint 9 |
| US19 | Audit log tracking | Activity logging, filters, export | High | 10 | 6 | Sprint 10 |
| US20 | Automated report generation | Schedule jobs, email reports | High | 9 | 5 | Sprint 10 |

# Sprint Backlog

## Sprint 1

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US01 | Meeting reporting module | Design UI form | Arjun Menon | In Progress | 6 hrs |
| US01 | Meeting reporting module | Backend integration | Ravi Prakash | To Do | 8 hrs |
| US01 | Meeting reporting module | QA Testing | Sameer Kulkarni | To Do | 4 hrs |
| US02 | Quotation generator | UI Layout Design | Karthik Iyer | In Progress | 5 hrs |
| US02 | Quotation generator | DB integration for product details | Mohit Sharma | To Do | 7 hrs |
| US02 | Quotation generator | PDF export feature | Arjun Menon | To Do | 6 hrs |

## Sprint 2

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US03 | Leave request workflow | Build form | Sameer Kulkarni | To Do | 5 hrs |
| US03 | Leave request workflow | Notification integration | Ravi Prakash | To Do | 4 hrs |
| US03 | Leave request workflow | QA testing | Arjun Menon | To Do | 3 hrs |
| US04 | Expense claim submission | UI design | Mohit Sharma | To Do | 6 hrs |
| US04 | Expense claim submission | Receipt upload integration | Karthik Iyer | To Do | 5 hrs |
| US04 | Expense claim submission | Approval workflow | Ravi Prakash | To Do | 4 hrs |

## Sprint 3

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US05 | Demo product booking | Booking calendar UI | Arjun Menon | To Do | 6 hrs |
| US05 | Demo product booking | Inventory check integration | Ravi Prakash | To Do | 7 hrs |
| US06 | Manager dashboards | Data aggregation logic | Sameer Kulkarni | To Do | 6 hrs |
| US06 | Manager dashboards | Chart and KPI design | Karthik Iyer | To Do | 5 hrs |

## Sprint 4

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US07 | Role-based access control | Role definition module | Mohit Sharma | To Do | 7 hrs |
| US07 | Role-based access control | Permission enforcement | Sameer Kulkarni | To Do | 6 hrs |
| US08 | Automated approval notifications | Email notification setup | Arjun Menon | To Do | 4 hrs |
| US08 | Automated approval notifications | Push notification setup | Karthik Iyer | To Do | 4 hrs |

## Sprint 5

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US09 | Offline mode for mobile app | Local storage design | Ravi Prakash | To Do | 6 hrs |
| US09 | Offline mode for mobile app | Sync logic | Mohit Sharma | To Do | 7 hrs |
| US10 | Training material section | Content upload feature | Arjun Menon | To Do | 4 hrs |
| US10 | Training material section | Progress tracking module | Karthik Iyer | To Do | 3 hrs |

## Sprint 6

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US11 | Advanced search functionality | Filter UI | Arjun Menon | To Do | 5 hrs |
| US11 | Advanced search functionality | DB optimization | Sameer Kulkarni | To Do | 6 hrs |
| US12 | Real-time chat support | Chat API integration | Ravi Prakash | To Do | 5 hrs |
| US12 | Real-time chat support | Chat UI design | Mohit Sharma | To Do | 4 hrs |

## Sprint 7

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US13 | Expense trend analytics | Data aggregation logic | Karthik Iyer | To Do | 5 hrs |
| US13 | Expense trend analytics | Chart creation | Arjun Menon | To Do | 4 hrs |
| US14 | Digital signature feature | API integration | Mohit Sharma | To Do | 6 hrs |
| US14 | Digital signature feature | Storage and security | Sameer Kulkarni | To Do | 5 hrs |

## Sprint 8

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US15 | Meeting reminder push notifications | Reminder scheduling | Arjun Menon | To Do | 4 hrs |
| US15 | Meeting reminder push notifications | Mobile integration | Ravi Prakash | To Do | 4 hrs |
| US16 | Performance review tracking | Review form UI | Mohit Sharma | To Do | 4 hrs |
| US16 | Performance review tracking | Summary report generation | Sameer Kulkarni | To Do | 4 hrs |

## Sprint 9

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US17 | Multi-language support | Language pack integration | Karthik Iyer | To Do | 5 hrs |
| US17 | Multi-language support | Translation UI | Arjun Menon | To Do | 5 hrs |
| US18 | Product catalog with images | Image upload & optimization | Ravi Prakash | To Do | 5 hrs |
| US18 | Product catalog with images | Search function | Mohit Sharma | To Do | 4 hrs |

## Sprint 10

| User Story ID | User Story | Tasks | Owner | Status | Estimated Effort |
| --- | --- | --- | --- | --- | --- |
| US19 | Audit log tracking | Activity logging module | Sameer Kulkarni | To Do | 6 hrs |
| US19 | Audit log tracking | Filters & export | Arjun Menon | To Do | 5 hrs |
| US20 | Automated report generation | Schedule jobs | Karthik Iyer | To Do | 4 hrs |
| US20 | Automated report generation | Email sending module | Ravi Prakash | To Do | 4 hrs |

# Product burn down chart

# Sprint burn down charts

## Sprint 1

## Sprint 2

## Sprint 3

## Sprint 4

## Sprint 5

## Sprint 6

## Sprint 7

## Sprint 8

## Sprint 9

## Sprint 10

# Document 6 – sprint meetings

# Meeting type 1 – sprint planning meeting

## Sprint 1:

| Date | 01/09/2025 |  |
| --- | --- | --- |
| Time | 10:00 AM – 12:00 PM |  |
| Location | Conference Room A / MS Teams |  |
| Prepared By | Mr Ramesh (Product Owner) |  |
| Attendees | Barath Narayanan (Scrum Master & Business Analyst) Mr. Ramesh (Product Owner) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |
| Agenda Topics |  |  |
| Topic | Presenter | Time allotted |
| Review Product Backlog | Mr. Ramesh | 20 mins |
| Define Sprint Goal | Barath Narayanan | 15 mins |
| Select User Stories for Sprint | Team | 30 mins |
| Task Breakdown & Estimation | Team | 45 mins |
| Finalize Sprint Plan | Barath Narayanan | 10 mins |
| Other Information |  |  |
| Observers | Resources | Special Notes |
| QA Lead, UI/UX Designer | Jira Board, Product Roadmap | Focus on delivering MVP core features |

## Sprint 2

| Date | 15/09/2025 |  |
| --- | --- | --- |
| Time | 10:00 AM – 12:00 PM |  |
| Location | Conference Room B / MS Teams |  |
| Prepared By | Product Owner |  |
| Attendees | Barath Narayanan (Scrum Master & Business Analyst) Mr. Ramesh (Product Owner) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |
| Agenda Topics |  |  |
| Topic | Presenter | Time allotted |
| Review Previous Sprint Outcome | Barath Narayanan | 15 mins |
| Update Product Backlog | Mr. Ramesh | 20 mins |
| Select User Stories | Team | 30 mins |
| Estimate & Assign Tasks | Team | 45 mins |
| Confirm Sprint Goal | Barath Narayanan | 10 mins |
| Other Information |  |  |
| Observers | Resources | Special Notes |
| Sales Team Reps | Jira Board, Test Environment | Include high-priority bug fixes |

## Sprint 3

| Date | 29/09/2025 |  |
| --- | --- | --- |
| Time | 2:00 PM – 4:00 PM |  |
| Location | Conference Room C / MS Teams |  |
| Prepared By | Mr. Ramesh (Product Owner) |  |
| Attendees | Barath Narayanan (Scrum Master & Business Analyst) Mr. Ramesh (Product Owner) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |
| Agenda Topics |  |  |
| Topic | Presenter | Time allotted |
| Analyze Sprint Metrics | Barath Narayanan | 15 mins |
| Reprioritize Backlog | Mr. Ramesh | 20 mins |
| Select User Stories | Team | 30 mins |
| Breakdown into Tasks | Team | 45 mins |
| Final Approval | Barath Narayanan | 10 mins |
| Other Information |  |  |
| Observers | Resources | Special Notes |
| Business Analyst | Jira Board, Sprint Reports | Introduce new UI features |

## Sprint 4

| Date | 13/10/2025 |  |
| --- | --- | --- |
| Time | 10:00 AM – 12:00 PM |  |
| Location | Conference Room A |  |
| Prepared By | Mr. Ramesh (Product Owner) |  |
| Attendees | Barath Narayanan (Scrum Master & Business Analyst) Mr. Ramesh (Product Owner) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |
| Agenda Topics |  |  |
| Topic | Presenter | Time allotted |
| Backlog Refinement | Mr. Ramesh | 20 mins |
| Define Sprint Scope | Barath Narayanan | 15 mins |
| Allocate User Stories | Team | 30 mins |
| Task Estimation | Team | 45 mins |
| Risk Review | Barath Narayanan | 10 mins |
| Other Information |  |  |
| Observers | Resources | Special Notes |
| QA Lead | Jira Board, Risk Register | Include cross-browser testing |

## Sprint 5

| Date | 27/10/2025 |  |
| --- | --- | --- |
| Time | 3:00 PM – 5:00 PM |  |
| Location | Conference Room B |  |
| Prepared By | Mr. Ramesh (Product Owner) |  |
| Attendees | Barath Narayanan (Scrum Master & Business Analyst) Mr. Ramesh (Product Owner) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |
| Agenda Topics |  |  |
| Topic | Presenter | Time allotted |
| Review Stakeholder Feedback | Mr. Ramesh | 20 mins |
| Backlog Grooming | Barath Narayanan | 15 mins |
| Pick High ROI Features | Team | 30 mins |
| Task Assignments | Team | 45 mins |
| Sprint Commitment | Barath Narayanan | 10 mins |
| Other Information |  |  |
| Observers | Resources | Special Notes |
| UX Designer | Jira Board, Feedback Docs | Improve dashboard performance |

## Sprint 6

| Date | 10/11/2025 |  |
| --- | --- | --- |
| Time | 10:00 AM – 12:00 PM |  |
| Location | Conference Room C |  |
| Prepared By | Mr. Ramesh (Product Owner) |  |
| Attendees | Barath Narayanan (Scrum Master & Business Analyst) Mr. Ramesh (Product Owner) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |
| Agenda Topics |  |  |
| Topic | Presenter | Time allotted |
| Sprint Review Outcomes | Barath Narayanan | 15 mins |
| Update Priorities | Mr. Ramesh | 20 mins |
| Select Key Stories | Team | 30 mins |
| Create Task Breakdown | Team | 45 mins |
| Approve Sprint Plan | Barath Narayanan | 10 mins |
| Other Information |  |  |
| Observers | Resources | Special Notes |
| Sales team Rep | Jira Board, Design Assets | Launch ticket request feature |

## Sprint 7

| Date | 24/11/2025 |  |
| --- | --- | --- |
| Time | 2:00 PM – 4:00 PM |  |
| Location | Conference Room A |  |
| Prepared By | Mr. Ramesh (Product Owner) |  |
| Attendees | Barath Narayanan (Scrum Master & Business Analyst) Mr. Ramesh (Product Owner) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |
| Agenda Topics |  |  |
| Topic | Presenter | Time allotted |
| Discuss New Requirements | Mr. Ramesh | 20 mins |
| Prioritize Stories | Barath Narayanan | 15 mins |
| Allocate Work | Team | 30 mins |
| Define Test Strategy | Team | 45 mins |
| Confirm Sprint Goal | Barath Narayanan | 10 mins |
| Other Information |  |  |
| Observers | Resources | Special Notes |
| QA Lead | Jira Board, Test Cases | Emphasis on security testing |

## Sprint 8

| Date | 08/12/2025 |  |
| --- | --- | --- |
| Time | 10:00 AM – 12:00 PM |  |
| Location | Conference Room B |  |
| Prepared By | Mr. Ramesh (Product Owner) |  |
| Attendees | Barath Narayanan (Scrum Master & Business Analyst) Mr. Ramesh (Product Owner) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |
| Agenda Topics |  |  |
| Topic | Presenter | Time allotted |
| Backlog Grooming | Mr. Ramesh | 20 mins |
| Feature Selection | Barath Narayanan | 15 mins |
| Assign Stories | Team | 30 mins |
| Estimate Workload | Team | 45 mins |
| Lock Sprint Scope | Barath Narayanan | 10 mins |
| Other Information |  |  |
| Observers | Resources | Special Notes |
| UX Designer | Jira Board, Product Docs | Introduce mobile app optimization |

## Sprint 9

| Date | 22/12/2025 |  |
| --- | --- | --- |
| Time | 3:00 PM – 5:00 PM |  |
| Location | Conference Room C |  |
| Prepared By | Mr. Ramesh (Product Owner) |  |
| Attendees | Barath Narayanan (Scrum Master & Business Analyst) Mr. Ramesh (Product Owner) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |
| Agenda Topics |  |  |
| Topic | Presenter | Time allotted |
| Review Product Milestones | Mr. Ramesh | 20 mins |
| Prioritize Critical Features | Barath Narayanan | 15 mins |
| Allocate Stories | Team | 30 mins |
| Plan Test Execution | Team | 45 mins |
| Confirm Delivery Timeline | Barath Narayanan | 10 mins |
| Other Information |  |  |
| Observers | Resources | Special Notes |
| QA Lead, Client Rep | Jira Board, Release Plan | Prepare for UAT phase |

## Sprint 10

| Date | 05/01/2026 |  |
| --- | --- | --- |
| Time | 10:00 AM – 12:00 PM |  |
| Location | Conference Room A |  |
| Prepared By | Mr. Ramesh (Product Owner) |  |
| Attendees | Barath Narayanan (Scrum Master & Business Analyst) Mr. Ramesh (Product Owner) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |
| Agenda Topics |  |  |
| Topic | Presenter | Time allotted |
| Final Backlog Review | Mr. Ramesh | 20 mins |
| Scope Lock for Release | Barath Narayanan | 15 mins |
| Assign Final Tasks | Team | 30 mins |
| Estimate & Validate | Team | 45 mins |
| Sprint & Release Approval | Barath Narayanan | 10 mins |
| Other Information |  |  |
| Observers | Resources | Special Notes |
| Stakeholder Group | Jira Board, Release Docs | Focus on release readiness |

# Sprint review meetings

## Sprint 1

| Date | 14/09/2025 |  |  |
| --- | --- | --- | --- |
| Time | 11:00 AM – 12:30 PM |  |  |
| Location | Conference Room A / MS Teams |  |  |
| Prepared By | Mr. Ramesh (Product Owner) |  |  |
| Attendees | Barath Narayanan (Scrum Master & BA) Mr. Ramesh (PO) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| Completed 90% of planned stories | Login module, User dashboard | Minor API performance issues fixed | Integrate payment gateway |

## Sprint 2

| Date | 28/09/2025 |  |  |
| --- | --- | --- | --- |
| Time | 11:00 AM – 12:30 PM |  |  |
| Location | Conference Room B / MS Teams |  |  |
| Prepared By | Mr. Ramesh |  |  |
| Attendees | Barath Narayanan (Scrum Master & BA) Mr. Ramesh (PO) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| Completed all planned features | Ticket request, download tickets | New security measures implemented | Develop admin analytics dashboard |

## Sprint 3

| Date | 12/10/2025 |  |  |
| --- | --- | --- | --- |
| Time | 2:00 PM – 3:30 PM |  |  |
| Location | Conference Room C / MS Teams |  |  |
| Prepared By | Mr. Ramesh |  |  |
| Attendees | Barath Narayanan (Scrum Master & BA) Mr. Ramesh (PO) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| Completed 85% of scope | Admin analytics dashboard, Email notifications | Delay due to API bug resolution | Mobile app initial version |

## Sprint 4

| Date | 26/10/2025 |  |  |
| --- | --- | --- | --- |
| Time | 10:30 AM – 12:00 PM |  |  |
| Location | Conference Room A |  |  |
| Prepared By | Mr. Ramesh |  |  |
| Attendees | Barath Narayanan (Scrum Master & BA) Mr. Ramesh (PO) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| Completed 95% of stories | Mobile app prototype, UI updates | Client approved mobile app design | Implement chat support |

## Sprint 5

| Date | 09/11/2025 |  |  |
| --- | --- | --- | --- |
| Time | 3:00 PM – 4:30 PM |  |  |
| Location | Conference Room B |  |  |
| Prepared By | Mr. Ramesh |  |  |
| Attendees | Barath Narayanan (Scrum Master & BA) Mr. Ramesh (PO) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| All planned features completed | Chat support, Profile update module | Minor UI fixes completed | Launch beta testing phase |

## Sprint 6

| Date | 23/11/2025 |  |  |
| --- | --- | --- | --- |
| Time | 10:00 AM – 11:30 AM |  |  |
| Location | Conference Room C |  |  |
| Prepared By | Mr. Ramesh |  |  |
| Attendees | Barath Narayanan (Scrum Master & BA) Mr. Ramesh (PO) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| Completed 88% of scope | Beta version walkthrough | Gathered early user feedback | Apply feedback-based improvements |

## Sprint 7

| Date | 07/12/2025 |  |  |
| --- | --- | --- | --- |
| Time | 2:00 PM – 3:30 PM |  |  |
| Location | Conference Room A |  |  |
| Prepared By | Mr. Ramesh |  |  |
| Attendees | Barath Narayanan (Scrum Master & BA) Mr. Ramesh (PO) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| Completed all backlog items | Performance optimization, Faster load times | Reduced server response by 30% | Start final UAT preparation |

## Sprint 8

| Date | 21/12/2025 |  |  |
| --- | --- | --- | --- |
| Time | 11:00 AM – 12:30 PM |  |  |
| Location | Conference Room B |  |  |
| Prepared By | Mr. Ramesh |  |  |
| Attendees | Barath Narayanan (Scrum Master & BA) Mr. Ramesh (PO) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| Completed 92% of tasks | UAT-ready build, Full feature set | All critical bugs resolved | Conduct UAT with client |

## Sprint 9

| Date | 04/01/2026 |  |  |
| --- | --- | --- | --- |
| Time | 10:00 AM – 11:30 AM |  |  |
| Location | Conference Room C |  |  |
| Prepared By | Mr. Ramesh |  |  |
| Attendees | Barath Narayanan (Scrum Master & BA) Mr. Ramesh (PO) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| Completed UAT feedback changes | Final product demo | Client signed off on main features | Prepare release documentation |

## Sprint 10

| Date | 18/01/2026 |  |  |
| --- | --- | --- | --- |
| Time | 10:00 AM – 11:30 AM |  |  |
| Location | Conference Room A |  |  |
| Prepared By | Mr. Ramesh |  |  |
| Attendees | Barath Narayanan (Scrum Master & BA) Mr. Ramesh (PO) Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |
| Sprint status | Things to demo | Quick updates | What’s next |
| Release-ready | Final release version | Deployment scheduled | Post-release support & maintenance |

# Sprint retrospective meetings

## Sprint 1

| Date | 14/09/2025 |  |  |  |
| --- | --- | --- | --- | --- |
| Time | 3:00 PM – 4:00 PM |  |  |  |
| Location | Conference Room A / MS Teams |  |  |  |
| Prepared By | Barath Narayanan (Scrum Master) |  |  |  |
| Attendees | Mr. Ramesh Barath Narayanan Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |  |
| Agenda | What went well | What didn’t go well | Questions | Reference |
| Review Sprint 1 outcomes | Login module completed ahead of time | API documentation incomplete | How to streamline documentation | Sprint 1 backlog & burndown |

## Sprint 2

| Date | 28/09/2025 |  |  |  |
| --- | --- | --- | --- | --- |
| Time | 3:00 PM – 4:00 PM |  |  |  |
| Location | Conference Room A / MS Teams |  |  |  |
| Prepared By | Barath Narayanan (Scrum Master) |  |  |  |
| Attendees | Mr. Ramesh Barath Narayanan Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |  |
| Agenda | What went well | What didn’t go well | Questions | Reference |
| Review Sprint 2 outcomes | Payment gateway integrated successfully | Minor delays due to QA environment setup | How to automate deployment | Sprint 2 backlog & burndown |

## Sprint 3

| Date | 12/10/2025 |  |  |  |
| --- | --- | --- | --- | --- |
| Time | 4:00 PM – 5:00 PM |  |  |  |
| Location | Conference Room C |  |  |  |
| Prepared By | Barath Narayanan (Scrum Master) |  |  |  |
| Attendees | Mr. Ramesh Barath Narayanan Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |  |
| Agenda | What went well | What didn’t go well | Questions | Reference |
| Review Sprint 3 outcomes | Analytics dashboard functional | API bug delayed story completion | How to handle unexpected blockers | Sprint 3 backlog & burndown |

## Sprint 4

| Date | 26/10/2025 |  |  |  |
| --- | --- | --- | --- | --- |
| Time | 2:00 PM – 3:00 PM |  |  |  |
| Location | Conference Room A |  |  |  |
| Prepared By | Barath Narayanan (Scrum Master) |  |  |  |
| Attendees | Mr. Ramesh Barath Narayanan Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |  |
| Agenda | What went well | What didn’t go well | Questions | Reference |
| Review Sprint 4 outcomes | Mobile app prototype approved | Some UI inconsistencies found late | How to implement early UI reviews | Sprint 4 backlog & burndown |

## Sprint 5

| Date | 09/11/2025 |  |  |  |
| --- | --- | --- | --- | --- |
| Time | 4:00 PM – 5:00 PM |  |  |  |
| Location | Conference Room B |  |  |  |
| Prepared By | Barath Narayanan (Scrum Master) |  |  |  |
| Attendees | Mr. Ramesh Barath Narayanan Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |  |
| Agenda | What went well | What didn’t go well | Questions | Reference |
| Review Sprint 5 outcomes | Chat support deployed | Minor connectivity issue during testing | How to simulate production-like network in test | Sprint 5 backlog & burndown |

## Sprint 6

| Date | 23/11/2025 |  |  |  |
| --- | --- | --- | --- | --- |
| Time | 10:30 AM – 11:30 AM |  |  |  |
| Location | Conference Room C |  |  |  |
| Prepared By | Barath Narayanan (Scrum Master) |  |  |  |
| Attendees | Mr. Ramesh Barath Narayanan Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |  |
| Agenda | What went well | What didn’t go well | Questions | Reference |
| Review Sprint 6 outcomes | Beta feedback received early | Few users reported app crashes | How to improve crash logging | Sprint 6 backlog & burndown |

## Sprint 7

| Date | 07/12/2025 |  |  |  |
| --- | --- | --- | --- | --- |
| Time | 4:00 PM – 5:00 PM |  |  |  |
| Location | Conference Room A |  |  |  |
| Prepared By | Barath Narayanan (Scrum Master) |  |  |  |
| Attendees | Mr. Ramesh Barath Narayanan Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |  |
| Agenda | What went well | What didn’t go well | Questions | Reference |
| Review Sprint 7 outcomes | Performance improved by 30% | Delay in third-party API response | How to handle third-party SLAs | Sprint 7 backlog & burndown |

## Sprint 8

| Date | 21/12/2025 |  |  |  |
| --- | --- | --- | --- | --- |
| Time | 2:00 PM – 3:00 PM |  |  |  |
| Location | Conference Room B |  |  |  |
| Prepared By | Barath Narayanan (Scrum Master) |  |  |  |
| Attendees | Mr. Ramesh Barath Narayanan Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |  |
| Agenda | What went well | What didn’t go well | Questions | Reference |
| Review Sprint 8 outcomes | UAT-ready build delivered | Minor usability issues reported | How to integrate usability testing earlier | Sprint 8 backlog & burndown |

## Sprint 9

| Date | 04/01/2026 |  |  |  |
| --- | --- | --- | --- | --- |
| Time | 11:00 AM – 12:00 PM |  |  |  |
| Location | Conference Room C |  |  |  |
| Prepared By | Barath Narayanan (Scrum Master) |  |  |  |
| Attendees | Mr. Ramesh Barath Narayanan Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |  |
| Agenda | What went well | What didn’t go well | Questions | Reference |
| Review Sprint 9 outcomes | Client approved all major changes | Documentation updates lagging | How to keep docs updated in parallel | Sprint 9 backlog & burndown |

## Sprint 10

| Date | 18/01/2026 |  |  |  |
| --- | --- | --- | --- | --- |
| Time | 3:00 PM – 4:00 PM |  |  |  |
| Location | Conference Room A |  |  |  |
| Prepared By | Barath Narayanan (Scrum Master) |  |  |  |
| Attendees | Mr. Ramesh Barath Narayanan Suresh Menon Vivek Reddy Anil Sharma Karthik Iyer Prakash Rao |  |  |  |
| Agenda | What went well | What didn’t go well | Questions | Reference |
| Review Sprint 10 outcomes | Release deployed successfully | Minor post-release bug found | How to improve regression testing | Sprint 10 backlog & burndown |

# Daily stand up meeting

## Sprint 1 – Daily Stand-up Meeting

Week: 01-09-2025 to 14-09-2025

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Suresh Menon | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Vivek Reddy | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Anil Sharma | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
| What will you do today? | Suresh Menon | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Vivek Reddy | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Anil Sharma | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
| What (if any) is blocking your progress? | Suresh Menon | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Vivek Reddy | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Anil Sharma | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |

## Sprint 2 – Daily Stand-up Meeting

Week: 15-09-2025 to 28-09-2025

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Suresh Menon | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Vivek Reddy | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Anil Sharma | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
| What will you do today? | Suresh Menon | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Vivek Reddy | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Anil Sharma | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
| What (if any) is blocking your progress? | Suresh Menon | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Vivek Reddy | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Anil Sharma | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |

## Sprint 3 – Daily Stand-up Meeting

Week: 29-09-2025 to 12-10-2025

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Suresh Menon | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Vivek Reddy | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Anil Sharma | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
| What will you do today? | Suresh Menon | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Vivek Reddy | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Anil Sharma | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
| What (if any) is blocking your progress? | Suresh Menon | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Vivek Reddy | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Anil Sharma | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |

## Sprint 4 – Daily Stand-up Meeting

Week: 13-10-2025 to 26-10-2025

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Suresh Menon | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Vivek Reddy | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Anil Sharma | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
| What will you do today? | Suresh Menon | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Vivek Reddy | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Anil Sharma | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
| What (if any) is blocking your progress? | Suresh Menon | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Vivek Reddy | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Anil Sharma | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |

## Sprint 5 – Daily Stand-up Meeting

Week: 27-10-2025 to 09-11-2025

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Suresh Menon | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Vivek Reddy | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Anil Sharma | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
| What will you do today? | Suresh Menon | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Vivek Reddy | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Anil Sharma | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
| What (if any) is blocking your progress? | Suresh Menon | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Vivek Reddy | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Anil Sharma | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |

## Sprint 6 – Daily Stand-up Meeting

Week: 10-11-2025 to 23-11-2025

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Suresh Menon | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Vivek Reddy | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Anil Sharma | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
| What will you do today? | Suresh Menon | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Vivek Reddy | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Anil Sharma | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
| What (if any) is blocking your progress? | Suresh Menon | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Vivek Reddy | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Anil Sharma | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |

## Sprint 7 – Daily Stand-up Meeting

Week: 24-11-2025 to 07-12-2025

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Suresh Menon | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Vivek Reddy | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Anil Sharma | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
| What will you do today? | Suresh Menon | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Vivek Reddy | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Anil Sharma | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
| What (if any) is blocking your progress? | Suresh Menon | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Vivek Reddy | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Anil Sharma | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |

## Sprint 8 – Daily Stand-up Meeting

Week: 08-12-2025 to 21-12-2025

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Suresh Menon | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Vivek Reddy | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Anil Sharma | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
| What will you do today? | Suresh Menon | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Vivek Reddy | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Anil Sharma | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
| What (if any) is blocking your progress? | Suresh Menon | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Vivek Reddy | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Anil Sharma | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |

## Sprint 9 – Daily Stand-up Meeting

Week: 22-12-2025 to 04-01-2026

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Suresh Menon | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Vivek Reddy | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Anil Sharma | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
| What will you do today? | Suresh Menon | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Vivek Reddy | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Anil Sharma | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
| What (if any) is blocking your progress? | Suresh Menon | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Vivek Reddy | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Anil Sharma | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |

## Sprint 10 – Daily Stand-up Meeting

Week: 05-01-2026 to 18-01-2026

| Question | Name / Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What did you do yesterday? | Suresh Menon | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Vivek Reddy | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
|  | Anil Sharma | Set up module | Implemented feature | Tested component | Fixed bug | Reviewed code | Updated documentation |
| What will you do today? | Suresh Menon | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Vivek Reddy | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
|  | Anil Sharma | Continue feature dev | Integrate module | Conduct testing | Bug fixing | Prepare demo | Optimize performance |
| What (if any) is blocking your progress? | Suresh Menon | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Vivek Reddy | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |
|  | Anil Sharma | None | API downtime | Waiting for review | Dependency delay | Environment issue | None |