## Slide 1: Implementation of a New Learning Management System for the Institute Library (Agile Methodology)
- Prathmesh Anerao

## Slide 2: Problem Identification
Current System: Manual processes for managing library resources and user interactions
Issues:
Inefficient and immense operations
Limited digital accessibility and slow response times
Increased risk of errors and data loss
Difficulty in managing and tracking library resources and user activities

## Slide 3: Purpose Statement
Goal: Implement a modern Learning Management System (LMS) to replace the manual processes
Objective:
Streamline library operations
Enhance accessibility to digital resources
Improve user experience with a user-friendly platform
Provide scalable and secure management of library resources and interactions

## Slide 4: Project Objectives
Iterative Solution Selection: Refine and select an LMS through iterative development and evaluation
Prototyping and Feedback: Develop and test prototypes, integrating user feedback
Incremental Implementation: Deploy the LMS in stages, adding value with each iteration
Continuous Improvement: Optimize the LMS based on feedback and performance metrics
Final Evaluation: Confirm the system meets all project goals and user requirements

## Slide 5: Success Criteria
Improved Accessibility: Transition from manual to digital with enhanced access to library resources
Enhanced Performance: Reduced system downtime and faster response times
Positive User Experience: Increased satisfaction among library users and reduced support issues
Effective Training: Comprehensive training for users and technical staff to ensure a smooth transition
Operational Efficiency: Streamlined processes and reduced manual workload

## Slide 6: Methods (Agile Methodology)
Form Agile Team: Assemble a cross-functional team including product owner, scrum master, developers, and library stakeholders
Define Product Backlog: Create and prioritize backlog items with library-specific requirements
Sprint Planning: Plan iterative sprints with clear goals and deliverables
Develop and Test: Develop LMS features in sprints, incorporating feedback and performing testing
User Feedback: Gather and integrate feedback at the end of each sprint
Incremental Rollout: Deploy features in stages, ensuring each stage adds value
Review and Adapt: Conduct regular reviews and make necessary adjustments
Go Live and Post-Implementation: Launch the LMS and provide ongoing support and optimization

## Slide 7: Resources
People:
  Agile Team: Product Owner, Scrum Master, Developers, Library Staff, and Stakeholders
  Technical Support: ITS staff for system implementation and maintenance
Time: Complete implementation within 9 months
Budget: Total budget detailed below
Other: Costs for third-party evaluations, site visits, and reports

## Slide 8: Budget
Category | Estimated Cost (INR)
Hardware | 1,00,000
Software | 5,00,000
Training | 2,00,000
Services | 1,50,000
Third-Party Evaluations | 50,000
Site Visits | 30,000
Dataquest Reports | 20,000
Total Budget | 10,50,000

## Slide 9: Risk and Dependencies
User Adaptation: Potential resistance from users accustomed to manual processes; managed through phased implementation and training
Data Migration: Challenges related to accuracy and completeness of migrating data from manual records; require thorough planning and validation
Scope Creep: Evolving requirements may impact project scope and timelines; mitigated through effective backlog management and regular stakeholder communication
Technical Issues: Potential integration challenges; addressed through comprehensive testing and support

## Slide 10: Project Timeline
Phase | Start Date | End Date
Form Agile Team | 01-Oct-2024 | 15-Oct-2024
Define Product Backlog | 16-Oct-2024 | 31-Oct-2024
Sprint 1: Develop Prototype | 01-Nov-2024 | 30-Nov-2024
Sprint 2: User Feedback | 01-Dec-2024 | 15-Dec-2024
Sprint 3: Further Development | 16-Dec-2024 | 31-Dec-2024
Incremental Rollout | 01-Jan-2025 | 28-Feb-2025
Training and Support | 01-Mar-2025 | 15-Mar-2025
Go Live | 16-Mar-2025 | 31-Mar-2025
Post-Implementation Review | 01-Apr-2025 | 30-Apr-2025

## Slide 11: Conclusion
Summary: Implementing a new LMS will replace inefficient manual processes, enhance resource accessibility, and improve user experience through an agile approach.
Next Steps: Obtain approval to proceed with detailed planning and kickoff of agile phases.