## Slide 1: COEPD
Live Project – Waterfall Deliverables -Part ⅓
Presented By
DEBADRITA DAS

## Slide 2: PROJECT INITIATION : PROBLEM
Financial regulations vary by jurisdictions and subjected to frequent updates and changes
High false-positive rate (~85 %) from rules-based screening generates costly backlogs
Data complexity and volume are the major problem
Fragmented data hampers end-to-end customer-risk view

## Slide 3: PROJECT : GOAL
Rolling out NICE ACTIMIZE by integrating the Software into Organization’s existing infrastructure and workflows and configuring it to meet specific needs.
Use multilayered analytics & ML threshold optimisation to cut false positives by ≈80 %
Consolidate customer, transaction & sanctions data for real-time, context-rich screening

## Slide 4: VALUE
Regulatory confidence – Faster, more accurate detection with audit-ready, transparent reporting.
Operational efficiency – Frees up ~30 analyst hours per week for higher-value investigations.
Enhanced detection – Identifies up to 4× more true positives, significantly reducing missed suspicious activities.
Cost avoidance – Reduces manual review effort and mitigates the risk of regulatory penalties.
Customer experience – Speeds up KYC and onboarding, minimizing unnecessary account holds.
Consistency – Ensures uniform alert investigation processes across teams, branches, and geographies.
Integration – Seamlessly connects with KYC, fraud detection, and case management systems.

## Slide 5: Scope & Stakeholders
IN - SCOPE :
Deployment of NICE Actimize SAM-10 for customer & transaction screening
Configuration of sanctions/watchlist data feeds (OFAC, EU, UN, local)
Analyst & investigator training and SOP update
OUT - SCOPE :
    Historical transaction back-screening beyond 5 years
    Implementation of non-AML Actimize modules (fraud, trade surveillance)
KEY - STAKEHOLDERS :
    Executive Sponsor – Chief Compliance Officer
    Business Owner – AML Operations Lead
    Project Manager – PMO
    Business Analyst
    IT Integration Lead & QA/Test Lead
    NICE Actimize Professional Services (vendor)

## Slide 6: Methodology :
Waterfall Overview :
  Linear and sequential project methodology with clearly defined phases:
  Requirements → Design → Development → Testing → Deployment → Maintenance
  Each phase is completed before the next begins – ideal for fixed-scope, compliance-driven projects
Why Waterfall for This Project :
  Regulatory requirements demand upfront clarity, documentation, and sign-offs
  Scope and compliance deliverables are well-defined with limited room for iteration
  Third-party vendors (e.g., NICE Actimize) follow structured implementation protocols
  System integrations (e.g., core banking, sanctions lists) require formal test and deployment plans
  Stakeholders expect milestone-based tracking and phased acceptance sign-offs

## Slide 7: RESOURCES
PEOPLE : Project Manager, skilled developers with the updates with recent technologies for the compliance and risk management platforms, Skilled UI/UX designers, Compliance / AML SMEs, QA / Test Engineers , IT Infrastructure & DBA , Training & Change-Mgmt Lead, and obviously Business Analyst.
TIME : This application will be developed under waterfall methodology in the shortest time of approx 28 weeks (≈ 7 months)
BUDGET : This application relies on the most vulnerable project because it deals with combating ANTI-MONEY Laundering and Terrorist Financing, so the software and hardware ranges high, also the amount of work which we input, Total Budget – approximately 870 k.

## Slide 8: Risks & Mitigations
Data integration delays could impact timeline
  Mitigation: Early data profiling, phased interface tests, weekly escalation of blockers
  Owner: Integration Lead
  Status: Amber
Requirement misinterpretation may create compliance gaps
  Mitigation: Involve Compliance SMEs for validation; design walkthroughs with regulators
  Owner: Compliance SME Lead
  Status: Green – Requirements signed off, periodic reviews scheduled
High false positives remain above target post go-live
  Mitigation: Iterative threshold tuning, ML optimisation, champion/challenger approach
  Owner: AML Operations Lead
  Status: Amber

## Slide 9: Key Deliverables
Requirements (100 % complete)
Business Requirements Document (BRD) signed off
Functional Specification (FRD , SRS)
Regulatory Traceability Matrix
2. Design (100 % complete)
Solution Architecture Diagram & Interface Specs
Alert Workflow & Escalation Design
UI Mock-ups for Analyst Workbench
3. Build / Configuration (70 % complete)
Sanctions & PEP watchlist feeds integrated
Initial risk threshold parameters set

## Slide 10: Key Deliverables (Contd. )
4. Testing (40 % complete)
Test Strategy & Detailed Test Plan
100+ System Test Cases authored in JIRA
Mock sanctions lists & test datasets prepared
Test environment deployed and smoke-tested
5. Other :
Training Curriculum Outline drafted
Cut-over & Rollback Plan

## Slide 11: Next Steps & Asks
Next Steps (Next 4–6 Weeks)
Finish UAT test case execution and capture results
Finalize training content and deliver 2 analyst workshops
Conduct Go‑No‑Go readiness assessment by end of next month
Plan deployment window with IT Ops and Risk Steering Committee
2. Asks – Decisions Needed
Approval of Go‑Live deployment date and rollout plan
Decision on post‑go‑live alert handling staffing model (central vs local)
Agreement on long‑term watchlist data subscription provider
3. Asks – Support Required
Continued SME availability for UAT support and sign‑offs
IT Ops to prioritize data pipeline monitoring setup
Executive comms support for change‑management readiness across branches

## Slide 12
THANK YOU