Question 1 – write Agile Manifesto – 8 Marks

Answer 1. Agile Manifesto - The Agile Manifesto, introduced in 2001 by 17 software practitioners, outlines the core values and principles for agile software development. It guides teams to work collaboratively, adapt quickly to change, and deliver customer-centric solutions.

### Four Core Values of the Agile Manifesto:

### 1. Individuals and Interactions Over Processes and Tools

What it means:
Agile emphasizes that the people on the team and the way they communicate are more important than strictly following processes or relying on tools.

Why it matters:

- Tools and processes are important, but they can’t replace good teamwork.

- Direct communication (face-to-face or digital) helps resolve issues faster.

- Agile teams collaborate closely, take ownership, and make decisions together.

Example:
Instead of waiting for a ticket to be created in a tool like Jira, a developer directly discusses a change with the tester and makes faster progress.

### 2. Working Software Over Comprehensive Documentation

What it means:
Delivering functional, usable software is more valuable than spending excessive time creating detailed documentation.

Why it matters:

- Agile values lean documentation – just enough to guide development.

- Real value is delivered when users can use the product, not when they read documents.

- Documentation should support development, not slow it down.

Example:
Rather than creating a 100-page requirements document, the team builds a working prototype and iterates based on client feedback.

### 3. Customer Collaboration Over Contract Negotiation

What it means:
Agile encourages continuous communication and partnership with customers rather than rigidly following a contract.

Why it matters:

- Requirements change frequently in real-world projects.

- Involving customers regularly ensures the product is aligned with their expectations.

- Agile promotes flexibility over fixed terms.

Example:
Instead of sticking to a signed-off scope from 3 months ago, the Product Owner adjusts the backlog based on evolving customer needs.

### 4. Responding to Change Over Following a Plan

What it means:
Agile acknowledges that change is inevitable and teams should be ready to adapt quickly rather than sticking blindly to a plan.

Why it matters:

- Static plans become outdated as priorities shift.

- Agile teams use short iterations (Sprints) to inspect and adapt frequently.

- The focus is on delivering value, not just finishing what was planned initially.

Example:
During Sprint Planning, a high-priority feature is added to the backlog based on new business insights—even if it means changing the previous plan.

### 12 Agile Principles:

- Customer satisfaction through early and continuous delivery of valuable software

- Welcome changing requirements, even late in development

- Deliver working software frequently (from a couple of weeks to a couple of months)

- Business people and developers must work together daily

- Build projects around motivated individuals and trust them

- Use face-to-face conversation as the most effective communication method

- Working software is the primary measure of progress

- Promote sustainable development – maintain a constant pace

- Continuous attention to technical excellence and good design

- Simplicity – maximizing the amount of work not done – is essential

- The best architectures, requirements, and designs emerge from self-organizing teams

- Regularly reflect and adjust behavior for continuous improvement

### Conclusion:

The Agile Manifesto provides a foundation for Agile frameworks like Scrum, Kanban, SAFe, etc. It emphasizes flexibility, customer satisfaction, collaboration, and frequent delivery of high-quality products

Question 2 – User Stories- Acceptance Criteria-BV-CP – 40 Marks

Write minimum 40 User stories and their Acceptance Criteria

along with their BV and CP

Answer 2.

| User Story No: | 1 | Tasks: | 3 | Priority: | High |
| --- | --- | --- | --- | --- | --- |
| AS A CUSTOMER |  |  |  |  |  |
| I WANT TO REGISTER ON THE APP |  |  |  |  |  |
| SO THAT I CAN PLACE FOOD ORDERS |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Provide name, contact number, email, address |  |  |  |  |  |
| OTP/email verification for validation |  |  |  |  |  |
| Successful registration confirmation |  |  |  |  |  |
| User Story No: | 2 | Tasks: | 3 | Priority: | High |
| AS A DELIVERY BOY |  |  |  |  |  |
| I WANT TO REGISTER ON THE APP |  |  |  |  |  |
| SO THAT I CAN DELIVER FOOD TO CUSTOMER |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Provide name, contact number, email, address |  |  |  |  |  |
| OTP/email verification for validation |  |  |  |  |  |
| Successful registration confirmation |  |  |  |  |  |
| User Story No: | 3 | Tasks: | 3 | Priority: | High |
| AS A RESTAURANT |  |  |  |  |  |
| I WANT TO REGISTER ON THE APP |  |  |  |  |  |
| SO THAT I CAN PREPARE FOOD FOR THE CUSTOMER |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Provide name, contact number, email, address |  |  |  |  |  |
| OTP/email verification for validation |  |  |  |  |  |
| Successful registration confirmation |  |  |  |  |  |
| User Story No: | 4 | Tasks: | 3 | Priority: | High |
| AS A REGIONAL ADMIN |  |  |  |  |  |
| I WANT TO REGISTER ON THE APP |  |  |  |  |  |
| SO THAT I CAN MANAGER ORDERS, DELIVERY, TRACKING FOOD |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Provide name, contact number, email, |  |  |  |  |  |
| OTP/email verification for validation |  |  |  |  |  |
| Successful registration confirmation |  |  |  |  |  |
| User Story No: | 5 | Tasks: | 3 | Priority: | High |
| AS AN ADMIN |  |  |  |  |  |
| I WANT TO REGISTER ON THE APP |  |  |  |  |  |
| SO THAT I CAN MANAGER ORDERS, DELIVERY, TRACKING FOOD |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Provide name, contact number, email, |  |  |  |  |  |
| OTP/email verification for validation |  |  |  |  |  |
| Successful registration confirmation |  |  |  |  |  |
| User Story No: | 5 | Tasks: | 3 | Priority: | High |
| AS A BUSINESS OWNER |  |  |  |  |  |
| I WANT TO REGISTER ON THE APP |  |  |  |  |  |
| SO THAT I CAN MANAGE PAYEMENTS FOR REASTAURANT AND DELIVERY BOY |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Provide name, contact number, email, |  |  |  |  |  |
| OTP/email verification for validation |  |  |  |  |  |
| Successful registration confirmation |  |  |  |  |  |
| User Story No: | 6 | Tasks: | 3 | Priority: | High |
| AS A BUSINESS OWNER |  |  |  |  |  |
| I WANT TO REGISTER ON THE APP |  |  |  |  |  |
| SO THAT I CAN MANAGE PAYEMENTS FOR REASTAURANT AND DELIVERY BOY |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Provide name, contact number, email, |  |  |  |  |  |
| OTP/email verification for validation |  |  |  |  |  |
| Successful registration confirmation |  |  |  |  |  |
| User Story No: | 7 | Tasks: | 1 | Priority: | Medium |
| AS CUSTOMER |  |  |  |  |  |
| I WANT TO LOGIN SECURELY, |  |  |  |  |  |
| SO THAT I CAN ACCESS MY ACCOUNT AND PLACE ORDERS |  |  |  |  |  |
|  | BV: | 150 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Enter username and password |  |  |  |  |  |
| Verify credentials with database |  |  |  |  |  |
| Redirect to dashboard upon success |  |  |  |  |  |
| User Story No: | 8 | Tasks: | 1 | Priority: | Medium |
| AS A DELIVERY BOY |  |  |  |  |  |
| I WANT TO LOGIN SECURELY, |  |  |  |  |  |
| SO THAT I CAN ACCESS MY ACCOUNT AND DELIVER ORDERS |  |  |  |  |  |
|  | BV: | 150 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Enter username and password |  |  |  |  |  |
| Verify credentials with database |  |  |  |  |  |
| User Story No: | 9 | Tasks: | 1 | Priority: | Medium |
| AS A RESTAURANT |  |  |  |  |  |
| I WANT TO LOGIN SECURELY, |  |  |  |  |  |
| SO THAT I CAN ACCESS MY ACCOUNT AND CHECK ORDERS |  |  |  |  |  |
|  | BV: | 150 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Enter username and password |  |  |  |  |  |
| Verify credentials with database |  |  |  |  |  |
| User Story No: | 10 | Tasks: | 1 | Priority: | Medium |
| AS A DELIVERY BOY |  |  |  |  |  |
| I WANT TO CHECK IS THE PAYMENT RECEIVED OR NOT FROM THE CUSTOMER, |  |  |  |  |  |
| SO THAT IF NOT RECEIVED I CAN COLLECT FROM THE CUSTOMER AT THE TIME OF DELIVERY |  |  |  |  |  |
|  | BV: | 150 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| ORDER DETAILS, PAYMENT PAID OR NOT |  |  |  |  |  |
| IF NOT, How much I need to receive |  |  |  |  |  |
| User Story No: | 11 | Tasks: | 1 | Priority: | Medium |
| AS A DELIVERY BOY |  |  |  |  |  |
| I WANT TO CHECK IS THE PAYMENT RECEIVED OR NOT FROM THE CUSTOMER, |  |  |  |  |  |
| SO THAT IF NOT RECEIVED I CAN COLLECT FROM THE CUSTOMER AT THE TIME OF DELIVERY |  |  |  |  |  |
|  | BV: | 150 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| ORDER DETAILS, PAYMENT PAID OR NOT |  |  |  |  |  |
| IF NOT, How much I need to receive |  |  |  |  |  |
| User Story No: | 12 | Tasks: | 2 | Priority: | High |
| AS CUSTOMER |  |  |  |  |  |
| I WANT TO SEARCH FOR RESTAURANTS |  |  |  |  |  |
| SO THAT I CAN ORDER FROM MY PREFERRED PLACE |  |  |  |  |  |
|  | BV: | 180 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Search by name, cuisine, or rating |  |  |  |  |  |
| Display list with filters (distance, rating, delivery time) |  |  |  |  |  |
| User Story No: | 13 | Tasks: | 3 | Priority: | High |
| AS CUSTOMER |  |  |  |  |  |
| I WANT TO PLACE AN ORDER |  |  |  |  |  |
| SO THAT I CAN RECEIVE FOOD AT MY DOORSTEP |  |  |  |  |  |
|  | BV: | 250 | CP: | 4 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Add items to cart |  |  |  |  |  |
| Proceed to checkout |  |  |  |  |  |
| Confirm order with selected payment method |  |  |  |  |  |
| User Story No: | 14 | Tasks: | 2 | Priority: | Medium |
| AS DELIVERY BOY |  |  |  |  |  |
| I WANT TO VIEW MY ORDERS |  |  |  |  |  |
| SO THAT I KNOW WHICH ORDER TO PICK AND DELIVER |  |  |  |  |  |
|  | BV: | 150 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| View order details (pickup & delivery address) |  |  |  |  |  |
| Accept or decline order |  |  |  |  |  |
| User Story No: | 15 | Tasks: | 1 | Priority: | Medium |
| AS CUSTOMER |  |  |  |  |  |
| I WANT TO TRACK MY ORDER IN REAL TIME |  |  |  |  |  |
| SO THAT I KNOW THE STATUS OF MY DELIVERY |  |  |  |  |  |
|  | BV: | 180 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Live map tracking after order confirmation |  |  |  |  |  |
| Display estimated delivery time |  |  |  |  |  |
| User Story No: | 16 | Tasks: | 2 | Priority: | Medium |
| AS RESTAURANT |  |  |  |  |  |
| I WANT TO SEE RECEIVED ORDERS |  |  |  |  |  |
| SO THAT I CAN PREPARE THEM FOR PICKUP |  |  |  |  |  |
|  | BV: | 160 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Orders visible on dashboard |  |  |  |  |  |
| Time stamp of order received and assigned delivery boy |  |  |  |  |  |
| User Story No: | 17 | Tasks: | 1 | Priority: | Low |
| AS CUSTOMER |  |  |  |  |  |
| I WANT TO CANCEL MY ORDER |  |  |  |  |  |
| SO THAT I CAN MANAGE MY REQUEST IF PLANS CHANGE |  |  |  |  |  |
|  | BV: | 120 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Allow cancellation before order is prepared |  |  |  |  |  |
| Confirmation popup before cancelling |  |  |  |  |  |
| User Story No: | 18 | Tasks: | 3 | Priority: | high |
| AS ADMIN |  |  |  |  |  |
| I WANT TO APPROVE OR REJECT RESTAURANT REGISTRATIONS |  |  |  |  |  |
| SO THAT I CAN ENSURE QUALITY AND COMPLIANCE |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| View pending registration list |  |  |  |  |  |
| Approve/reject with comments |  |  |  |  |  |
| Status change to ‘active’ or ‘rejected’ |  |  |  |  |  |
| User Story No: | 19 | Tasks: | 2 | Priority: | Medium |
| AS DELIVERY BOY |  |  |  |  |  |
| I WANT TO VIEW MY DAILY REVENUE REPORT |  |  |  |  |  |
| SO THAT I CAN TRACK MY EARNINGS |  |  |  |  |  |
|  | BV: | 100 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Daily breakdown of earnings |  |  |  |  |  |
| Filters by date |  |  |  |  |  |
| User Story No: | 20 | Tasks: | 1 | Priority: | Low |
| AS CUSTOMER |  |  |  |  |  |
| I WANT TO GIVE FEEDBACK AFTER DELIVERY |  |  |  |  |  |
| SO THAT I CAN RATE THE SERVICE AND FOOD |  |  |  |  |  |
|  | BV: | 90 | CP: | 1 |  |
| Acceptance Criteria : |  |  |  |  |  |
| 1–5 star rating |  |  |  |  |  |
| Optional comment box |  |  |  |  |  |
| Submitted feedback visible in admin panel |  |  |  |  |  |
| User Story No: | 21 | Tasks: | 2 | Priority: | Low |
| AS CUSTOMER |  |  |  |  |  |
| I WANT TO EDIT MY PROFILE |  |  |  |  |  |
| SO THAT I CAN KEEP MY INFO UPDATED |  |  |  |  |  |
|  | BV: | 116 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Edit Name/email/phone |  |  |  |  |  |
| Save confirmation |  |  |  |  |  |
| User Story No: | 22 | Tasks: | 2 | Priority: | HIGH |
| AS ADMIN |  |  |  |  |  |
| I WANT TO GENERATE REPORTS |  |  |  |  |  |
| SO THAT I CAN ANALYZE PLATFORM METRICS |  |  |  |  |  |
|  | BV: | 117 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Select Date range |  |  |  |  |  |
| Download CSV |  |  |  |  |  |
| User Story No: | 23 | Tasks: | 2 | Priority: | HIGH |
| AS CUSTOMER |  |  |  |  |  |
| I WANT TO CHANGE PASSWORD |  |  |  |  |  |
| SO THAT I CAN SECURE MY ACCOUNT |  |  |  |  |  |
|  | BV: | 118 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Enter old/new password |  |  |  |  |  |
| Save |  |  |  |  |  |
| User Story No: | 24 | Tasks: | 2 | Priority: | Medium |
| AS DELIVERY BOY |  |  |  |  |  |
| I WANT TO VIEW DELIVERY HISTORY |  |  |  |  |  |
| SO THAT I CAN TRACK PAST ORDERS |  |  |  |  |  |
|  | BV: | 119 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| List by date |  |  |  |  |  |
| Filter by Region |  |  |  |  |  |
| User Story No: | 25 | Tasks: | 2 | Priority: | HIGH |
| AS RESTAURANT |  |  |  |  |  |
| I WANT TO RAISE ISSUE |  |  |  |  |  |
| SO THAT I CAN REPORT DELIVERY PROBLEMS |  |  |  |  |  |
|  | BV: | 120 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Select issue type |  |  |  |  |  |
| Submit with comment |  |  |  |  |  |
| User Story No: | 26 | Tasks: | 2 | Priority: | HIGH |
| AS A CUSTOMER |  |  |  |  |  |
| I WANT TO CHAT WITH REG ADMIN |  |  |  |  |  |
| SO THAT I CAN REQUEST FOR REFUND |  |  |  |  |  |
|  | BV: | 200 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| BR-ALL MANDATORY |  |  |  |  |  |
| TEXT BOX FIELDS |  |  |  |  |  |
| DISPLAY ORDER ID |  |  |  |  |  |
| TEXT BOX,FOR DESCRIPTION |  |  |  |  |  |
| SUBMIT BUTTON |  |  |  |  |  |
| GENERATE ISSUE ID |  |  |  |  |  |
| DISPLAY SUCCESSFUL |  |  |  |  |  |
| User Story No: | 27 | Tasks: | 3 | Priority: | HIGH |
| AS A REG ADMIN |  |  |  |  |  |
| I WANT TO MANAGE REGIONAL RESTAURANTS, |  |  |  |  |  |
| SO THAT, I CAN TRACK THE PERFORMANCE OF REGIONAL RESTAURANTS. |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| CLICK ON PERFORMANCE OF RESTAURANTS |  |  |  |  |  |
| SELECT FROM DATE TO DATE |  |  |  |  |  |
| CLINCK ON GENERATE REPORT WHICH INCLUSES RESTAURANTS ID, NAME, |  |  |  |  |  |
| REVENUE |  |  |  |  |  |
| CLICK ON DOWNLOAD REPORT SHOULD BE IN EXCEL |  |  |  |  |  |
| User Story No: | 28 | Tasks: | 2 | Priority: | HIGH |
| AS A BUSINESS OWNER |  |  |  |  |  |
| I WANT TO VIEW RESTAURANT REVENUE REPORT |  |  |  |  |  |
| SO THAT I CAN VIEW THE RESTAURANT’S REVENUE |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Select Reports |  |  |  |  |  |
| Select Revenue Reports |  |  |  |  |  |
| Select to and from date |  |  |  |  |  |
| Select Region (can select all) |  |  |  |  |  |
| Generate Report |  |  |  |  |  |
| Download Report in EXCEL |  |  |  |  |  |
| User Story No: | 29 | Tasks: | 2 | Priority: | Medium |
| AS A RESTAURANT OWNER |  |  |  |  |  |
| I WANT TO PROVIDE TIME SLOTS |  |  |  |  |  |
| SO THAT CUSTOMER CAN CHECK OPENING AND CLOSING HOURS |  |  |  |  |  |
|  | BV: | 200 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Click on restaurant dashboard |  |  |  |  |  |
| Add from time to time |  |  |  |  |  |
| Click on submit |  |  |  |  |  |
| Display updated successfully |  |  |  |  |  |
| User Story No: | 30 | Tasks: | 2 | Priority: | Low |
| AS A CUSTOMER |  |  |  |  |  |
| I WANT TO VIEW THE CONTACT NUMBER OF DELIVERY BOY |  |  |  |  |  |
| SO THAT I CAN CONTACT DELIVERY BOY FOR THE STATUS |  |  |  |  |  |
|  | BV: | 50 | CP: | 1 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Display delivery boy mobile number |  |  |  |  |  |
| Display delivery boy name in tracking field |  |  |  |  |  |
| Display delivery boy picture |  |  |  |  |  |
| User Story No: | 31 | Tasks: | 2 | Priority: | Low |
| AS A CUSTOMER |  |  |  |  |  |
| I WANT TO VIEW THE PRICE |  |  |  |  |  |
| SO THAT I CAN ORDER THE FOOD |  |  |  |  |  |
|  | BV: | 50 | CP: | 1 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Display list of Menu |  |  |  |  |  |
| User Story No: | 32 | Tasks: | 2 | Priority: | Low |
| AS AN ADMIN |  |  |  |  |  |
| I WANT TO VIEW THE RESTAURANTS |  |  |  |  |  |
| SO THAT I CAN APPROVE THEIR REGISTRATION |  |  |  |  |  |
|  | BV: | 50 | CP: | 1 |  |
| Acceptance Criteria : |  |  |  |  |  |
| List of restaurant, select Restaurants, verify restaurant details, approve |  |  |  |  |  |
| button, reject button, notification to the restaurant. |  |  |  |  |  |
| User Story No: | 33 | Tasks: | 2 | Priority: | High |
| AS A CUSTOMER |  |  |  |  |  |
| I WANT TO SELECT THE PAYMENT MODE |  |  |  |  |  |
| SO THAT I CAN MAKE PAYMENT OF MY CHOICE |  |  |  |  |  |
|  | BV: | 500 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Display payment modes, radio buttons to select payment modes, payments buttons |  |  |  |  |  |
| Business Rule. Can select only one payment mode |  |  |  |  |  |
| User Story No: | 34 | Tasks: | 2 | Priority: | MEDIUM |
| AS A DELIVERY BOY |  |  |  |  |  |
| I WANT TO VIEW FEEDBACK |  |  |  |  |  |
| SO THAT I CAN IMPROVE MY SERVICE |  |  |  |  |  |
|  | BV: | 200 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Display Feedback Panel |  |  |  |  |  |
| User Story No: | 35 | Tasks: | 2 | Priority: | Medium |
| AS ADMIN |  |  |  |  |  |
| I WANT TO SEE THE REGIONAL REVENUE REPORTS, |  |  |  |  |  |
| SO THAT I CAN VIEW THE REGIONAL PERFORMANCE |  |  |  |  |  |
|  | BV: | 100 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Select regional dropdown |  |  |  |  |  |
| View performance of each restaurant in that region in tabular form which includes rest name, revenue generated |  |  |  |  |  |
| User Story No: | 36 | Tasks: | 2 | Priority: | Medium |
| AS REGIONAL ADMIN |  |  |  |  |  |
| I WANT TO MANAGE RESTAURANTS IN MY REGION, |  |  |  |  |  |
| SO THAT I CAN ENSURE SERVICE QUALITY |  |  |  |  |  |
|  | BV: | 170 | CP: | 3 |  |
| Acceptance Criteria : |  |  |  |  |  |
| View list of all registered restaurants in the region |  |  |  |  |  |
| Approve/Block restaurant access |  |  |  |  |  |
| User Story No: | 37 | Tasks: | 1 | Priority: | HIGH |
| AS DELIVERY BOY |  |  |  |  |  |
| I WANT TO UPDATE DELIVERY STATUS, |  |  |  |  |  |
| SO THAT I CAN KEEP THE CUSTOMER INFORMED |  |  |  |  |  |
|  | BV: | 110 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Mark order as picked, enroute, and delivered |  |  |  |  |  |
| Update reflects on customer tracking screen |  |  |  |  |  |
| User Story No: | 38 | Tasks: | 1 | Priority: | Low |
| AS BUSINESS OWNER |  |  |  |  |  |
| I WANT TO CHECK ISSUES FACING BY THE BUSINESS OWNER |  |  |  |  |  |
| SO THAT I CAN ENSURE SERVICE QUALITY |  |  |  |  |  |
|  | BV: | 120 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| View issue raised by the Business Owner |  |  |  |  |  |
| Resolve the issue if possible |  |  |  |  |  |
| User Story No: | 39 | Tasks: | 1 | Priority: | MEDIUM |
| AS AN ADMIN |  |  |  |  |  |
| I WANT TO APPROVE OR REJJECT THE PRIVILIGES BY THE RESTAURANT |  |  |  |  |  |
| SO THAT I CAN ENSURE ONLY VERIFIED AND QUALITY RESTAURANTS ARE ALLOWED ON THE PLATFORM. |  |  |  |  |  |
|  | BV: | 150 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Admin should be able to view a list of all pending restaurant registration requests. |  |  |  |  |  |
| Each request must display restaurant name, license/verification documents, location, and contact details. |  |  |  |  |  |
| Upon rejection, the restaurant's status is updated to Rejected, and a rejection email with reasons is sent. |  |  |  |  |  |
| Upon approval, the restaurant's status is updated to Active, and a confirmation email is sent. |  |  |  |  |  |
| Approved restaurants should become accessible in the platform's public restaurant list. |  |  |  |  |  |
| Rejected restaurants should not appear in any public listings. |  |  |  |  |  |
| User Story No: | 40 | Tasks: | 1 | Priority: | LOW |
| AS REGIONAL ADMIN |  |  |  |  |  |
| I WANT TO REFUND IF THE ORDER NOT SATISFIED BY THE CUSTOMER |  |  |  |  |  |
| SO THAT I CAN MAINTAIN CUSTOMER TRUST AND ENSURE QUALITY SERVICE RECOVERY. |  |  |  |  |  |
|  | BV: | 200 | CP: | 2 |  |
| Acceptance Criteria : |  |  |  |  |  |
| Regional Admin should be able to view refund requests raised by customers. |  |  |  |  |  |
| Once approved, refund is initiated to the customer's original payment method. |  |  |  |  |  |
| Each request must include order ID, customer feedback, and reason for dissatisfaction. |  |  |  |  |  |
| Customer receives a confirmation message/email of the refund status. |  |  |  |  |  |
| Admin can approve or reject the refund after review. |  |  |  |  |  |
| Refund record is updated in the system for audit purposes. |  |  |  |  |  |

Question 3– What is epic? Write 2 epics – 5 Marks

Business Value and Complexity Points

### Answer 3. What is an Epic?

An Epic is a large body of work that can be broken down into multiple smaller tasks called User Stories. It represents a high-level business requirement or feature set that may take several sprints to complete. Epics help organize the product backlog and maintain alignment with business goals.

### Epics for Scrum Foods

### Epic 1: Customer Order Management

Description:
This epic covers all functionalities required for a customer to place, manage, and track food orders from registration to delivery.

- Customer registration and login

- Search restaurants and view menus

- Add to cart and place order

- Make payments

- Track orders in real-time

- Cancel orders

- Give feedback and ratings

Business Value (BV): 300
Complexity Points (CP): 13

### Epic 2: Restaurant & Delivery Partner Onboarding

Description:
This epic involves onboarding and managing restaurants and delivery partners, ensuring they are verified, approved, and operational on the platform.

- Restaurant registration and login

- Admin approval/rejection of restaurant profiles

- Delivery partner registration

- Assign delivery partner to orders

- View earnings and order history

- Raise issues and feedback by restaurant or delivery boy

Business Value (BV): 250
Complexity Points (CP): 11

Question 4 –What is the difference between BV and CP – 2 Marks

## Answer 4.  1. Business Value (BV)

### Definition: Business Value (BV) refers to the importance, benefit, or impact a user story or feature brings to the business, customers, or end users. It helps prioritize the backlog by focusing on features that deliver the highest return on investment (ROI) or customer satisfaction.

### Who Assigns It?

Usually determined by the Product Owner in collaboration with stakeholders (like business owners, clients, or marketing).

### What It Represents:

- Revenue potential

- Cost savings

- Customer satisfaction

- Market demand or competitive advantage

- Strategic alignment with business goals

### Scale Example:

| Business Value | Description |
| --- | --- |
| 100 | Must-have; critical for MVP or launch |
| 50 | Important but not urgent |
| 20 | Nice-to-have or cosmetic feature |

### Example in Scrum Foods:

User Story: “As a customer, I want to track my order in real time.”
BV: 100 — Because it enhances user experience and reduces support queries.

## 2. Complexity Points (CP)

### Definition: Complexity Points (CP) represent the effort, difficulty, or risk involved in implementing a user story. It includes coding, testing, integration, research, and dependencies.

### Who Assigns It?

Assigned by the Development Team during estimation sessions (e.g., Planning Poker).

### What It Includes:

- Technical complexity

- Number of integrations/APIs

- Code changes needed

- Uncertainty or unknowns

- Effort in development & testing

### Scale Example

| Complexity Points | Description |
| --- | --- |
| 1 | Very easy, minimal work |
| 3 | Medium effort |
| 8 | High effort or unknowns |
| 13 | Very complex or risky |

### Example in Scrum Foods:

User Story: “As a restaurant, I want to view my daily revenue.”
CP: 5 — Moderate backend calculations and UI updates.

## Summary Table

| Factor | Business Value (BV) | Complexity Points (CP) |
| --- | --- | --- |
| What it measures | Value to business/customer | Technical effort/difficulty |
| Assigned by | Product Owner & Stakeholders | Development Team |
| Helps in | Prioritizing high-value features | Sprint planning and workload estimation |
| Unit | Any numeric scale (10, 50, 100...) | Story points (1, 2, 3, 5, 8, 13...) |
| Example analogy | “How important is it?” | “How hard is it to build?” |

| Aspect | Business Value (BV) | Complexity Points (CP) |
| --- | --- | --- |
| Definition | A measure of the importance or impact of a user story to the business. | A measure of the effort, difficulty, or technical complexity needed to implement the user story. |
| Determined by | Product Owner and Stakeholders | Development Team |
| Purpose | Helps prioritize what delivers the most value to users/business. | Helps estimate time, resources, and effort needed to complete the work. |
| Unit of Measure | Numerical value (e.g., 10, 50, 100, etc.) | Story Points (e.g., 1, 3, 5, 8, 13...) |

Question 5 –Explain about Sprint– 5 Marks

Sprint Understanding

What is sprint Duration: 2 Weeks - Your sprint Value

Scrum is a subunit of Sprint.

What is scrum Duration: 1 day – Your scrum Value ?

PBI: Product Backlog Item

Task: Unit of Work done by 1 Developer in 1 Scrum

WIP: Work In Progress

Sprint Backlog

PBI Tasks WIP Done

### Answer 5. Definition of a Sprint:

A Sprint is a time-boxed iteration in the Scrum framework, typically lasting 1 to 4 weeks, during which a usable and potentially shippable product increment is created. It is the heartbeat of Scrum, ensuring continuous delivery and feedback.

### Key Characteristics of a Sprint:

| Feature | Description |
| --- | --- |
| Time-boxed | Usually 2 weeks (but can range from 1 to 4 weeks) and has a fixed duration |
| Goal-driven | Has a Sprint Goal, which defines what will be delivered during the Sprint |
| Focused | Team commits to completing selected Product Backlog Items (PBIs) |
| No changes allowed | Once a Sprint starts, scope is locked to avoid distractions and shifting focus |
| Ends with a review | Completed work is shown in a Sprint Review, and improvements discussed in Sprint Retrospective |

### Sprint Lifecycle Overview:

- Sprint Planning:
The team selects PBIs from the Product Backlog and defines the Sprint Goal.

- Daily Scrum:
A 15-minute daily meeting to discuss progress, plans, and impediments.

- Development Work:
Team works on tasks to build the committed product increment.

- Sprint Review:
Stakeholders review the increment and provide feedback.

- Sprint Retrospective:
The Scrum Team reflects on the Sprint and identifies improvements.

### Benefits of Sprint:

- Faster delivery of working software

- Early and regular feedback from stakeholders

- Increased team focus and collaboration

- Continuous improvement through retrospectives

- Easy to adapt to changing requirements

### Example from Scrum Foods Project:

In Scrum Foods, a 2-week Sprint might include:

- Implementing real-time delivery tracking

- Adding restaurant approval workflow for Admin

- Testing and deploying customer feedback module

### Scrum

Scrum refers to the daily stand-up meeting within a Sprint, where the Development Team syncs up on progress, plans, and impediments.

- Scrum Duration: 15 minutes per day

- Scrum Value: Promotes transparency, early detection of blockers, and team alignment.

### PBI – Product Backlog Item

A PBI is a feature, requirement, or enhancement that delivers value to the customer. It is selected during Sprint Planning and broken into smaller executable units.

### Task

A Task is the smallest unit of work derived from a PBI that can be completed by one developer within one Scrum day.

- Example:

  - PBI: “Implement order tracking”

  - Task: “Integrate Google Maps API for real-time tracking”

### WIP – Work In Progress

WIP refers to the tasks or PBIs that are currently being worked on but are not yet completed. Managing WIP limits helps improve flow and reduce context switching.

### Sprint Backlog

The Sprint Backlog is a subset of the Product Backlog selected for a specific Sprint, including:

- PBIs committed by the team

- Associated tasks for each PBI

- Their current status (To Do, WIP, Done)

### Sprint Backlog Table:

| PBI | Tasks | Status |
| --- | --- | --- |
| Customer Registration | UI Form Design, DB Integration | WIP |
| Order Tracking | API Integration, UI Updates | To Do |
| Restaurant Approval Workflow | Verify Docs, Approval Logic | Done |

Question 6. Explain Product backlog and sprint back log– 5 Marks

Sprint Planning Meeting: All 8 Scrum Developers will gather before the sprint starts and understand how many user stories, they can develop in 1 sprint (2 weeks), and move them from the product Backlog to the sprint Backlog. They take inputs from Sprint Retrospective meeting.

Scrum Meeting – Daily Stand-up Meeting

End of every Scrum, Scrum Developers will participate in Scrum meeting. Here they must answer 3

Questions.

a. What task did you work in this scrum?

b. What task will you work on next scrum?

c. Any Challenges/impediments? When you will complete the user story?

### Answer 6. Product Backlog:

The Product Backlog is a master list of all desired features, enhancements, bug fixes, and technical tasks for the product. It is dynamic, constantly evolving, and prioritized by the Product Owner based on business value and customer needs.

- Contains Product Backlog Items (PBIs)

- Prioritized from highest to lowest value

- Updated continuously based on feedback, changes, or new ideas

- Serves as the single source of truth for work to be done

Example:
"Customer registration", "Order tracking", "Restaurant approval workflow", etc.

### Sprint Backlog:

The Sprint Backlog is a subset of the Product Backlog, selected during the Sprint Planning Meeting. It contains the PBIs the development team commits to complete during the upcoming Sprint (e.g., 2 weeks).

- Includes detailed tasks broken down from each PBI

- Owned and maintained by the Scrum Developers

- Updated daily during the Sprint

- Provides visibility into progress (To Do, WIP, Done)

Goal: To complete all Sprint Backlog items and deliver a potentially shippable increment.

## Sprint Planning Meeting

Before a Sprint begins, all 8 Scrum Developers meet with the Product Owner and Scrum Master in a Sprint Planning Meeting. Here’s what happens:

- Review the Product Backlog

- Select User Stories (PBIs) they can complete in 1 Sprint (2 weeks)

- Break PBIs into tasks

- Move selected items into the Sprint Backlog

- Take improvement inputs from the previous Sprint Retrospective

Outcome: A clear Sprint Goal and a Sprint Backlog the team commits to.

Scrum Meeting – Daily Stand-up

Held daily (15 mins), every Scrum Developer answers 3 important questions:

- What task did you work on in the last Scrum?

- What task will you work on in the next Scrum?

- Are there any challenges or impediments?

  - (Also, when do you expect to complete the assigned user story?)

Question 7 – What is impediments log? write 2 impediments – 5 Marks

### Answer 7. Definition:

An Impediments Log is a centralized document or tracker used in Scrum to record, monitor, and manage all issues or blockers that are affecting the team's progress during a Sprint.

Impediments are anything that slow down or stop the Scrum Team from achieving the Sprint Goal — these could be technical, process-related, people-related, or external dependencies.

The Scrum Master is responsible for maintaining this log and actively working to resolve these issues.

Purpose of the Impediments Log:

- Track and document reported blockers

- Assign ownership for resolution

- Ensure transparency and accountability

- Help in Sprint Retrospectives to analyze recurring issues

- Improve team efficiency and delivery consistency

### Impediments Log:

| ID | Date Logged | Impediment Description | Raised By | Owner | Status | Resolution Date |
| --- | --- | --- | --- | --- | --- | --- |
| 001 | 15-Jun-2025 | Database access not provided to developer | Yogender | Scrum Master | Open | - |
| 002 | 17-Jun-2025 | Delay in UI approval from Product Owner | Madhuri | Product Owner | Resolved | 19-Jun-2025 |

### Example Impediments (2):

- "Database access not provided to developers"

  - This blocked backend integration for Order History page.

  - Resolution: Access granted by the IT team after escalation by Scrum Master.

- "Delay in UI approval for restaurant dashboard"

  - Developers were waiting on final design approval to begin front-end work.

  - Resolution: Product Owner reviewed and approved UI within 2 days after follow-up.

Question 8 – Explain Velocity of the Team – 1 Marks

Velocity – How many CP is covered in this sprint

### Answer 8. Velocity - Velocity refers to the total number of Complexity Points (CP) completed by the Scrum Team in a single Sprint.

### Definition: Velocity = Total CP of user stories completed in the Sprint.

It helps in forecasting how much work the team can handle in future Sprints and is a key metric for Sprint Planning.

Example: If the team committed to 8 user stories totalling 40 CP in a 2-week Sprint and completed all of them, Velocity = 40 CP

If they completed only 6 out of 8 stories (30 CP),

Velocity = 30 CP

Question 9 – Draw Sprint Burn Charts n Product Burn Down Charts– 3 Marks

### Answer 9. Sprint Burn Down Chart

A Sprint Burn Down Chart is a graphical representation that shows the remaining work (in Story Points or Complexity Points) in a Sprint over time.

- It tracks daily progress within a single Sprint (usually 1–4 weeks).

- The Y-axis represents the remaining work (CP or tasks).

- The X-axis represents the days of the Sprint.

- The chart compares Ideal Progress vs. Actual Progress.

- It helps the team and stakeholders know if they are on track to complete the committed work by the end of the Sprint.

Purpose:
To monitor the team’s daily progress and identify delays or blockers early.

About the Diagram

- Tracks progress within a single Sprint (2 weeks = 10 days).

- Shows how many Complexity Points (CP) remain each day.

- Compares Ideal Burn (gray dashed line) vs. Actual Burn (blue line).

- Helps visualize whether the team is on track to complete all user stories.

### Product Burn Down Chart

A Product Burn Down Chart tracks the total remaining work in the entire Product Backlog across multiple Sprints.

- The Y-axis shows total remaining Complexity Points or Story Points.

- The X-axis shows each Sprint.

- It gives a high-level view of how quickly the product is progressing toward completion.

- Used by Product Owners, Scrum Masters, and Stakeholders for release planning and forecasting.

Purpose:
To visualize the overall project progress and determine when the product might be ready for release.

About the Diagram

- Tracks progress across multiple Sprints (e.g., 4 Sprints).

- Displays the total remaining CP in the Product Backlog after each Sprint.

- Shows how the product is evolving toward completion.

Question 10 – Explain about Product Grooming – 2 Marks

### Answer 10. What is Product Grooming?

Product Grooming, also known as Backlog Grooming or Backlog Refinement, is a collaborative meeting in Agile where the Scrum Team reviews and revises the Product Backlog to ensure it is prioritized, clear, and ready for upcoming Sprints.

### Purpose of Product Grooming:

- To break down large user stories into smaller, manageable ones

- To clarify requirements and remove any ambiguity

- To add acceptance criteria

- To estimate Complexity Points (CP)

- To prioritize items based on business value and urgency

### Who Attends?

- Product Owner (PO) – leads the session

- Scrum Team (Developers & Scrum Master)

- Stakeholders (optional)

### When is it done?

- Typically done once or twice per Sprint

- Duration: 30–60 minutes, depending on backlog size

### Example:

If a user story like “As a customer, I want to track my food order” is too broad, during grooming it may be broken down into:

- Display estimated delivery time

- Show delivery partner location

- Notify when the order is dispatched

Summary:

Product Grooming ensures the backlog is always clean, refined, and prioritized, so the team can start Sprint Planning efficiently with well-defined, actionable items.

Question 11 – Explain the roles of Scrum Master and Product Owner – 3 Marks

### Answer 11. Scrum Master – Role & Responsibilities

### The Scrum Master is a servant-leader responsible for ensuring that the Scrum framework is understood and followed by the team. They facilitate processes, remove impediments, and support the team’s productivity.

#### Key Responsibilities:

- Facilitates Scrum ceremonies (Daily Stand-up, Sprint Planning, Review & Retrospective)

- Removes obstacles or impediments blocking team progress

- Coaches the team on Agile practices and principles

- Ensures team adheres to Scrum values and rules

- Acts as a bridge between team and stakeholders (without managing the team)

### Product Owner – Role & Responsibilities

The Product Owner (PO) is responsible for maximizing the value of the product resulting from the work of the Scrum Team. They manage the Product Backlog and ensure the team builds the right product features based on business priorities.

#### Key Responsibilities:

- Defines and prioritizes Product Backlog Items (PBIs)

- Communicates with stakeholders to gather and refine requirements

- Ensures the development team understands what to build and why

- Accepts or rejects work based on acceptance criteria

- Represents the voice of the customer/business

### Summary:

| Role | Focus | Key Responsibility |
| --- | --- | --- |
| Scrum Master | Scrum Process & Team Efficiency | Facilitates, coaches, removes blockers |
| Product Owner | Product Direction & Business Value | Manages backlog, prioritizes features |

Question 12 – Explain all Meetings Conducted in Scrum Project – 8 Marks

Answer 12. Scrum framework includes 5 key events (ceremonies) to ensure continuous delivery, collaboration, and improvement throughout the project lifecycle. These meetings are designed to keep the team aligned, focused, and flexible.

### 1. Sprint Planning Meeting

- When: At the beginning of each Sprint

- Who Attends: Product Owner, Scrum Master, Scrum Team

- Purpose:

  - Decide what work will be completed in the Sprint

  - Break down Product Backlog Items (PBIs) into tasks

  - Estimate effort (Complexity Points) and commit to goals

Output: Sprint Goal, Sprint Backlog

### 2. Daily Scrum (Stand-Up Meeting)

- When: Every day during the Sprint (15 minutes max)

- Who Attends: Scrum Team (Scrum Master facilitates)

- Purpose:

  - Share progress

  - Plan the day

  - Identify any impediments

Each team member answers:

- What did I do yesterday?

- What will I do today?

- Any blockers or challenges?

### 3. Sprint Review Meeting

- When: At the end of the Sprint

- Who Attends: Scrum Team + Stakeholders

- Purpose:

  - Demonstrate the working product increment

  - Gather feedback from stakeholders

  - Adjust the Product Backlog if needed

Output: Input for future Sprints, product acceptance or rework

### 4. Sprint Retrospective

- When: Immediately after Sprint Review

- Who Attends: Scrum Team (PO optional)

- Purpose:

  - Reflect on the Sprint

  - Identify what went well, what can be improved, and how to improve

  - Plan for process improvements

Output: Action items for the next Sprint

### 5. Product Backlog Grooming (Refinement)

- When: Mid-Sprint (1–2 sessions per Sprint)

- Who Attends: Product Owner, Scrum Team, Scrum Master

- Purpose:

  - Review and prioritize the Product Backlog

  - Break down large user stories

  - Add acceptance criteria and estimates

Output: Well-defined and prioritized backlog ready for Sprint Planning

### Summary Table:

| Meeting | When | Purpose | Participants |
| --- | --- | --- | --- |
| Sprint Planning | Start of Sprint | Decide Sprint Goal, plan work | PO, Scrum Master, Developers |
| Daily Scrum | Every day (15 mins) | Share status and blockers | Scrum Team |
| Sprint Review | End of Sprint | Demo product, get feedback | Scrum Team, Stakeholders |
| Sprint Retrospective | After Sprint Review | Improve team processes | Scrum Team |
| Backlog Grooming | Mid-Sprint (1–2 times) | Refine, prioritize, and estimate backlog items | PO, Scrum Master, Developers |

Question 13 – Explain Sprint Size and Scrum Size– 2 Marks

### Answer 13. Sprint Size:

- Definition:
Sprint Size refers to the duration of a Sprint in Agile Scrum.

- Standard Duration:
Usually between 1 to 4 weeks depending on the project complexity and team capacity.

- Common Sprint Size:
In most projects, a 2-week Sprint is standard, allowing quick delivery and regular feedback.

Example:
In the Scrum Foods project, the Sprint size is 2 weeks (10 working days), during which the Scrum team commits to delivering a set of user stories.

### Scrum Size:

- Definition:
Scrum Size refers to the frequency and duration of daily Scrum meetings during a Sprint.

- Standard Practice:
One Scrum (Daily Stand-up) per day, lasting 15 minutes.

- Purpose:
Team members share updates, plan the day, and surface any blockers.

Example:
In a 2-week Sprint (10 working days), there are 10 Scrums, each lasting 15 minutes.

### Summary Table:

| Term | Definition | Standard Value |
| --- | --- | --- |
| Sprint Size | Duration of a full Sprint | 1 to 4 weeks (commonly 2) |
| Scrum Size | Duration of one daily stand-up meeting | 15 minutes per day |

Question 14 – Explain DOR and DOD – 2 Marks

### Answer 14. DOR – Definition of Ready

Definition: The Definition of Ready (DOR) is a checklist that ensures a user story is well-prepared before it can be picked up in a Sprint.

Purpose: It confirms the user story is clear, feasible, and testable.

Typical DOR Checklist:

- User Story is clearly written and understood by the team

- Acceptance Criteria are defined

- Dependencies are identified and resolved

- Estimation is done

- Business Value is clear

Example:
Before development begins on “Customer can track orders,” it must have clear steps, acceptance criteria, and no blockers — then it's “Ready.”

### DOD – Definition of Done

Definition: The Definition of Done (DOD) is a checklist used to ensure a user story is completely finished.

Purpose: It ensures that the product increment meets the team's quality standards and is ready for release.

Typical DOD Checklist:

- Code is developed and reviewed

- Unit and integration testing are complete

- Accepted by Product Owner

- No critical bugs

- Deployed to staging or production

Example:
When “Restaurant can view feedback” passes all tests, is reviewed, and accepted by the PO — it’s considered “Done.”

### Summary:

| Term | Meaning | Used When |
| --- | --- | --- |
| DOR | Ready to start development | Before Sprint starts |
| DOD | Work is fully complete and shippable | At end of Sprint |

Question 15 – Explain Prioritization Techniques and MVP – 3 Marks

### Answer 15. Prioritization Techniques in Agile: Agile teams use prioritization techniques to decide which features or user stories to implement first based on value, urgency, and effort. Common techniques include:

1. MoSCoW Technique

- Must Have – Essential features without which the product will fail

- Should Have – Important but not vital for initial release

- Could Have – Nice to have, low impact

- Won’t Have – Out of scope for now

Example: “Customer registration” is a Must Have, while “Dark Mode” may be Could Have

### 2. Value vs. Effort Matrix

- Plot user stories based on Business Value vs. Development Effort

- High value + Low effort → Top Priority

- Low value + High effort → Lowest Priority

Used in Product Grooming meetings

### 3. Kano Model

- Categorizes features based on customer satisfaction

  - Basic Needs

  - Performance Needs

  - Excitement Needs

Useful in UX-focused products

### MVP – Minimum Viable Product

Definition: MVP is the simplest version of a product that can be released to early adopters with just enough features to deliver value and gather feedback.

### Purpose of MVP:

- Validate business idea early

- Reduce development time and cost

- Get real user feedback

- Avoid building unnecessary features

Example in Scrum Foods:
An MVP could include only:

- Customer registration

- Restaurant menu viewing

- Placing an order

- Payment

Advanced features like delivery tracking, coupons, and feedback can be added later based on feedback.

### Summary Table:

| Concept | Purpose |
| --- | --- |
| MoSCoW | Prioritize features by importance |
| Value vs Effort | Pick high-value, low-effort items first |
| MVP | Deliver basic but functional version early |

Question 16 – Difference between Business Analyst n Product Owner – 3 Marks

### Answer 16. Definition of Business Analyst (BA):

A Business Analyst is a professional who identifies business needs, analyses processes, gathers and documents requirements, and acts as a bridge between stakeholders and the development team. The BA ensures that the solution built by the team aligns with the business goals and user expectations.

Think of the BA as the voice of the business — ensuring the team understands what the business really needs.

### Definition of Product Owner (PO):

A Product Owner is a role in the Scrum framework responsible for maximizing the value of the product by managing the product backlog. The PO works closely with stakeholders and the development team, decides priorities, and ensures that the team delivers the right features at the right time.

Think of the PO as the owner of the product vision — deciding what to build and when.

## Business Analyst vs Product Owner

| Aspect | Business Analyst (BA) | Product Owner (PO) |
| --- | --- | --- |
| Role Definition | Gathers, analyzes, and documents business requirements | Owns the product, defines features, and sets priorities |
| Focus Area | Problem analysis, requirement gathering, stakeholder coordination | Maximizing product value through backlog management |
| Authority Level | Usually advisory — supports decision making | Has the authority to make product decisions |
| Backlog Ownership | May contribute, but does not own the backlog | Owns and manages the Product Backlog |
| Stakeholder Communication | Acts as a bridge between stakeholders and developers | Works closely with stakeholders to gather input |
| Decision Making | Provides insights for decisions, not final authority | Has final say on what gets built and when |
| Sprint Involvement | Participates in planning and grooming | Leads grooming, planning, prioritization |
| Deliverables | BRD, FRD, Use Cases, Process Flows, Reports | User Stories, Acceptance Criteria, Backlog items |

### Key Difference in Simple Terms:

- The Business Analyst finds out what the business needs and helps define it clearly.

- The Product Owner decides which of those needs to build, when, and ensures the development team is aligned with business goals.

### Example in Scrum Foods Project:

- BA: Gathers inputs from customers and restaurants, documents features like order tracking, feedback system, etc.

- PO : Decides to prioritize real-time tracking and fast checkout in the next Sprint, creates user stories, and accepts/rejects deliverables.

Question 17 – Prepare a sample Resume of 3yrs exp Product Owner – 3 Marks

## Answer 17. SAMPLE RESUME – PRODUCT OWNER (3 YEARS EXPERIENCE)

### See Below

### Name: Priya Mehta

📞 +91-XXXXXXXXXX | 📧 priya.mehta@email.com
📍 Pune, Maharashtra | [LinkedIn Profile]

### 🎯 Career Objective

Certified Product Owner with 3 years of experience in Agile product development, backlog management, and stakeholder collaboration. Proven ability to translate business needs into functional features, manage cross-functional Scrum teams, and deliver high-quality product increments. Seeking to contribute to innovative digital products in a growth-oriented organization.

### 💼 Professional Experience

#### Product Owner

COEPD IT Solutions – Pune
📅 May 2022 – Present

- Managed the Scrum Foods food delivery app development lifecycle with 8 developers under Scrum methodology.

- Created and prioritized a product backlog of 40+ user stories with clear Acceptance Criteria, BV & CP.

- Led Sprint Planning, Grooming, Reviews, and Retrospectives for 2-week sprint cycles.

- Collaborated with stakeholders: restaurants, delivery agents, and administrators to gather feedback and translate into functional requirements.

- Used tools like JIRA, Confluence, Trello for sprint tracking and documentation.

- Ensured product delivery aligned with the vision of safe, real-time, 24/7 food delivery.

Key Achievements:

- Reduced delivery time complaints by 40% by prioritizing real-time tracking features.

- Delivered MVP in 3 sprints, enabling early user testing and feedback.

### 📚 Education

PG Diploma in Business Management
XYZ University, Pune – 2021

Bachelor of Commerce (B.Com)
XYZ University, Pune – 2019

### 🛠️ Technical Skills

- Agile/Scrum, Product Backlog, User Stories, Sprint Planning

- Tools: JIRA, Confluence, MS Excel, Trello, Figma

- Documentation: BRD, FRD, User Stories, Acceptance Criteria

- Communication, Stakeholder Management, Prioritization Techniques

### 📜 Certifications

- Certified Scrum Product Owner (CSPO) – Scrum Alliance – 2022

- Agile Business Analyst – COEPD – 2021

### ⭐ Core Competencies

- Product Lifecycle Management

- Agile Delivery & Scrum Ceremonies

- Requirements Gathering & User Story Mapping

- MVP Planning & Release Management

- Cross-Functional Team Leadership