Question 1

| We Value | Over |
| --- | --- |
| Individuals and Interactions | Processes and Tools |
| Working Products | Comprehensive Documentation |
| Customer Collaboration | Contract Negotiation |
| Responding to Feedback | Following a Plan |

| # | Principle |
| --- | --- |
| 1 | Our highest priority is to satisfy the customer through early and continuous delivery |
| 2 | Welcome changing requirements, even late in development |
| 3 | Deliver working product frequently |
| 4 | Business-people and cross-discipline teams must work together daily |
| 5 | Build projects around motivated individuals and trust them to get the job done |
| 6 | The most effective and efficient method of conveying information is face-to-face conversation |
| 7 | Working product is the primary measure of progress |
| 8 | Maintain a sustainable pace indefinitely |
| 9 | Give continuous attention to technical excellence |
| 10 | Simplicity – the art of maximizing the amount of work not done is essential |
| 11 | Teams self-organize |
| 12 | Teams regularly reflect and adjust to become more effective |

Question 2:

| User Story No |  | Tasks | Priority | As a | I want to | So that | BV | CP | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 |  | Highest | Delivery Boy | Register in Scrum Foods | I can deliver orders | 500 | 02 | Registration Screen, Text Boxes for User Name, Password, Nation ID, Mobile No, Email, Address, Phone Number. Click on Register Button. Send Successful Notification to the user. |
| 2 | 2 |  | Highest | Restaurant Owner | View Orders | I can view the list of orders | 500 | 02 | View Order, Display List of orders in the tabular Form |
| 3 | 2 |  | Highest | Customer | Add the address | I can get the order to my address | 500 | 02 | Text Box to enter. Business Rules: Within the radius of 5 km |

| Field | User Story No. 4 | User Story No. 5 (Admin) | User Story No. 6 (Customer) |
| --- | --- | --- | --- |
| Story Type | As a Customer | As an Admin | As a Customer |
| Goal | I want to select the payment mode so that I can make payment of my choice | I want to view the restaurants so that I can approve their registration | I want to view the price so that I can order the food |
| BV | 500 | 500 | 50 |
| CP | 3 | 2 | 1 |
| Acceptance Criteria | Display payment modes, radio buttons to select payment modes, payments button. | Register in the platform with the details | Display price in the list of menu items |
| Business Rule | Can select only one payment mode |  |  |
| Tasks | 2 | 1 | 1 |
| Priority | Highest | Highest | Low |

| User Story No |  | Tasks | Priority | As a | I want to | So that | BV | CP | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7 | 2 |  | Low | Customer | View the contact number of delivery boy | So that I can contact delivery boy for the status | 50 | 01 | 1. Display delivery boy mobile number<br>2. Display delivery boy name in tracking field<br>3. Display delivery boy picture |
| 8 | 2 |  | Medium | Restaurant Owner | Provide time slots | customer can check opening and closing hours | 100 | 02 | 1. Click on restaurant dashboard 2. Add time slot<br> 3. Submit on submit<br> 4. Display updated successfully |
| 9 | 2 |  | High | Business Owner | View Restaurant Revenue report | I can view Restaurant revenue | 200 | 03 | Select Reports and revenue Select to & from date. Select region (select all) & generate all reports. |
| 10 | 3 |  | High | Regis Admin | Manage Regional Restaurants | Can track the performance | 200 | 03 | Click on performance of reports & select from date to date, click on generate reports, which includes restaurant id, name and revenue. |
| 11 | 2 |  | Medium | Admin | Regional Revenue reports | I can view regional performance | 100 | 03 | Select regional dropdown, view performance of each rest of that region in tabular form which includes rest name, revenue generated |
| 12 | 2 |  | High | Customer | Chat with Reg Admin | I can request for refund | 200 | 02 | BR-ALL Mandatory Text Box fields.ds. Display order ID Text box for description Generate issue ID |
| 13 | 2 |  | High | Hungry User | Browse Nearby Hotels | I can order food | 200 | 02 | Each restaurant entry displays its name, cuisine type and rating |
| 14 | 2 |  | High | Customer | Browse Different Hotels And Menu | I Can find a place to order food | 200 | 02 | Menu includes dishes price and description Show restaurant is open or closed |
| 15 | 1 |  | High | Customer | Browse for specific dishes and cuisines | I can find a place to order food | 200 | 02 | App displays relevant restaurant and dishes matching the query |
| 16 | 1 |  | High | Customer | Filter Restaurant | I Can find a place to order food | 200 | 02 | Filter restaurants by cuisine type & delivery options (vegans, non-vegans) |
| 17 | 1 |  | High | User | Rate & Review | I can rate and suggest reviews to restaurant I visited | 200 | 02 | Can see reviews from other customers to help me make dining decision |
| 18 | 2 |  | High | Customer | Browse Different Hotels And Menu | I Can find a place to order food | 200 | 02 | Menu includes dishes price and description Show restaurant is open or closed |
| 19 | 1 |  | High | User | Want to view past order history | I can order again | 200 | 02 | Can see details such as order items, total cost & order date. |
| 20 | 3 |  | High | User | Receive notifications | I can receive updates | 200 | 02 | Notification for order confirmation Notification for dispatch & delivery |
| 21 | 1 |  | Medium | Customer | Want to contact customer care support | I can submit Queries and raise issues | 200 | 02 | Customer care support section with contact information |
| 22 | 2 |  | High | Restaurant Owner | Receive & manage order | I can update order status | 200 | 02 | Manage order status Notify restaurants about upcoming order |
| 23 | 2 |  | High | Restaurant Owner | Want to access to customer reviews | I can view & respond to customer reviews | 200 | 02 | Owner can address feedback Basis on feedback, owner can improve their services |
| 24 | 1 |  | Medium | A Customer | Want to apply promocodes & Discounts | I can order at lower price | 100 | 4 | Active promocodes |
| 25 | 7 |  | High | Delivery Boy | View order | Accept order | 200 | 4 | - Order visibility - Real time updates - Order details - Order filtering & Sorting - Order Map view & Navigation |
| 26 | 5 |  | High | Delivery Boy | Want to login | I can accept the order | 200 | 4 | - User Authentication - Error Handling - Password security |
| 27 | 5 |  | Medium | Delivery Boy | Want to view feedback | I can get customer feedback | 200 | 4 | - Access to feedback system - Feedback visibility & sorting - Response Mechanism - User support |
| 28 | 5 |  | Medium | Admin | Want to view feedback | I can get customer feedback | 200 | 4 | - Access to feedback system - Feedback visibility & sorting - Response Mechanism |
| 29 | 5 |  | Medium | Restaurant Owner | View feedback | I can get the customer feedback | 200 | 04 | - Access to feedback system - Feedback visibility & sorting - Response Mechanism |
| 30 | 3 |  | High | Admin | Want to know issues | I can resolve them | 100 | 3 | - Display Issue section - Sorting & filtering of issues - Editing & modifying issues |
| 31 | 3 |  | High | Regional Admin | Want to know issues | I can resolve them | 200 | 4 | - Display Issue section - Sorting & filtering of issues - Editing & modifying issues |
| 32 | 6 |  | High | Restaurant Owner | View revenue generated | I view Restaurants revenue | 200 | 4 | 1)Select Reports 2) Select revenue reports 3)Select to and from date 4) Generate report |
| 33 | 2 |  | High | Restaurant Owner | I want to know Delivery boy | I verify Delivery Boy | 200 | 4 | ID Proof Punctuality & reliabiliy |
| 34 | 2 |  | Low | Customer | View contact no of delivery Boy | I can contact him | 50 | 01 | - Display delivery boy contact no. - Boys name in tracking field - Delivery boy picture |
| 35 | 2 |  | Medium | Restaurant Owner | Provide time slots | Customer can check opening & Closing hours | 100 | 02 | - Click on restaurant dashboard - Add from time to time - Click on submit - Display updated successfully |
| 36 | 2 |  | Medium | Online User | File a complaint about delivery executive | Scrum Delivery app can take necessary action | 500 | 05 | - Complaint should be forwarded to Scrum Delivery app. - If no necessary action taken, matter needs to get escalated to higher authority. |
| 37 | 2 |  | High | Online User | Choose my preferred payment mode | I can make payment using preferred mode | 500 | 05 | - The payment options should be displayed in the app. - If the payment is through UPI, a message will confirm the payment & order placement. |

Question 3:

What is epic? Write 2 epics

Epic is a large user story or a collection of related user stories that represents a significant feature or functionality

Epics are high level. Multiple sprints or iterations and they provide a way to organize and prioritize works in product backlog.

2 Epics

EPICS

- Ratings and reviews

- Schedule orders

Epic 1. Ratings and reviews:

As a user, I want to view ratings and reviews for restaurants on scrum food delivery, so that I can make informed decisions about where to order food from.
As a user, I want to provide ratings and reviews for restaurants on scrum food delivery application, so that I can share my experience with other users and contribute to the community.

- Acceptance criteria:

- User can view average ratings and reviews for each restaurant on the restaurant detail page

- User can read detailed reviews and comments left by the customer

- User can sort and filter reviews based on the criteria such as rating, recently and relevance

- User can rate a restaurant and leave a review after placing order

- User can edit or delete their own review on specified time period

- Reviews are displayed in a way that provides helpful insights to other users

- The rating and review system maintains the integrity and authenticity of user feedback

Epic 2. Scheduled order:

✅ As a user, I want to schedule food orders in advance on scrum food delivery application so that I can place meals ahead of the time and avoid last-minute hassles.
✅ As a user, I want to have the flexibility to choose specific delivery time slots for scheduled orders on scrum food delivery application.

- Acceptance criteria:
 User can select a future date and time for placing a scheduled order.
User can browse and order from available restaurants during scheduled order placement.
User can choose from available delivery time slots during the day, afternoon, evening, and night.
 User can modify or cancel orders within a specific timeframe.
 User receive reminders and notification regarding their scheduled order including order confirmation and upcoming delivery alerts.
 The system handles scheduled orders seamlessly, ensuring timely delivery and accurate order fulfilment.

Question 4 –What is the difference between BV and CP – 2 Marks

Techniques used in BV:

- Moscow technique

- Currency notes technique

CP (Customer Priority) represents the importance and urgency of a user story or feature from the perspective of the customer or end user.

Techniques used in CV:

- Planning poker

Evaluate business value (BV):

- Assess the potential impact on revenue generation, cost saving or other measurable business metrics. For example, a user story that enables upselling or introduces a new revenue stream would have high BV.

- Consider the alignment of the user story with the strategic objectives and long-time vision of the scrum food delivery application.

- Assign a relative value or weight to each user story based on its potential business impacts.

Evaluate Complexity points (CP)

- Understand the needs, pinpoints and exceptions of the end user (customers) of the scrum food delivery application.

- Consider user feedback, user research and market demand to gauge the importance of the user story from the customer’s perspective.

- Assess the potential impact on enhancing the user experience, improving convenience or addressing critical user needs.

- Assign a relative priority or weight to each user story based on its significance to the customer.

Question 5 –Explain about Sprint– 5 Marks

In the context of software development and project management, a sprint is a time-boxed, iterative development period during which a specific set of tasks and goals are worked on by a development team. Sprint is a core concept in Agile methodologies, such as Scrum, which emphasizes flexibility, collaboration, and delivering value to the customer in shorter cycles. Here are the key characteristics and components of a sprint:

Time Frame: A sprint typically has a fixed duration, often ranging from i to 4weeks. The duration is consistent across all sprints to provide a predictable cadence for development and planning. *Goals and Objectives: At the beginning of each sprint, the development team, along with stakeholders, selects a set of user stories, features, or tasks to work on during that sprint. These items are collectively referred to as the sprint backlog.

Planning: During sprint planning, the development team breaks down the selected items from the product backlog into smaller tasks and estimates the effort required for each task The team commits to completing these tasks within the sprint duration.

Daily Stand-ups: Throughout the sprint, the team holds daily stand-up meetings (also known as daily scrums) to discuss progress, obstacles, and plans. Each team member shares what they've accomplished, what they're working on, and any challenges they're facing. These meetings foster communication and collaboration.

Development: The development team works on the tasks identified in the sprint backlog. They collaborate closely, often using techniques like pair programming and frequent code reviews to ensure high-quality work.

Continuous Integration: Developers integrate their code changes into the main codebase regularly, ensuring that the software remains functional and stable throughout the sprint.

Testing: Testing is an integral part of a sprint. Automated tests are run to validate code changes, and manual testing may be conducted to ensure the quality of the software.

Review and Demo: At the end of the sprint, the development team conducts a sprint review and demo. They showcase the completed work to stakeholders, gathering feedback and validation. This helps ensure that the delivered features align with expectations.

Retrospective: Following the review and demo, the team holds a sprint retrospective. They reflect on what went well during the sprint, what could be improved, and actions to take in the next sprint. The retrospective encourages continuous improvement.

Incremental Development: Each sprint results in a potentially shippable product increment, meaning that at the end of each sprint, a new version of the software is available with additional features or improvements.

Adaptability: Agile methodologies emphasize adaptability and the ability to respond to changing requirements. If new priorities or insights emerge, adjustments can be made in subsequent sprints. Sprints allow development teams to iteratively deliver value to customers and stakeholders in a controlled and predictable manner. By breaking down the work into manageable chunks and continuously seeking feedback, Agile teams can enhance collaboration, reduce risk, and improve the overall quality of the software being developed.

Question 6 Explain Product backlog and sprint back log– 5 Marks

Ans:

The Product Backlog is a prioritized list of all desired work on the project. It serves as the single source of requirements for any changes to be made to the product. Its a dynamic document that evolves as more is learned about the product and the customer needs change.

Ownership: The Product Backlog is owned and managed by the Product Owner, who is responsible for maximizing the value of the product and ensuring that the team is working on the most valuable items.

Content: The items in the Product Backlog can include new features, enhancements, bug fixes, technical work, or any other work that adds value to the product. These items are typically expressed as user stories, epics, or other forms of requirements, and they are prioritized based on their value to the product and the stakeholders.

Planning Horizon: The Product Backlog provides a long-term view of the work to be done on the product, covering multiple releases or iterations. It helps guide the overall direction and strategy for the product, allowing the team to plan and adapt as necessary to meet business objectives.

Sprint Backlog.

The Sprint Backlog is a subset of the Product Backlog that contains the work selected for the current sprint. It represents the plan for how the team will achieve the sprint goal and deliver a potentially shippable product increment by the end of the sprint.

Ownership:

The Sprint Backlog is owned by the Development Team, who are responsible for selecting the items from the Product Backlog, breaking them down into tasks, and completing the work during the sprint

Content: The Sprint Backlog typically includes user stories or other Product Backlog items that have been decomposed into smaller, actionable tasks. These tasks are estimated, assigned to team members, and tracked throughout the sprint to ensure progress towards the sprint goal.

Planning Horizon: The Sprint Backlog provides a short-term view of the work to be done during the current sprint, typically covering a time frame of one to four weeks. It helps the team focus on the immediate priorities and commitments for the sprint, allowing for flexibility and adaptation as they work towards the sprint goal.

Question 7 – What is impediments log? write 2 impediments – 5 Marks

Ans

The impediments log is typically maintained by the Scrum Master, although it can be accessible to the entire team.

It contains a list of all obstacles or impediments that are hindering the team's progress in completing their work.

Each impediment is described briefly, including details such as its impact on the team, who is affected, and any potential solutions or actions needed to resolve it. The log is updated regularly during sprint retrospectives, daily stand-up meetings, or whenever new impediments arise. The Scrum Master is responsible for facilitating discussions around impediments, prioritizing them based on their severity and impact, and working with the team to find solutions.

Impediments for Scrum Food Delivery App:

1) Vendor API Integration Delay:

a. Description: The development team is facing delays in integrating the vendor's API into the app, which is essential for real-time menu updates and order processing.

b. Impact: Without the API integration, the app's functionality is limited, affecting user experience and potentially leading to customer dissatisfaction.

c. Resolution: The Scrum Master collaborates with the vendor and development team to expedite the API integration process, explores alternative solutions, or adjusts the sprint backlog to focus on other high-priority tasks while awaiting the integration.

2. Network Connectivity Issues for Delivery Drivers:

a. Description: Delivery drivers using the app report intermittent network connectivity issues, causing delays in receiving orders and updating order status.

b. Impact: The network connectivity issues disrupt the smooth operation of the delivery process, leading to delays in order deliveries and potentially impacting customer satisfaction.

c. Resolution: The development team investigates the root cause of the network connectivity issues, works on optimizing the app's network communication protocols, and implements offline functionality to allow delivery drivers to continue working even in low or no network connectivity areas

| Impediments | Description | Impact | Resolution |
| --- | --- | --- | --- |
| Delivery Partner shortage in a specific Region | There is a shortage of delivery partners in a specific region, resulting in delays in order deliveries. | Increased delivery times and potential loss of customers in an affected region. | Exploring hiring incentives or bonuses for delivery partners in a region. Collaborate with local delivery companies or expand recruitment efforts to address the shortage. |
| Technical issues causing intermittent order processing failure | A technical issue is causing intermittent failure in order processing leading to incomplete and failed orders. | Incomplete or failed order processing, customer dissatisfaction, and potential loss of trust. | Conduct a thorough investigation to identify the root cause of the technical issue. Implement fixes or workarounds to stabilize the order processing system. Communicate transparency with customers about the issue and expected resolution timeframe. |

Question 8 – Explain Velocity of the Team – 1 Marks

VELOCITY OF THE TEAM:

Velocity refers to the measure of the amount of work a development team can complete during a sprint. The calculation of velocity is performed by the development team itself, as they are responsible for estimating the effort required to complete each user story or backlog item.

Story point estimation:

Story point estimation is a technique used in agile software development to estimate the effort required for a specific task or user story. It’s a relative measure of complexity rather than a fixed time unit. Team members assign story points based on their understanding of the work involved, considering factors like complexity, effort, and uncertainty. The actual time a story point represents can vary from team to team. For some, it might equate to hours, while for others, it might represent days. It’s important to establish a consistent baseline within the team so that story point estimates can be used effectively for planning and prioritization.

Tracking completed work:

Tracking completed work in Agile development typically involves calculating the total story points completed by the team over a specific time frame, usually a sprint or iteration. Here’s how you can calculate completed work:

- Identify Completed Stories:
At the end of the sprint or iteration, review the user stories or tasks that were completed and accepted as done.

- Sum Story Points:
Add up the story points assigned to all the completed user stories. Exclude any story points that were not fully finished or accepted during the sprint.

- Calculate Total Completed Work:
The sum of story points completed represents the total completed work for that sprint. This completed work can be used to calculate the team’s velocity for that specific sprint, as mentioned in the previous response. It provides insights into the team’s capacity and helps with future sprint planning and estimation.

Summing story points:

Summing story points involves adding up the numerical values assigned to individual user stories or tasks during the estimation process in Agile development. Story points are used to represent the effort, complexity, and size of a piece of work relative to other items on the backlog. Here’s how you can sum story points:

- List Completed User Stories:
Gather a list of user stories or tasks that have been completed during a specific sprint or iteration.

- Identify Story Point Values:
Each user story or task should have a story point value assigned to it during the estimation process. These values are usually relative, such as 1, 2, 3, 5, 8, 13, etc., representing increasing levels of complexity or effort.

- Add Up Story Point Values:
Sum up the story point values for all the completed user stories or tasks. For example, if you completed user stories with story point values of 3, 5, and 8, the sum would be 16. The sum of story points provides a quantitative measure of the work completed by the team during a sprint. This sum is often used to calculate the team’s velocity, which helps in future sprint planning and estimation.

Average velocity:

Average velocity in Agile development refers to the average amount of work, measured in story points, that a team completes during a series of sprints or iterations. It’s a key metric used for planning and estimating future work. Here’s how to calculate average velocity:

- Select a Time Frame:
Choose a specific number of past sprints or iterations for which you want to calculate average velocity. For example, you might choose the last 5 sprints.

- Sum Completed Story Points:
Add up the total story points completed by the team in each of the selected sprints. This will give you the total completed work for the chosen time frame.

- Calculate Average:
Divide the total completed story points by the number of sprints or iterations you selected. This will give you the average velocity for that period.

The average velocity can serve as a guideline for future sprint planning. It helps the team estimate how much work they can commit to in upcoming iterations based on their past performance.

Question 9 :Draw Sprint Burn Charts n Product Burn Down Charts– 3 Marks

Breakdown of the Chart

To make the information as clear as possible, here is a detailed description of what the chart shows. This is a Sprint Burndown Chart for "Consent related tasks".

- Y-Axis (Vertical): Represents STORY POINTS, which is a measure of the effort required to complete tasks. The scale runs from 0 to 25.

- X-Axis (Horizontal): Represents TIME, spanning from November 28 to December 4.

Key Elements:

- Guideline (Grey Diagonal Line): This shows the ideal rate at which work should be completed to finish everything by the end of the sprint. It's a straight line from the starting total of story points to zero on the last day.

- Remaining Values (Red Line): This shows the actual amount of work (in story points) remaining at any given time. The goal is for this red line to reach zero by the end of the sprint.

- Non-Working Days (Shaded Grey Areas): The periods for November 30 and December 1 are shaded, indicating they are likely weekends or holidays where no work was planned.

Interpreting the Team's Progress (Red Line):

- Start (Nov 28): The sprint started with 24 story points.

- Nov 28 - Nov 29: The team completed work, and the remaining story points dropped in steps from 24 to about 15.5. The team was slightly behind the ideal guideline initially.

- Nov 30: The line drops sharply to 9 story points. This is interesting as it's marked as a non-working day, suggesting some work was completed over the weekend.

- Dec 1 - Dec 3: The line continues to drop, first to 5 points, then to 2, and finally to 0.

- Finish (Dec 3): The team successfully completed all the work (reached 0 story points) on December 3, ahead of the sprint's end date of December 4.

Product Burnout Chart

The Product Burn-Down Chart shows remaining work (complexity points) versus time (sprints).

It helps track progress toward completing all product backlog items.

The line should trend downward, ideally reaching zero by the last sprint.

It visually indicates whether the team is on schedule, ahead, or behind the planned progress.

Used in Agile/Scrum to ensure transparency and predictability of project completion.

Question 10 – Explain about Product Grooming – 2 Marks

Product Grooming, also known as backlog grooming or refinement, is an essential activity in Agile methodologies like Scrum.

It involves preparing the product backlog for upcoming sprints by refining and prioritizing items to ensure they are ready for implementation.

- Purpose: The main goal of product grooming is to ensure that the product backlog contains well-defined, prioritized, and estimable items that are ready for implementation in future sprints. It helps the product owner and development team maintain a clear understanding of the product vision, user needs, and upcoming work, facilitating effective planning and execution.

- Activities Involved:

  - Reviewing and Prioritizing: The product owner reviews the items in the product backlog, considering feedback from stakeholders, market changes, and business priorities. Items are prioritized based on their value to the product and customers.

  - Refining User Stories: User stories or backlog items are refined to ensure they are clear, concise, and actionable. This may involve breaking down large items into smaller ones, adding acceptance criteria, and clarifying requirements.

  - Estimation: The development team estimates the effort required to complete each backlog item, using techniques like story points or hours. This helps in capacity planning and sprint commitment.

  - Removing or Archiving Obsolete Items: Outdated or unnecessary items are removed from the backlog to maintain its relevance and focus on the most valuable work.

- Participants:

  - Product Owner: The product owner leads the grooming sessions, providing guidance on priorities and requirements.

  - Development Team: Developers, testers, and other team members actively participate in grooming sessions to provide input, ask questions, and clarify requirements.

  - Stakeholders: Relevant stakeholders may be invited to grooming sessions to provide feedback, share insights, and ensure alignment with business goals.

  - Frequency: Product grooming is an ongoing activity that occurs throughout the product development lifecycle, typically before the start of each sprint. The frequency of grooming sessions may vary depending on the project's needs, but they are often scheduled regularly to ensure backlog items remain up-to-date and actionable.

- Benefits:

  - Improved Planning: Well-groomed backlog items help in accurate sprint planning, resource allocation, and prioritization of work.

  - Reduced Waste: By refining and prioritizing backlog items in advance, the team can avoid wasted time and effort on unclear or low-priority tasks.

  - Enhanced Collaboration: Grooming sessions foster collaboration between the product owner and development team, leading to shared understanding and ownership of the product backlog.

  - Increased Flexibility & Better Predictability

  - In summary, product grooming is a continuous process that ensures the product backlog is a living, organized, and valuable asset, enabling effective sprint planning and successful product development.

Question 11: Explain the roles of Scrum Master and Product Owner

Scrum Master:

Servant Leader: The Scrum Master serves the Scrum Team and the organization by facilitating Scrum events, removing impediments, and coaching the team on Agile principles and practices.

- Process Facilitator: They ensure that the Scrum framework is understood and enacted properly. This includes organizing Scrum events (such as Sprint Planning, Daily Standups, Sprint Review, and Sprint Retrospective) and helping the team follow Scrum practices.

- Obstacle Remover: The Scrum Master helps remove any impediments hindering the team's progress. This might involve addressing issues within the team, coordinating with other teams or stakeholders, or escalating issues to higher levels of management for resolution.

- Protective Shield: They shield the team from external interference, allowing the team to focus on their work during the Sprint.

- Coach: The Scrum Master coaches the team on Agile principles, practices, and values. They help the team continuously improve by fostering a culture of learning and experimentation.

Product Owner:

- Visionary: The Product Owner is responsible for creating and communicating the vision for the product. They have a deep understanding of the market, customer needs, and business goals.

- Stakeholder Liaison: They represent the stakeholders and their interests to the Scrum Team. This involves gathering feedback, managing expectations, and prioritizing requirements based on business value.

- Product Backlog Management: The Product Owner creates and prioritizes the Product Backlog, which is a prioritized list of all the work that needs to be done on the project. They ensure that the Product Backlog is visible, transparent, and understood by everyone involved.

- Requirement Refinement: They work with the Scrum Team to refine the requirements in the Product Backlog, ensuring that they are clear, feasible, and well-understood by the team.

- Decision Maker: The Product Owner makes decisions about what features should be included in each Sprint and what order they should be developed in. They have the authority to accept or reject work done by the team based on whether it meets the acceptance criteria and delivers value to the customer.

Question 12 – Explain all Meetings Conducted in Scrum Project

Ans:

Sprint Planning:

This meeting kicks off each sprint, which is a time-boxed iteration of work, usually spanning 2-4 weeks. During this meeting, the Scrum team, including the Product Owner, Scrum Master, and Development Team, collaborates to determine which backlog items (user stories, features, etc.) will be worked on in the upcoming sprint. The team also breaks down these items into tasks and estimates the effort required.

Daily Stand-up (Daily Scrum): Held daily during the sprint, this short meeting aims to facilitate quick and focused communication among team members. Each team member answers three key questions:

What did I accomplish since the last stand-up?

What will I work on until the next stand-up?

Are there any obstacles or impediments in my way? This meeting helps keep everyone aligned and informed about progress and challenges.

Sprint Review:

At the end of each sprint, the team holds a review meeting to showcase the work completed during the sprint to stakeholders, customers, and the Product Owner. The team demonstrates the potentially shippable product increment and gathers feedback. Based on this feedback, the Product Owner can update the backlog.

Sprint Retrospective: Also held at the end of each sprint, the retrospective is a dedicated time for the team to reflect on their processes and practices. The team discusses what went well, what could be improved, and any potential changes they would like to make in the next sprint to enhance their efficiency and effectiveness.

Backlog Refinement (Grooming): While not officially part of the Scrum events, backlog refinement is an important ongoing activity. During these sessions, the team and the Product Owner review and refine backlog items, adding details, clarifications, and estimates to make them ready for inclusion in future sprints.

Product Backlog Refinement: This meeting focuses on refining the product backlog items. The team and the Product Owner discuss and clarify requirements, priorities, and any changes needed in the backlog items. This ensures that the backlog is well-prepared for upcoming sprints.

Release planning: This meeting occurs at the start of the project or major release and involves the product owner, development team, and stakeholders. It aims to discuss and plan the high-level scope, timeline, and goals for the project.

Ad hoc meetings: These meetings may be scheduled as needed to address specific topics or issues, such as resolving impediments, discussing technical challenges, or conducting additional planning or collaboration sessions.

Question No 13)- Explain Sprint Size and Scrum Size Sprint Size:

Ans:

In Scrum, a "sprint" is a time-boxed iteration during which the development Teamwork to deliver a potentially shippable product increment. The length of a sprint is referred to as the "sprint duration" and is usually fixed throughout the project. Common sprint durations are 1 to 4 weeks. The choice of sprint duration depends on factors such as team velocity, project complexity, and business needs. A shorter sprint encourages more frequent opportunities for feedback and adaptation, while a longer sprint provides more time for development.

Scrum Team Size:

The Scrum team size refers to the number of individuals who collectively contribute to the product's development. A Scrum team consists of three key roles:

The Product Owner, the Scrum Master, and the Development Team. The Development Team, in particular, is responsible for creating the product increment. Scrum recommends that the Development Team size be kept small, typically between 3 to 9 members, to facilitate effective communication, collaboration, and decision-making.

Question 14: Explain DOR and DOD

Ans:

Definition of Ready (DOR):

The Definition of Ready outlines the criteria that a product backlog item (user story, feature, task, etc.) should meet before it is considered ready to be taken into a sprint for development. The DOR ensures that the item is well-defined, understood, and prepared for efficient development. The specific criteria in the DOR can vary from team to team, but commonly include elements such as:

- Clear description and acceptance criteria: The item's requirements are clearly stated, and the conditions for its successful completion are well-defined.

- Dependencies identified: Any dependencies on external factors, teams, or resources are identified and addressed.

- Estimable: The team has enough information to provide a reasonable estimate of the effort required.

- Testable: It's possible to determine whether the item has been successfully implemented through testing.

- Minimal ambiguity: The item's details are clear, and any uncertainties are resolved

Definition of Done (DOD):

The Definition of Done outlines the criteria that must be met for a product increment or backlog item to be considered complete and potentially shippable. The DOD ensures that the team maintains a consistent level of quality and completeness in their work. The specific criteria in the DOD can vary based on the team's standards, the nature of the project, and the industry, but commonly include elements such as:

Code complete: All development work is finished, including coding, testing, and integration.

Peer-reviewed: Code has been reviewed by other team members for quality and adherence to coding standards.

• Automated tests passed: Automated tests (unit tests, integration tests, etc.) have been successfully executed and passed.

• Functional requirements met: The item meets all specified acceptance criteria and functional requirements.

Question 15: Explain Prioritization Techniques and MVP – 3 Marks

Ans:

Prioritization techniques are methods used to determine the order in which tasks, features, or items should be addressed in a project. These techniques help teams allocate resources effectively and focus on delivering the most valuable work first. Some common prioritization techniques include:

MOSCOW: This technique categorizes items into Must have, Should have, Could have, and Won't have categories. It helps clarify essential features from those that are optional or lower priority.

Weighted Shortest Job First (WSJF): WSJF assigns a priority score to each item based on factors like business value, time sensitivity, and risk. Items with higher scores are considered more important to work on.

Kano Model: This model categorizes features into Basic Needs, Performance Needs, and Delighters. It helps prioritize based on how features impact user satisfaction.

Value vs. Effort Music: Items are plotted on a matrix based on their potential value and effort required. This helps identify quick wins and high-value tasks.

Relative Prioritization: Teams compare items pairwise to determine which is more important. This helps create a relative ranking of items.

Buy a Feature: Stakeholders are given a budget to 'buy' features, which helps prioritize features based on how much value they see in them.

Minimum Viable Product (MVP): An MVP is the smallest version of a product that includes just enough features to provide value to early adopters and gather feedback. The MVP approach helps validate assumptions, learn from users, and iteratively build upon a product's foundation.

It involves:

• Core Functionality: An MVP focuses on delivering the core functionalities that address the primary needs or pain points of the target users.

• Minimal Features: The MVP omits non-essential features to avoid unnecessary complexity and expedite development.

• Testing Hypotheses: The MVP tests assumptions and hypotheses about user behaviour, market demand, and product viability.

•Iterative Development: Based on user feedback, the product is refined and expanded in subsequent iterations, gradually adding more features.

Question 16: Difference between Business Analyst n Product Owner

| Aspects | Business Analyst | Product Owner |
| --- | --- | --- |
| Focus | Business processes and requirements analysis | Product vision, strategy, and prioritization |
| Responsibility | - Analysing business needs and requirements - Documenting requirements - Facilitating communication between stakeholders - Supporting solution design | - Defining and communicating product vision - Prioritizing features and requirements - Managing the product backlog - Making decisions about what to build next |
| Stakeholder Interaction | Interacts with various stakeholders including users, subject matter experts, and development teams | Interacts with stakeholders including customers, users, development teams, and other business units |
| Decision Making | Provides input into decision-making processes regarding business solutions | Makes decisions about the product direction, features, and priorities |
| Team Collaboration | Collaborates closely with development teams to ensure requirements are understood and implemented correctly | Works closely with development teams to ensure that the product backlog is clear, prioritized, and actionable |
| Metrics and Success | May measure success based on project efficiency, cost savings, or process improvements | Measures success based on the value delivered to customers, user satisfaction, and product performance in the market |
| Ownership | Typically does not have ownership over the product itself but over the analysis and requirements documentation | Has ownership over the product vision, strategy, and backlog management |
| Role in Agile | Can play a role in Agile projects as a liaison between business stakeholders and development teams, ensuring that requirements are well-understood and implemented effectively | Plays a key role in Agile projects as the primary person responsible for defining and prioritizing the product backlog, ensuring that the development team delivers value to the customer |

Question 17:

Prepare a sample Resume of 3yrs exp Product Owner – 3 Marks

Ans:

Aditya [Last Name] 📍 Hyderabad, India 📧 aditya.email@example.com | 📞 +91-XXXXXXXXXX 🔗 LinkedIn: linkedin.com/in/aditya-profile (if available)

🧭 Objective

Dynamic and results-driven Product Owner with 3+ years of experience in Agile software development environments. Proven ability to lead cross-functional teams and deliver high-quality products aligned with customer needs and business goals. Seeking to leverage expertise in a challenging Product Owner role.

💼 Professional Experience

Product Owner Accenture, Hyderabad June 2022 – Present

- Defined and communicated product vision, strategy, and roadmap to stakeholders and development teams.

- Collaborated with stakeholders to gather and prioritize requirements aligned with business goals.

- Managed product backlog and prioritized user stories for sprint execution.

- Led sprint planning meetings and ensured successful delivery of sprint goals.

- Supervised UAT and incorporated feedback into product iterations.

- Coordinated with design and marketing teams for cohesive product experiences.

- Monitored KPIs and tracked metrics to evaluate product success.

Junior Product Owner Amazon, Hyderabad May 2019 – May 2022

- Assisted in defining product vision and roadmap.

- Collaborated with stakeholders to gather and refine user stories.

- Participated in sprint planning and backlog grooming sessions.

- Supported backlog prioritization and feature enhancement tracking.

- Conducted UAT and managed defect tracking to ensure product quality.

🎓 Education

Bachelor of Business Administration (BBA) Osmania University, Hyderabad Graduated: May 2019

🛠 Skills

- Agile Methodologies (Scrum, Kanban)

- Product Backlog Management

- Sprint Planning & Execution

- User Acceptance Testing (UAT)

- Stakeholder Communication

- Roadmap Development

- Cross-functional Team Collaboration

- KPI Tracking & Analysis

🌐 Languages

- English (Proficient)

- Hindi (Proficient)

- Telugu (Proficient)