Online Agriculture Products Store

Mr. Henry, after being successful as a businessman and has become one of the wealthiest persons in the city. Now, Mr. Henry wants to help others to fulfil their dreams. One day, Mr. Henry went to meet his childhood friends Peter, Kevin and Ben. They live in a remote village and do farming. Mr. Henry asked his friends if they are facing any difficulties in their day-to-day work. Peter told Mr. Henry that he is facing difficulties in procuring fertilizers which are very important for farm. Kevin said that he is also facing the same problem in-case of buying seeds for farming certain crops. Ben raised his concern on lack of pesticides which could help in greatly reducing pests in crops. After listening to all his friends’ problems, Mr. Henry thought that this is a crucial problem faced not only by his friends but also by so many other farmers. So, Mr. Henry decided to make an online agriculture product store to facilitate remote area farmers to buy agriculture products. Through this Online Web / mobile Application, Farmers and Companies (Fertilizers, seeds and pesticides manufacturing Companies) can communicate directly with each other. The main purpose to build this online store is to facilitate farmers to buy seeds, pesticides, and fertilizers from anywhere through internet connectivity. Since new users are involved, Application should be user friendly. This new application should be able to accept the product (fertilizers, seeds, pesticides) details from the manufacturers and should be able to display them to the Farmers. Farmers will browse through these products and select the products what they need and request to buy them and deliver them to farmers location. Mr. Henry has given this project through his Company SOONY. In SOONY Company, Mr Pandu is Financial Head and Mr Dooku is Project Coordinator. Mr. Henry, Mr Pandu, and Mr Dooku formed one Committee and gave this project to APT IT SOLUTIONS company for Budget 2 Crores INR and 18 months Duration under CSR initiative. Peter, Kevin and Ben are helping the Committee and can be considered as Stakeholders share requirements for the Project.

Mr Karthik is the Delivery Head in APT IT SOLUTIONS company and he reached out to Mr Henry through his connects and bagged this project. APT IT SOLUTIONS company have Talent pool Available for this Project. Mr Vandanam is project Manager, Ms. Juhi is Senior Java Developer, Mr Teyson, Ms Lucie, Mr Tucker, Mr Bravo are Java Developers. Network Admin is Mr Mike and DB Admin is John. Mr Jason and Ms Alekya are the Tester. And you joined this team as a BA.

Decode the case study:

Project Idea: To build a user-friendly online platform (Web & Mobile Application) that enables farmers in remote areas to purchase fertilizers, seeds, and pesticides directly from manufacturers, thereby overcoming the supply chain challenges they face locally.

- It is a CSR initiative by Mr. Henry through his company SOONY, implemented by APT IT SOLUTIONS.

- The app bridges the gap between manufacturers and rural farmers, enhancing accessibility, affordability, and digital empowerment.

Current needs:

- Farmers in remote villages are unable to access essential agricultural products due to:

- Poor distribution channels

- Lack of nearby vendors

- Price markups by intermediaries

- There's a digital gap for rural users, hence the need for:

- A simple, intuitive app

- Ability to browse and order products easily

- Delivery to doorstep

- Enable direct communication between product manufacturers and farmers to:

- Reduce dependency on middlemen

- Build long-term, transparent relationships

- Encourage fair pricing

Overview of the project: The project name is "Online Agriculture Products Store" CSR initiative spearheaded by Mr. Henry, a successful businessman with a vision to give back to society. The project is sponsored by SOONY and implemented by APT IT SOLUTIONS with a budget allocation of ₹2 Crores INR and a development timeline of 18 months. Aimed to uplifting farmers in remote areas as well as manufacturers of agricultural inputs such as seeds, fertilizers, and pesticides, the solution will be delivered through both web and mobile applications. Key modules of the platform include Farmer Registration, Company Registration, Product Upload, Product Browsing, Ordering, Communication, and Delivery Management. This CSR-driven initiative is designed to enhance the livelihoods of rural farmers by leveraging technology to connect them directly with suppliers and streamline the agricultural supply chain.

Current problems:

Farmers in remote areas face significant challenges in accessing essential agricultural inputs. For instance, Peter struggles to procure fertilizers, Kevin finds it difficult to buy quality seeds, and Ben lacks access to pesticides. These individual experiences reflect broader issues such as the unavailability of critical farm inputs in local markets, leading to increased travel costs and time just to reach the nearest agricultural supply store. Moreover, farmers are often exposed to counterfeit or overpriced products and have limited awareness of available options, affecting their productivity and profitability.

On the other hand, manufacturers of agricultural products also face notable challenges. Their reach to rural markets is restricted, as they heavily rely on intermediaries and local distributors, which complicates the supply chain. Furthermore, they lack direct access to customers, making it difficult to gather feedback or insights from the end-users—farmers—thus limiting opportunities for product improvement and market growth.

Know the Team: (Stakeholder Map)

| Name | Role | Organization | Responsibility |
| --- | --- | --- | --- |
| Mr. Henry | Project Sponsor / Visionary | SOONY | CSR Initiative Owner |
| Mr. Pandu | Financial Head | SOONY | Budget Oversight |
| Mr. Dooku | Project Coordinator | SOONY | Project Governance |
| Peter, Kevin, Ben | Farmers / End-User Advocates | Independent / Remote Villages | Share Real Needs and Validate Features |

Implementation Team (APT IT SOLUTIONS):

| Name | Role | Responsibility |
| --- | --- | --- |
| Mr. Karthik | Delivery Head | Client Liaison & Oversight |
| Mr. Vandanam | Project Manager | Project Planning & Execution |
| Ms. Juhi | Senior Java Developer | Architecture & Code Review |
| Mr. Teyson | Java Developer | Backend Development |
| Ms. Lucie | Java Developer | Frontend Integration |
| Mr. Bravo | Java Developer | Business Logic Implementation |
| Mr. Tucker | Java Developer | Feature Development |
| Mr. Mike | Network Admin | Infrastructure Setup |
| Mr. John | DB Admin | Database Design and Management |
| Mr. Jason | Tester | Functional Testing |
| Ms. Alekya | Tester | Usability and UAT Testing |
| Myself (BA) | Business Analyst | Requirement Gathering, BRD, User Stories, Process Flow, Liaison between SOONY and Dev Team |

Question 1 – BPM: Prepare Business Process Model.

Identify Business Process Model for Online Agriculture Store – (Goal, Inputs, Resources, Outputs,

Activities, Value created to the end Customer)

Goal: To enable remote farmers to directly purchase agricultural inputs (seeds, fertilizers, pesticides) from registered manufacturers using a user-friendly web/mobile platform, improving accessibility, affordability, and supply chain efficiency.

Inputs: The project inputs include several critical components to ensure its success.

- Farmer needs: Demand for quality seeds, fertilizers, and pesticides.

- Manufacturer Product Data: Product listings with descriptions, price, availability.

- Internet Connectivity: Farmers must have basic access to the internet.

- User Requirements: UI/UX considerations for rural and semi-literate users.

- Funding & Timeline: CSR Budget (₹2 Crores INR), Timeline (18 Months).

- Government/CSR Policies: CSR compliance, rural development schemes.

Resources:

- Human Resources: BA, PM, Developers, Testers, Admins, Farmers, Committee

- Technical Resources: Development Tools (Java, SQL), Hosting Infrastructure, Internet

- Stakeholder Support: Mr. Henry (CSR sponsor), Farmer group (Peter, Kevin, Ben)

- Knowledge Assets: Product info from manufacturers, usability data from farmers

- Financial Resources: CSR funding from SOONY (₹2 Crores INR)

Outputs:

- Functional Platform: Online store accessible via web/mobile with full e-commerce capabilities tailored for Agri-products.

- Product Listings: Real-time product availability and prices from manufacturers.

- Order Management System: for farmers to order, track, and receive deliveries.

- Communication Channel: Chat/contact interface between farmers and vendors.

- Delivery Logistics: Order fulfilment mechanism integrated or manual.

- Impact Metrics: Usage statistics, order volume, region-wise access reports.

Activities:

- Requirement Gathering: Interviews with farmers (Peter, Kevin, Ben), manufacturers, stakeholders (Mr. Henry, Mr. Dooku, Mr. Pandu).

- Planning & Design: Define scope, draft BRD, user personas, UX wireframes.

- Development: Build modules: registration, product upload, catalog, cart, order flow.

- Testing: Functional, usability, performance, UAT with real farmers.

- Deployment: Hosting, infrastructure setup, initial content load.

- Training & Support: Farmer onboarding support, help center, feedback system.

- Monitoring & Evaluation: Regular reviews of platform adoption, order trends, issue resolution.

Value: Value created to end customer (Farmers).

Accessibility: Easy access to essential agri-inputs from anywhere, Farmers gain digital confidence and buying power.

Affordability: Direct purchase = reduced intermediary costs.

Convenience: Shop from home; no need to travel to town markets.

Question 2 – SWOT

Mr Karthik is doing SWOT analysis before he accepts this project. What Aspects he Should consider as Strengths, as Weaknesses, as Opportunity and as Threats.

Below is the SWOT analysis for this Online Agriculture Products Store project.

Strengths:

- Strong CSR Backing: Sponsored by Mr. Henry and SOONY under a CSR initiative with ₹2 Crores budget, which ensures social goodwill and funding stability.

- Clearly Defined Stakeholders: Farmers (Peter, Kevin, Ben) are already involved for elicitation, ensuring early-stage validation of needs.

- Dedicated & Skilled Team: Availability of full project team including experienced Java developers, testers, admins, and a capable BA.

- Delivery Ownership: Mr. Karthik has direct connects with the sponsor, which gives leverage in communication and influence.

- Longer Timeline (18 months): Allows room for quality planning, execution, and rollout with minimal rush.

- High Social Impact Project: Increases company brand reputation and opens up avenues in public and NGO sectors.

Weaknesses:

- User base is technologically challenged: End users (rural farmers) may have low tech literacy — UI/UX must be exceptionally intuitive.

- Limited domain experience in AgriTech: If consulting company lacks prior experience in agricultural applications, domain-specific challenges may be overlooked.

- Potential for scope creep: Stakeholders (like the farmers or sponsors) may keep adding new features based on evolving needs.

- Dependency on internet access: Rural internet penetration is still uneven; adoption risks if app doesn’t work offline or with weak connectivity.

- Integration with logistics: Delivery to remote locations may not be easily manageable without third-party tie-ups.

- CSR Nature may delay decisions: Non-profit projects often face slower decision-making and lesser urgency from stakeholders.

Opportunities:

- Entry into AgriTech sector: Successful delivery creates a strong portfolio in a growing rural digital market.

- Scalability for future features: Future versions can include warehousing, crop advisory, weather alerts, etc.

- Government collaboration: Can attract government contracts, subsidies, or partnerships under rural development schemes like PM-KISAN or Digital India.

- Public relations & brand image: Delivering a successful CSR project raises company’s reputation and visibility.

- Upselling technical services: Scope to upsell maintenance, cloud hosting, analytics, or support services post-launch.

- Market expansion: Platform could later be monetized for other states or exported to similar geographies (Bangladesh, Nepal, Africa).

Threats:

- Adoption resistance by farmers: Low digital literacy or trust in digital platforms may hinder farmer onboarding.

- Competition from existing platforms: Agri marketplaces like DeHaat, AgroStar, BigHaat, etc., already operate in this space.

- Logistics disruptions: Inconsistent delivery partners or transportation issues in remote areas can affect user trust.

- Political or policy changes: Government subsidy policies, agri bans, or e-commerce regulations may impact operations.

- Sustainability of CSR funding: If CSR vision changes or SOONY pulls out support, there may be a lack of follow-up funding.

- Cybersecurity risk: Handling user data, orders, and transactions makes the system vulnerable to hacking or data breaches if not well-secured.

Strengths: Skilled team, clear goals, stable funding, CSR visibility.

Weaknesses: Agri domain gap, rural tech barriers, possible scope creep.

Opportunities: Entry into AgriTech, gov't tie-ups, future product scaling.

Threats: User adoption, logistics hurdles, existing competition, regulatory changes.

Question 3 – Feasibility study

Mr Karthik is trying to do feasibility study on doing this project in Technology (Java), Please help him with points (HW SW Trained Resources Budget Time frame) to consider in feasibility Study.

Feasibility Study focusing on the technology aspect (Java-based solution) for the Online Agriculture Products Store project.

Project: Online Agriculture Products Store

Client: SOONY (CSR Initiative by Mr. Henry)

Delivery Partner: APT IT SOLUTIONS

Delivery Head: Mr. Karthik

Focus: Technology Feasibility (Java)

Scope: Web and Mobile Application for Farmers and Manufacturers

Development Approach: Waterfall Model

Budget: ₹2 Crores INR

Timeline: 18 Months

Hardware Requirements (Infrastructure Feasibility):

- Development Machines: 5–6 High-performance laptops/desktops (16GB RAM, SSD, i5/i7, etc.) For BA, developers, testers.

- Test Devices: Smartphones (Android low-mid range), tablets, for mobile app testing in rural conditions.

- Staging & Production Servers: Cloud servers (AWS/DigitalOcean) or on-prem setup. Waterfall needs early provisioning for system design phase.

- Networking: Secure internet connectivity, VPNs for remote access during testing and support. Needed from design to deployment.

- Backup and Storage: Cloud backup tools, storage vaults for code repos, product images, UAT data.

- Optional On-Prem Hardware: If client mandates local hosting (unlikely in CSR), physical servers, routers, firewalls.

- Feasible within budget; hardware scale is manageable.

Software Requirements (Java Technology Stack Feasibility):

- Frontend (Web): HTML5, CSS3, JavaScript, React.js or Angular (optional but useful for UI responsiveness farmer interface).

- Frontend (Mobile): Android App (Java/Kotlin); optionally Flutter/React Native for cross-platform, Primary device used by farmers.

- Backend: Java (Spring Boot framework) – suitable for scalable microservices-based architecture.

- Database: MySQL or PostgreSQL (open source, cost-effective, scalable).

- Web Server: Apache Tomcat or Nginx.

- APIs: RESTful APIs (Java-based); for frontend-backend communication and third-party integration.

- Dev Tools: IntelliJ/Eclipse, GitHub, Maven are Development lifecycle tools.

- Testing Tools: JUnit, Selenium, Postman will be used in testing phase.

- Project Management Tools: JIRA, Confluence or equivalent.

- Cloud/Hosting: AWS, Apache Tomcat available throughout dev lifecycle.

- Security: SSL encryption, authentication libraries (OAuth 2.0), input validation frameworks.

- Fully feasible; software stack is open-source or cost-contained.

Trained Resources Availability (People Feasibility):

| Role | Name | Availability | Skills/ Comments |
| --- | --- | --- | --- |
| Delivery Head | Mr. Karthik | Yes | Project governance |
| Project Manager | Mr. Vandanam | Yes | Manages Waterfall Stage |
| Senior Developer | Ms. Juhi | Yes | Architecture & Tech lead |
| Developers | Teyson, Lucie, Tucker, Bravo | Yes | Backend, API, business logic |
| BA | Sham Kailas | Yes | BA documentation, process modelling |
| Testers | Jason, Alekya | Yes | Manuel, UAT, regression |
| DB Admin | John | Yes | Database design & Optimization |
| Network Admin | Mike | Yes | Infra setup & monitoring |
| UI/UX (Gap) | To be staffed/ outsourced | Needed | Low literacy UI design expertise preferable |
| Agri domain SME | To be consulted | Needed | Farmer specific flows and product validation. (Validate product names, terminologies, image, etc. |

Feasibility: Core tech team available, may need UI/UX designers and domain experts for field validation and localized design.

Budget Feasibility (Within ₹2 Crores INR):

| Cost Head | Estimated Allocation (INR) |
| --- | --- |
| Development Team Salaries | ₹90 Lakhs (across 18 months) |
| Infrastructure & Hosting | ₹20 Lakhs |
| Testing & QA | ₹10 Lakhs |
| UI/UX Design + Field Testing | ₹10 Lakhs |
| Training & Farmer Onboarding | ₹10 Lakhs |
| Travel, Reviews & Contingency | ₹15 Lakhs |
| Project Management & Tools | ₹10 Lakhs |
| Documentation & Support | ₹5 Lakhs |
| Total | ₹1.70 Crores |

Buffer (15%) = ₹30 Lakhs for scope changes or enhancements.

Fully feasible under ₹2 Cr budget, including 15% risk buffer.

Time Frame Feasibility (Waterfall Model – 18 Months):

| Phase | Duration |
| --- | --- |
| Requirements Analysis | 2 Months |
| System Design (UI, DB, Arch) | 2 Months |
| Development | 6 Months |
| Testing & QA | 3 Months |
| UAT & Feedback | 2 Months |
| Deployment & Support Setup | 1 Month |
| Training, Documentation & Handover | 2 Months |
| Total | 18 Months |

Feasibility: fits well into waterfall’s sequential planning and long-term delivery nature.

Final Summary: Technology Feasibility (Waterfall + Java)

| Factor | Status | Key Remarks |
| --- | --- | --- |
| Hardware | Yes | Cloud + Dev machines manageable |
| Software | Yes | Open-source Java stack = budget friendly |
| Resources | Yes | Skilled team, minor gaps in UI/UX & domain |
| Budget | Yes | ₹2 Cr is sufficient with 15% buffer |
| Time Frame | Yes | 18 months suits waterfall phases |

Question 4 – Gap Analysis:

Mr Karthik must submit Gap Analysis to Mr Henry to convince to initiate this project. What points (compare AS-IS existing process with TO-BE future Process) to showcase in the GAP Analysis

GAP Analysis Report:

Project: Online Agriculture Products Store

Submitted by: Mr. Karthik (Delivery Head, APT IT SOLUTIONS)

Submitted to: Mr. Henry (Sponsor, SOONY – CSR Initiative)

Objective: Justify the need for initiating the project by highlighting operational and technological gaps between the current state and the proposed solution.

Comparison Table: AS-IS vs TO-BE Process:

| Area | AS-IS (Current State) | TO-BE (Future State via Online Store) | GAP Identified |
| --- | --- | --- | --- |
| Product Procurement | Farmers travel long distances to local Agri shops or wait for seasonal vans. | Farmers order online from manufacturers via app. | Lack of accessibility to inputs; manual and time-consuming. |
| Product Availability | Limited choice and stock; often depends on local vendors’ inventory. | Wide range of products from multiple brands online; updated stock. | Restricted access to quality options and brands. |
| Pricing Transparency | Price is not standardized; includes middlemen commissions. | Direct pricing from manufacturer shown on app. | No pricing visibility, leading to overpaying. |
| Farmer-Vendor Communication | No direct communication; only through distributors or retailers. | In-app messaging or contact options with vendors. | Disconnected supply chain with no feedback loop. |
| Product Information Access | Farmers rely on vendor word-of-mouth or physical labels (often misleading). | Product details, images, usage guidelines shown digitally in local language. | Low awareness, prone to using wrong or fake products. |
| Order Fulfilment | Manual purchase and carrying of goods, often delayed or not possible in emergencies. | Online ordering + doorstep delivery (via local delivery agents or tie-ups). | Physical delivery inefficiency and risk of stock-outs. |
| Customer Support | No post-sale support or feedback mechanism. | In-app support, return policy, FAQ/help center. | Zero after-sales support in AS-IS process. |
| User Experience (UX) | Non-digital, language/literacy barrier in visiting urban shops. | Mobile-friendly UI, vernacular support, easy navigation. | Digital exclusion of rural farmers. |
| Data Collection & Monitoring | No data on product demand, usage, or farmer behaviour. | Analytics dashboard tracks orders, preferences, issues. | No insights for future decision-making or scalability. |
| CSR Visibility for SOONY | No structured way to measure CSR effectiveness. | Impact dashboards: # of farmers helped, orders placed, areas covered. | Lack of impact metrics in current support structure. |

Business Justification for Project Initiation:

- This GAP analysis clearly demonstrates urgent inefficiencies in the current agricultural input supply process.

- The proposed digital store directly addresses each gap with tangible, measurable solutions.

- The project will create real, long-term value for rural farmers, manufacturers, and SOONY’s CSR goals.

- A Waterfall model ensures structured delivery, clear scope, and progress checkpoints across 18 months.

Recommendation:

Based on the above analysis, we recommend initiating the Online Agriculture Products Store project to empower remote farmers, reduce supply inefficiencies, and fulfil the CSR vision with scalable and measurable impact.

Question 5 – Risk Analysis:

List down different risk factors that may be involved (BA Risks And process/Project Risks).

Risk Analysis Report:

Project: Online Agriculture Products Store

Delivery Model: Waterfall

Prepared For: Mr. Karthik (Delivery Head, APT IT SOLUTIONS)

Purpose: To identify, categorize, and assess risks associated with the successful delivery of the project.

Business Analyst Risks:

| Risk ID | Risk Category | Risk Description | Impact | Likelihood | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| BA-R1 | Requirement Gaps | Farmers may not be able to clearly articulate needs due to low digital awareness. | High | Medium | Use field interviews, observation, and visual aids for elicitation. |
| BA-R2 | Scope Misunderstanding | Misinterpretation of client (SOONY/Committee) expectations due to vague goals. | High | Medium | Regular stakeholder review meetings; validate scope early. |
| BA-R3 | Overlooking Non-Functional Requirements | Usability, accessibility, language support might be underestimated. | Medium | High | Include NFRs explicitly in the BRD; involve UI/UX expert. |
| BA-R4 | Inadequate Traceability | Difficulty mapping requirements through Waterfall phases. | Medium | Medium | Maintain a live Requirements Traceability Matrix (RTM). |
| BA-R5 | Change Resistance | Stakeholders hesitant to adopt new process/tools. | Medium | Medium | Communicate benefits clearly and document early buy-in. |
| BA-R6 | Communication Delays | With rural stakeholders (farmers) and SOONY committee. | High | Medium | Establish structured weekly communication and escalation matrix. |

Process / Project Risks (Waterfall-Specific):

| Risk ID | Risk Category | Risk Description | Impact | Likelihood | Mitigation Strategy |
| --- | --- | --- | --- | --- | --- |
| PR-R1 | Requirements Freeze Issues | Requirements cannot be changed mid-phase in Waterfall, but new needs may emerge. | High | High | Lock scope after validation; handle changes via formal CR process. |
| PR-R2 | Delayed Approvals | If any approval (design, UAT, budget) is delayed, entire phase is blocked. | High | Medium | Pre-define approval timelines and responsibilities. |
| PR-R3 | Dependency on Internet Infrastructure | Remote farmers may lack consistent access to use the application. | High | Medium | Design offline-friendly UI or SMS-based fallback options. |
| PR-R4 | Usability Failures | Poorly designed UI/UX may make the app unusable for semi-literate users. | High | High | Engage local language UI/UX designers and test with sample users. |
| PR-R5 | Training Gaps | Farmers and support staff may not understand how to use the system. | Medium | High | Prepare visual guides, videos, and conduct training workshops. |
| PR-R6 | Third-party Logistics | Delivery to rural areas may not be reliable or consistent. | High | Medium | Partner with local delivery agents and cooperatives. |
| PR-R7 | Testing Delays | Waterfall testing phase is late-stage; all bugs found here delay deployment. | High | Medium | Strengthen test case coverage and schedule UAT dry runs. |
| PR-R8 | Team Turnover | Long timeline (18 months) may lead to staff attrition. | Medium | Medium | Maintain knowledge base and process documentation. |
| PR-R9 | Budget Overrun | Unexpected costs (UI/UX, field testing, logistics) may push budget. | Medium | Medium | Keep 15% contingency in financial plan. |
| PR-R10 | CSR Vision Drift | Changing expectations from Mr. Henry/SOONY may shift project goals. | Medium | Medium | Lock CSR scope formally and review with sponsor quarterly. |

Risk Categorization Summary:

- BA Risks: Requirement clarity, usability focus, stakeholder communication

- Waterfall Risks: Requirement freeze, delayed approvals, testing bottlenecks

- End-User Risks: Farmer adoption, training, internet access

- External Risks: Delivery logistics, policy changes, vendor dependencies.

Risk Mitigation:

- Maintain a Risk Register with owners and mitigation status.

- Introduce toll-gate reviews after each Waterfall phase to assess risks before proceeding.

- Document Change Request (CR) process for mid-project updates.

- Pilot app with a sample farmer group before final rollout.

- Allocate a dedicated training & support team during deployment.

Question 6 – Stakeholder Analysis (RACI Matrix):

Perform stakeholder analysis (RACI Matrix) to find out the key stakeholders who can take Decisions and Who are the influencers

RACI Matrix for Stakeholder Roles:

Key Roles Used in RACI:

R – Responsible: A person who perform the task or activity

A – Accountable: A person who is ultimately answerable for the task’s success.

C – Consulted: A person whose opinions are sought (two-way communication)

I – Informed: A person who are kept updated (one-way communication).

| RACI Role | Stakeholder Name | Designation / Role | Key Notes |
| --- | --- | --- | --- |
| Accountable | Mr. Henry | Sponsor (SOONY) | Final decision-maker; approves budget, scope, UAT, and go-live. |
| Accountable | Mr. Pandu | Financial Head (SOONY) | Co-accountable for budget approvals and financial oversight. |
| Consulted | Mr. Dooku | Project Coordinator | Acts as liaison between SOONY and APT IT Solutions; influences direction. |
| Accountable | Mr. Karthik | Delivery Head | Owns successful delivery and overall client satisfaction. |
| Responsible | Mr. Vandanam | Project Manager | Executes daily project activities; manages the team and timeline. |
| Responsible & consulted | Sham Kailas | Business Analyst | Gathers requirements, model business processes, consults users. |
| Consulted | Peter, Kevin, Ben | Farmers (End Users / Stakeholder Advisors) | Provide domain-specific requirements; influence usability decisions. |
| Responsible | Ms. Juhi | Senior Java Developer | Leads development tasks and guides dev team. |
| Responsible | Teyson, Lucie, Tucker, Bravo | Java Developers | Implement core functionality and backend logic. |
| Responsible | Mr. Jason & Ms. Alekya | QA/Testers | Perform functional and regression testing. |
| Responsible | Mr. Mike | Network Administrator | Sets up hosting, networking, and app deployment infrastructure. |
| Responsible | Mr. John | Database Administrator | Designs and maintains data layer and database security. |
| Consulted | UI/UX Designer | (To be onboarded / outsourced) | Provides insights into layout, accessibility, and rural usability. |
| Informed | APT IT Legal / Finance | Corporate Finance & Compliance (internal) | Updated on fund utilization, legal compliance, etc. |
| Accountable | SOONY Committee | CSR Board (Henry, Pandu, Dooku) | Collective accountability for CSR success and project vision. |

Summary by Category:

Responsible (R) – Executes the Tasks:

- Mr. Vandanam (Project Manager)

- Business Analyst (Sham Kailas)

- Ms. Juhi (Senior Developer)

- Java Developers (Teyson, Lucie, Tucker, Bravo)

- QA/Testers (Jason, Alekya)

- Mr. Mike (Network Admin)

- Mr. John (DBA)

Accountable (A) – Final Decision-Makers:

- Mr. Henry (Sponsor)

- Mr. Pandu (Finance Head)

- Mr. Karthik (Delivery Head)

- SOONY Committee (CSR Governance Board)

Consulted (C) – Influence the Work:

- Mr. Dooku (Project Coordinator)

- Business Analyst (during requirement gathering)

- Peter, Kevin, Ben (Farmer Stakeholders)

- UI/UX Designer

Informed (I) – Need Updates, Not Involved in Decisions:

- APT IT Legal / Finance Team

- Internal HR / Admin for staffing

- Support staff for training delivery (later phase)

Key Decision Makers:

- Mr. Henry, Mr. Pandu, and Mr. Karthik are the main accountable stakeholders — they have decision-making authority at all key phases (budget, design approval, UAT sign-off, go-live).

Key Influencers:

- Mr. Dooku, Peter/Kevin/Ben, and UI/UX Designer are consulted regularly — they influence feature design, accessibility, and usability decisions.

Question 7 – Business Case Document:

Help Mr Karthik to prepare a business case document.

Business Case Document:

Project Title: Online Agriculture Products Store

Submitted By: Mr. Karthik, Delivery Head, APT IT SOLUTIONS

Client: SOONY CSR Committee (Mr. Henry, Mr. Pandu, Mr. Dooku)

Date: 25/07/2025

Model: Waterfall Development Approach

Budget: ₹2 Crores INR

Duration: 18 Months

Why is this project initiated?

This business case outlines the justification for developing an Online Agriculture Products Store, a CSR initiative by SOONY aimed at addressing the supply challenges faced by farmers in remote villages. The platform will enable farmers to access and order fertilizers, seeds, and pesticides directly from manufacturers through a mobile/web application. This initiative supports rural empowerment, supply chain transparency, and digital inclusion.

What are the current problems?

Current Problem Statement Situation, Farmers like Peter, Kevin, and Ben currently face:

- Inconsistent supply and availability of agri-products.

- High cost due to multiple intermediaries.

- No product transparency or after-sales support.

- Travel burden and limited local inventory.

- Low digital access and literacy for modern procurement methods.

With this project, how many problems could be solved?

Project Objectives:

- Enable remote farmers to purchase agriculture products digitally.

- Connect farmers directly with manufacturers (bypassing middlemen).

- Promote transparency in pricing and availability.

- Build a scalable, user-friendly digital ecosystem accessible even in rural areas.

- Support SOONY's CSR goal of sustainable rural development.

Waterfall-model-based application:

- Digitally lists products from certified manufacturers.

- Allows farmers to browse, compare, and purchase online.

- Supports regional language, simple UI, mobile-first design.

- Facilitates direct communication and feedback with vendors.

- Provides delivery tracking and customer service.

What are the resources required?

To successfully deliver the Online Agriculture Products Store project under the Waterfall model, a combination of human, technical, financial, and external resources is essential.

Key human resources include a project sponsor, financial head, project coordinator, project manager, business analyst, UI/UX designer, senior and junior Java developers, QA testers, database and network administrators, as well as trainers for farmer onboarding.

Technical resources such as development machines, cloud hosting infrastructure, mobile test devices, databases, version control systems, project management tools (like JIRA), testing tools (e.g., Selenium, Postman), and UI/UX design platforms (like Figma or Adobe XD) will be required to support system design and development. For training and support, localized guides, visual tutorials, help desk platforms, and community engagement resources will ensure farmer adoption and post-launch assistance.

As the project will be financed through a ₹2 Crore CSR budget, covering salaries, infrastructure costs, training expenses, and a contingency buffer. Comprehensive documentation such as Business Requirement Documents (BRD), Software Requirement Specifications (SRS), traceability matrices, test plans, user manuals, and CSR impact reports will ensure alignment and transparency throughout the project lifecycle. Additionally, external resources such as logistics partners for last-mile delivery, manufacturer APIs for product listings, and legal support for compliance and data privacy are vital for end-to-end functionality and scalability.

How much organizational changes is required to adopt this technology?

Scope of the Project:

In Scope:

- Requirement analysis, UI/UX design, backend development using Java.

- Android-based mobile app & responsive web portal.

- Admin panel for manufacturers and CSR reporting.

- Order management, inventory view, delivery request features.

- Training and onboarding support.

Out of Scope:

- Offline manual orders.

- Hardware/device distribution to farmers.

- Integration with government subsidy or KYC systems.

What is the time frame to recover ROI (Return on Investments)?

- Timeline (Waterfall Phases)

- Requirement Gathering: 2 months duration

- System & UI Design: 2 months duration

- Development: 6 months duration

- Testing & UAT: 3 months duration

- Deployment & Training: 3 months duration

- Handover & Closure: 2 months duration

- Total: 18 months

How to identify Stakeholders?

Stakeholder Analysis (Key Roles) RACI.

| Stakeholder | Role |
| --- | --- |
| Mr. Henry | Project Sponsor & CSR Lead |
| Mr. Pandu | Financial Approver |
| Mr. Dooku | Project Coordinator (SOONY) |
| Mr. Karthik | Delivery Head (APT IT) |
| Mr. Vandanam | Project Manager |
| BA | Requirements & Process Modelling |
| Dev/QA/Infra Team | Technical Execution |
| Peter, Kevin, Ben | Farmer Advisors (User) |

Resources Required:

- Skilled manpower: PM, BA, Dev, QA, UI/UX, Trainers, Infra

- Technical assets: Cloud infra, devices, dev/test tools

- Financial planning: ₹2 Cr overall budget with 15% buffer

- Documentation & support systems for training and feedback

- Partnerships: Manufacturers, delivery agents, rural champions

Benefits & Value Creation:

Farmers: Easy access to quality products, better prices, reduced travel, improved yield.

SOONY (CSR): Visibility into impact metrics, rural empowerment, brand goodwill.

Manufacturers: Direct market access to untapped rural buyers.

Local Economy: More efficient supply chain and reduced exploitation.

Question 8 – Four SDLC Methodologies:

The Committee of Mr. Henry, Mr Pandu, and Mr Dooku and Mr Karthik are having a discussion on Project Development Approach.

Mr Karthik explained to Mr. Henry about SDLC. And four methodologies like Sequential, Iterative, Evolutionary and Agile. Please share your thoughts and clarity on Methodologies.

Software Development Life Cycle (SDLC) is a structured process that defines the stages involved in developing a software solution — from planning stage to requirement analysis, design, development, testing, deployment, and maintenance. The SDLC helps teams deliver high-quality software that meets customer expectations, within time and budget constraints.

There are various methodologies under SDLC to manage how these phases are executed. The choice of methodology depends on:

Complexity of the project

Flexibility of scope

Stakeholder involvement

Time and budget constraints

4 Types of Methodologies:

Sequential Model (Waterfall): The Sequential (Waterfall) model is the most traditional SDLC methodology. It follows a linear and step-by-step approach, where each phase (Requirements → Design → Development → Testing → Deployment) is completed before moving to the next.

Key Features:

- Well-documented requirements at the beginning

- Little to no overlap between phases

- Progress flows in one direction

Best For:

- Projects with fixed scope, time, and budget

- Government or CSR-funded projects

- Minimal stakeholder change requests

Limitations:

- Not flexible once development begins

- Late detection of issues (during testing)

- Not ideal when requirements are expected to evolve

Iterative Model: The Iterative model breaks the system into smaller sections called iterations. Each iteration passes through the complete SDLC cycle — and builds on the previous version — gradually improving the system.

Key Features:

- Partial implementation is delivered early

- New features or changes can be added in the next iteration

- Allows progressive learning and refinement

Best For:

- Projects where requirements evolve during development

- Situations where client wants early visibility of working features

Limitations:

- Initial architecture needs to be robust

- Cost may increase if too many iterations occur

Evolutionary Model: The Evolutionary model focuses on rapid prototyping and continuous refinement based on frequent customer feedback. The system evolves as user needs become clearer.

Key Features:

- Early delivery of a working prototype

- Feedback is collected regularly and implemented in subsequent versions

- Good for experimental or uncertain requirements

Best For:

- Pilot projects

- Applications needing field validation (like this agriculture app)

- Projects involving end-users with low digital literacy who benefit from seeing prototypes

Limitations:

- Project scope may become unclear

- Harder to manage and predict timelines or budget.

Agile Scrum Methodology: Agile Scrum is a collaborative, incremental, and flexible development methodology. Work is broken into sprints (typically 2–4 weeks), each delivering a functional piece of the system. Stakeholders are involved throughout.

Key Features:

- Strong focus on customer feedback

- Daily stand-up meetings, sprint planning, reviews

- Functional product delivered at end of each sprint

Best For:

- Projects requiring frequent changes or updates

- Teams with high collaboration and communication

- Products for dynamic user markets

Limitations:

- Requires close client involvement

- Harder to apply in fixed-cost CSR or government projects

- May lead to scope creep without tight control

Question 9 – Waterfall RUP Spiral and Scrum Models

They discussed models in SDLC like waterfall RUP Spiral and Scrum. You put forth your understanding on these models

When the APT IT SOLUTIONS company got the project to make this online agriculture product store, there is a difference of opinion between a couple of SMEs and the project team regarding which methodology would be more suitable for this project. SMEs are stressing on using the V model and the project team is leaning more onto the side of waterfall model. As a business analyst, which methodology do you think would be better for this project?

As a Business Analyst, it is my role to evaluate and recommend the most appropriate SDLC methodology for the project's success—balancing client expectations, project constraints, and technical feasibility.

Understanding of SDLC Models (Waterfall, RUP, Spiral, Scrum, V-Model):

Waterfall Model:

- Linear and phase-based, where each stage (requirements, design, development, testing, deployment) must be completed before moving to the next.

- Works best when requirements are stable, scope is well-defined, and changes are minimal.

- Suited for fixed-budget and timeline projects like CSR initiatives.

V-Model (Validation & Verification Model):

- An extension of the Waterfall model, where each development phase has a directly associated testing phase.

- Offers strong quality assurance, and supports early test planning.

- Suitable for projects with minimal changes, strong compliance needs, and structured requirements.

RUP (Rational Unified Process):

- A framework-based iterative model with four phases: Inception, Elaboration, Construction, Transition.

- Emphasizes risk reduction and reuse, but needs skilled teams and may be overkill for smaller or medium projects.

- Best for complex, enterprise-scale systems.

Spiral Model:

- Combines iterative development with risk analysis.

- Ideal for projects with high risk, evolving requirements, and frequent reassessments.

- Less suitable for CSR projects with limited resources and short timelines.

Scrum (Agile Methodology):

- Incremental and iterative, involving short sprints and continuous user feedback.

- Encourages collaboration, flexibility, and early delivery.

- Needs high stakeholder involvement and quick turnaround — not always feasible with non-tech-savvy users (farmers) or government-style CSR models.

The Conflict: V-Model vs Waterfall – Which One to Choose?

- SMEs prefer the V-Model:
Because it emphasizes testing and validation at every step, it reduces the risk of defects reaching the end user, which is especially important for systems used by non-technical rural farmers.

- Project Team leans toward Waterfall:
Likely due to its simplicity, cost predictability, and alignment with the CSR contract's structure (fixed scope, budget, and time).

As a Business Analyst, I would support the SMEs' suggestion to use the V-Model, for the following reasons:

- Farmers are non-technical users — system must be bug-free and reliable.

- The V-Model ensures rigorous testing at each stage — reducing post-deployment failures.

- Requirements are well-defined — perfect for the structured nature of the V-Model.

- Matches Waterfall in structure but adds early quality assurance, improving user trust.

- The project has limited timeline and budget, so catching bugs early avoids costly rework.

In short, the V-Model provides all the predictability of Waterfall, but with the added strength of early and parallel testing, which is vital for a public-facing rural CSR project.

Question 10 – Waterfall Vs V-Model:

20 Write down the differences between waterfall model and V model.

Differences between Waterfall Model and V-Model as below:

| Aspect | Waterfall Model | V-Model |
| --- | --- | --- |
| 1. Approach | Sequential (linear flow) | Sequential with parallel testing activities |
| 2. Testing Phase | Starts after development phase ends | Testing is planned and executed alongside each development phase |
| 3. Focus | Focus is mainly on development | Equal focus on development and testing |
| 4. Verification & Validation | Performed only at the end | Performed at each corresponding phase |
| 5. Defect Detection | Detected late, during testing | Detected early due to parallel testing activities |
| 6. Risk of Rework | Higher due to late error discovery | Lower due to early error detection |
| 7. Time to Market | May be longer if errors are found late | Potentially faster due to early quality control |
| 8. Cost of Fixing Bugs | High (bugs found late) | Lower (bugs found early) |
| 9. Flexibility for Changes | Low | low; not suited for frequent requirement changes |
| 10. Diagram Representation | Linear straight line | V-shape (development on left, testing on right) |
| 11. User Involvement | Involved mainly during requirement and acceptance | Involved in validation and UAT stages |
| 12. Test Planning | Done only after development | Planned during requirement and design stages |
| 13. Suitable For | Projects with clearly defined, simple requirements | Projects where quality, reliability, and early testing are critical |
| 14. Error Correction Time | Late in development cycle | Throughout the cycle, in each phase |
| 15. Documentation | Required upfront | Required for both development and testing early on |
| 16. Example Usage | Simple web apps, internal tools | Banking, healthcare, government, CSR solutions |
| 17. QA Team Involvement | Starts in the testing phase | Starts from the very beginning |
| 18. Maintenance Effort | Often more due to late bug discovery | Typically less because of early quality checks |
| 19. Model Type | Development-driven | Verification-driven |
| 20. Best Use Case in CSR | When speed and simplicity are key | When trust, quality, and user safety are priorities (like for farmers) |

Question 11 – Justify your choice:

As a BA, state your reason for choosing one model for this project?

Adopt the V-Model:

In alignment with the opinions shared by Subject Matter Experts (SMEs) and considering the project’s characteristics — such as a fixed CSR budget, strict timeline, and end users from rural farming communities — the V-Model is recommended over the standard Waterfall approach.

Justification:

- It ensures early detection of defects through parallel testing at each development stage.

- It maintains structured phase-based flow similar to Waterfall — aligned with the expectations of the CSR Committee and funding model.

- It allows test planning from the beginning, improving overall quality and reliability.

- It is highly suitable for projects where user acceptance and trust are critical, especially in low-tech rural areas.

- Mitigates risk of post-deployment issues, which may be costly or logistically difficult to fix after rollout.

- V-Model is best when quality assurance is critical and early testing must be integrated.

Question 12 – Gantt Chart:

The Committee of Mr. Henry, Mr Pandu, and Mr Dooku discussed with Mr Karthik and finalised on the V Model approach (RG, RA, Design, D1, T1, D2, T2, D3, T3, D4, T4 and UAT) Mr Vandanam is mapped as a PM to this project. He studies this Project and Prepares a Gantt chart with V Model (RG, RA, Design, D1, T1, D2, T2, D3, T3, D4, T4 and UAT) as development process and the Resources are PM, BA, Java Developers, testers, DB Admin, NW Admin.

Continues in next page..

Project Development Approach: V-Model

Each Development Phase is followed by a corresponding Testing Phase, consistent with the V-Model approach. Here's a breakdown of tasks and durations.

| Phase | Duration | Start Date | End Date | Assigned Resources |
| --- | --- | --- | --- | --- |
| Requirement Gathering (RG) | 6 weeks | Aug 1, 2025 | Sep 12, 2025 | PM, BA |
| Requirement Analysis (RA) | 6 weeks | Sep 13, 2025 | Oct 24, 2025 | PM, BA |
| System Design | 6 weeks | Oct 25, 2025 | Dec 5, 2025 | PM, BA, Java Devs, DB Admin |
| Development Phase 1 (D1) | 8 weeks | Dec 6, 2025 | Jan 30, 2026 | Java Developers |
| Testing Phase 1 (T1) | 4 weeks | Jan 31, 2026 | Feb 27, 2026 | Testers |
| Development Phase 2 (D2) | 8 weeks | Feb 28, 2026 | Apr 24, 2026 | Java Developers |
| Testing Phase 2 (T2) | 4 weeks | Apr 25, 2026 | May 22, 2026 | Testers |
| Development Phase 3 (D3) | 8 weeks | May 23, 2026 | Jul 17, 2026 | Java Developers |
| Testing Phase 3 (T3) | 4 weeks | Jul 18, 2026 | Aug 14, 2026 | Testers |
| Development Phase 4 (D4) | 8 weeks | Aug 15, 2026 | Oct 9, 2026 | Java Developers |
| Testing Phase 4 (T4) | 4 weeks | Oct 10, 2026 | Nov 6, 2026 | Testers |
| User Acceptance Testing (UAT) | 6 weeks | Nov 7, 2026 | Dec 18, 2026 | PM, BA, Testers, NW Admin |

Question 13 – Fixed Bid Vs Billing:

Explain the difference between Fixed Bid and Billing projects?

In software and IT project delivery, Fixed Bid and Billing (Time and Material) represent two distinct engagement models, each suited for different types of project needs.

A Fixed Bid project is one where the client and vendor agree upon a set price for the entire project, regardless of the actual effort or time taken to complete it. This model requires a clearly defined scope and well-documented requirements at the beginning. Since the pricing is fixed, the vendor bears most of the risk if the project effort exceeds estimates, making it suitable for projects where the requirements are unlikely to change. The timelines and deliverables are strictly bound to the initial agreement, and any deviation from the original scope usually requires formal change requests and cost renegotiation.

On the other hand, a Billing project is one where the client pays for the actual hours or resources spent on the project. This model is much more flexible and adaptive to evolving requirements. The scope is not rigid and can be adjusted throughout the development process, which makes this approach ideal for projects where the requirements are not fully known upfront or are expected to change frequently. While it offers flexibility, it also places more risk on the client, especially in terms of potential cost overrun if the project expands beyond initial expectations. The vendor benefits from this model as they are compensated for the actual effort without being penalized for changing scopes or extended timelines.

In summary, Fixed Bid is best suited for well-defined, predictable projects with minimal change, while Billing project is better for complex or evolving projects where flexibility and iterative progress are needed.

Question 14 – Preparer Timesheets of a BA in various stages of SDLC:

- Design Timesheet of a BA

- Development Timesheet of a BA

- Testing Timesheet of a BA

- UAT Timesheet of a BA

- Deployment n Implementation Timesheet of a BA

Business Analyst Timesheet – Design Stage (SDLC):

| S.No | Task | Actionable Items | Start Time | End Time | Duration |
| --- | --- | --- | --- | --- | --- |
| 1 | Review Functional Specs | Go through BRD and SRS to validate inputs for design phase | 9:00 AM | 10:30 AM | 1hr 30m |
| 2 | Prepare Use Case Diagrams | Create visual flows for major user interactions | 10:45 AM | 12:15 PM | 1hr 30m |
| 3 | Collaborate with Designers | Discuss wireframes and layout structure with UI/UX team | 1:30 PM | 2:30 PM | 1hr |
| 4 | Validate Data Requirements | Align data inputs/outputs with DB design team | 2:45 PM | 4:00 PM | 1hr 15m |
| 5 | Review Design Document | Final review of HLD/LLD drafts before walkthrough with stakeholders | 4:15 PM | 5:30 PM | 1hr 15m |

Business Analyst Timesheet – Development Stage (SDLC):

| S.No | Task | Actionable Items | Start Time | End Time | Duration |
| --- | --- | --- | --- | --- | --- |
| 1 | Conduct Developer Walkthrough | Explain finalized requirements and workflows to the development team | 9:00 AM | 10:00 AM | 1 hr |
| 2 | Clarify Requirements | Respond to developer queries and provide clarifications on business logic | 10:15 AM | 11:30 AM | 1 hr 15m |
| 3 | Review Technical Design Docs | Review mapping of business requirements to technical modules | 11:45 AM | 12:30 PM | 45 mins |
| 4 | Support Development QA | Participate in data validation and test case alignment with dev & QA teams | 2:00 PM | 3:30 PM | 1 hr 30m |
| 5 | Update Requirement Traceability | Ensure traceability matrix reflects ongoing development status | 3:45 PM | 4:30 PM | 45 mins |

Business Analyst Timesheet – Testing Stage (SDLC):

| S.No | Task | Actionable Items | Start Time | End Time | Duration |
| --- | --- | --- | --- | --- | --- |
| 1 | Review Test Cases | Validate test cases against business requirements and use cases | 9:00 AM | 10:30 AM | 1 hr 30m |
| 2 | Participate in Test Execution | Attend test execution sessions to observe critical user journeys | 10:45 AM | 12:00 PM | 1 hr 15m |
| 3 | Log Defects/Clarify Issues | Review defects, provide clarifications, and verify against original requirements | 1:30 PM | 2:30 PM | 1 hr |
| 4 | Support UAT Preparation | Assist in preparing UAT scenarios, aligning them with business expectations | 2:45 PM | 4:00 PM | 1 hr 15m |
| 5 | Update RTM & Test Reports | Update the Requirement Traceability Matrix and review daily test status reports | 4:15 PM | 5:00 PM | 45 mins |

Business Analyst Timesheet – UAT Stage (SDLC):

| S.No | Task | Actionable Items | Start Time | End Time | Duration |
| --- | --- | --- | --- | --- | --- |
| 1 | Prepare UAT Checklist | Create UAT scenarios, acceptance criteria, and test data in line with business needs | 9:00 AM | 10:30 AM | 1 hr 30m |
| 2 | Coordinate with Users | Guide end users through test cases and clarify business rules during execution | 10:45 AM | 12:15 PM | 1 hr 30m |
| 3 | Monitor UAT Progress | Track UAT execution status, log observations, and report issues to dev/test teams | 1:30 PM | 2:30 PM | 1 hr |
| 4 | Validate Reported Defects | Analyze UAT bugs, confirm alignment with requirements, and support resolution | 2:45 PM | 3:45 PM | 1 hr |
| 5 | Final Sign-off Support | Assist in preparing UAT sign-off document and ensure business requirements are met | 4:00 PM | 5:00 PM | 1 hr |

Business Analyst Timesheet – Deployment & Implementation Stage (SDLC):

| S.No | Task | Actionable Items | Start Time | End Time | Duration |
| --- | --- | --- | --- | --- | --- |
| 1 | Coordinate Go-Live Activities | Participate in go-live planning, schedule meetings with stakeholders | 9:00 AM | 10:30 AM | 1 hr 30m |
| 2 | Final Requirements Validation | Recheck if deployed system aligns with signed-off requirements | 10:45 AM | 12:00 PM | 1 hr 15m |
| 3 | Support Data Migration Checks | Work with DB Admin to validate migrated data is complete and accurate | 1:30 PM | 2:30 PM | 1 hr |
| 4 | End User Support Coordination | Coordinate initial issue handling, FAQs, and basic guidance to users | 2:45 PM | 4:00 PM | 1 hr 15m |
| 5 | Feedback Collection & Handover | Collect feedback, update implementation checklist, and assist in formal closure | 4:15 PM | 5:00 PM | 45 mins |