## Slide 1: SRT OPTIFLOW WORKFLOW OPTIMIZATION ENHANCEMENT
PREPARED BY: Bandari Vaishnavi
DATE: 28-08-2025

## Slide 2
Situation:
Title: Current Challenges
Manual effort required to locate key policy rules.
Scrolling through large transcripts is time-consuming.
URLs scattered across transcript text.
Risk of tagging errors without confirmation.

## Slide 3
Problems:
Title: Challenges Identified 1. Only one out of many policies currently shows highlight keywords making it difficult to verify ad compliance for the rest.
2. Moderators spend excessive time navigating transcripts and locating URLs.
3. Serious escalation policy sits near “ None” option in UI , prone to misclicks and risk.
4. This results in slower processing, missed details, and an increased risk of mistakes.

## Slide 4
Opportunity:
Opportunities Title: Areas for Improvement By introducing key enhancements, moderators can work smarter, not harder:
- Quickly find key rules using highlights.
- View all URLs in a single click.
- Avoid scrolling large transcript texts.
- Prevent serious tagging errors with confirmation pop-ups.

## Slide 5
Purpose Statement:
To enhance the existing moderation workflow by implementing four targeted features that reduce manual effort, improve accuracy, and prevent critical errors — ultimately streamlining the daily operations of content moderators.
Proposed Features
Policy Highlights: Highlight key rules for quick scanning.
2. URL Aggregator: Display all URLs in a popup window.
3. Collapsible Transcript: Allow minimized transcript view.
4. Escalation Confirmation: Prevent critical tagging errors.

## Slide 6
Project Objectives:
- Integrate policy highlighters into the UI.
- Provide centralized URL viewing.
- Implement collapsible transcript sections.
- Add confirmation prompts for escalations.

## Slide 7
30% faster policy referencing using highlighters.
Reduce URL navigation time by 50 %assessments
40% reduction in average page scroll length due to minimized text.
Eliminate escalation tagging errors by 90 %using reposition + pop-up.
Success Criteria

## Slide 8
Waterfall Method/Approach:
The Waterfall model is a linear and sequential approach where the project progresses through distinct phases. Each phase must be completed before the next begins, and there is typically no overlapping between phases.
Requirement Gathering (0.5 month):
  Collected feedback from employees, review current workflows.
  Identify employee problem and feature feasibility.
  Reviewed existing portal analytics and user behavior.
  Defined business needs and system limitations
  Estimated Cost: ₹1lakh
  BRD(Business Requirement Document)
  Business Case Document
  RTM Requirement Traceability Matrix
Design (0.5 month):
  Created UI/UX wireframes/mockups for new features and create workflows.
  Updated system architecture documentation
  Finalized workflows for Highlighters,url button, minus the extra content , change danger policy position and alert popup.
  Use Case Spec Document , Use Case And Activity Diagrams

## Slide 9
Development (1.5 months):
  Frontend: UI component one single button , highlighters colouring .
  Backend: Logic for highlighters, URL tab ,remove content , set popup for most impacted policy, linking red color for that serious biggest escalation policy.
  Database: Schema updates for new features
  Estimated Cost: ₹7,00,000
  Functional and Non-functional Requirement Document
Testing (0.5 month):
  Unit testing of individual modules
  Integration testing with SRT modules
  Regression testing to ensure no disruption to current features
  Estimated Cost: ₹100,000
  Test Case Document
UAT (1 month):
  Conducted with selected employees
  Collected feedback on usability and feature completeness
  Final approval before full deployment
  Estimated Cost: ₹200,000
  Sign off and Approval
Total Estimated Budge ₹12,00,000

## Slide 10
Resources
Role | Count | Company | Involvement Period
Project Manager | 1 | IT Solutions | Full project (4 months)
Java Developers Devops engineer , Python Developers | 5 | IT Solutions | 2.5 months (Design to Testing)
Database Admins | 2 | IT Solutions | 1.75 months (Design to Testing)
System Admins | 2 | IT Solutions | 1.25 months (Dev, Testing, UAT)
QA Testers | 3 | IT Solutions | 1.5 months (Testing & UAT)
Business Analyst (You) | 1 | IT Solutions | Entire lifecycle (4 months)

## Slide 11
Total Duration: 4 months Total Budget: ₹12,00,000
Phase | Duration | Key Activities | Estimated Cost
Requirement Gathering | 0.5 month | Stakeholder interviews, documentation | ₹100,000
Design | 0.5 month | Wireframes, architecture planning | ₹1,00,000
Development | 1.5 months | Coding backend/frontend, DB setup | ₹7,00,000
Testing | 0.5 month | QA, integration, regression testing | ₹100,000
User Acceptance Testing (UAT) | 1 month | Feedback, bug fixes, approval | ₹2,00,000

## Slide 12
Other Resources:
Hardware:
Dedicated servers.
Developer laptops/workstations
Storage and backup devices
Redundancy hardware (RAID/ cloud)
I/O devices (monitors , projectors)
Software:
Optiflow platform (core)
IDEs, Git for development
Testing tools (Selenium, JIRA)
Design tools (Figma,Adobe XD)
Collaboration tools (Teams)
Database (SQL) and automated url tools
Network:
High-speed internet connections
VPNs or secure email gateways for handling client data securely
APIs for integrations.

## Slide 13
Risks and Dependencies
Risks:
Resistance to UI changes .
Miscommunication on policy priority.
Bugs during integration.
Dependencies:
3rd party tools for highlighting and URL rendering.
Approval from policy owners for UI adjustments.
Content API for transcript controls.

## Slide 14
Thank You…. !