# Question 1: Definition of Done

Answer:
The Definition of Done for CRMNEXT checklist

Definition of Done is a checklist of well-defined, measurable, and agreed-upon criteria that must be met before a backlog item is considered done.

Code Functionality

• Code implemented for all intended functionalities.

• Code reviewed and matches acceptance criteria.

User Story Validation

• Assumptions of user story verified.

• Acceptance criteria clearly met.

Build and Deployment

• Project builds successfully with no errors.

• Deployed to test environment identical to production.

Testing and QA

• Unit and integration tests written and passing.

• QA testing completed and issues resolved.

Cross-Platform Assurance

• Feature tested across all supported browsers/devices.

• No UI/UX discrepancies found on target platforms.

Design Approval

• UX designer reviewed and approved feature.

• Designs aligned with user expectations.

PO and Peer Review

• Product Owner signed off the feature.

• Peer code review completed successfully.

Documentation and Config

• Documentation updated as per new implementation.

• Any config/build changes logged and documented.

Refactoring and Cleanup

• Code refactored and optimized.

• No deprecated logic or commented code left behind.

# Question 2: Product Vision

# Answer:
Product Vision – CRMNEXT Lead Management System

| Section | Details (CRMNEXT Project) | Reference |
| --- | --- | --- |
| Project Name | Customer Lead Management System – CRMNEXT | Title Slide |
| Client | Retail Banking Business Division | Sign-off Slide |
| Stakeholders | Project Sponsor, CRMNEXT Vendor, Agile Coach, IT Integration Lead, Business Analysts, End-user Champions | Sign-off Slide |
| Scrum Master | To be assigned internally (Agile Coach / Project Manager likely candidate) | Assumed from Agile Coach role |
| Product Owner | Ritesh Nigam | Prepared By PO + PM Role |
| Scrum Developers | CRMNEXT Implementation Specialists, IT Integration Team | Resources Slide |

VISION:
Banks today face significant challenges due to disjointed lead sources, delayed follow-ups, and poor visibility into customer engagement. CRMNEXT aims to transform banking lead management by offering a centralized, automated, and intelligent system that ensures faster response, improved conversions, and higher customer satisfaction. Our mission is to empower banks with real-time insights, process automation, and seamless integration—ensuring agility, transparency, and growth across every lead lifecycle touchpoint.

| Market Segment | Target Users/Customers | Needs | Product Features | Feasibility & Value |
| --- | --- | --- | --- | --- |
| Banking and financial services industry, especially retail and corporate banking | Bank sales managers, relationship officers, customer support teams, and IT/business heads | Banks need to unify their lead tracking and response process across channels to reduce leakage, improve conversions, and enhance visibility. | CRMNEXT offers automated lead assignment, escalation workflows, real-time dashboards, multi-device access, and integration with core banking systems. | Feasible via Agile delivery and vendor-backed CRM modules. High ROI potential via increased conversion rates, reduced TAT, and improved customer engagement. |
|  | Customers seeking faster query responses or product support (loans, cards, savings, etc.) | Timely communication and proper follow-up from the bank to avoid dissatisfaction or churn. | Features include instant notifications, lead aging alerts, self-service lead creation, and UAT-tested CRM dashboards. | Adds value through faster go-to-market, scalability, and audit-ready digital process trails that enhance trust and compliance. |

# Question 3: User Stories

Answer:

| User Story No: 1 | Tasks: 2 |
| --- | --- |
| Priority: Highest |  |
| AS A SALES MANAGER I WANT TO VIEW REAL-TIME DASHBOARDS SO THAT I CAN MONITOR TEAM PERFORMANCE |  |
| BV: 400 | CP: 04 |
| ACCEPTANCE CRITERIA : Dashboard Screen Filters for Region, RM, and Status Real-time data refresh Export to Excel option |  |

| User Story No: 2 | Tasks: 3 |
| --- | --- |
| Priority: High |  |
| AS A RELATIONSHIP MANAGER I WANT TO GET NOTIFIED ON LEAD ASSIGNMENT SO THAT I CAN TO RESPOND TO CUSTOMERS IMMEDIATELY |  |
| BV: 350 | CP: 03 |
| ACCEPTANCE CRITERIA SMS/Email trigger on assignment Notification within 1 minute Log for notification delivery |  |

| User Story No: 3 | Tasks: 2 |
| --- | --- |
| Priority: Medium |  |
| AS A DATA ENTRY EXECUTIVE I WANT TO CAPTURE LEAD DATA SO THAT I CAN TO ENSURE COMPLETE LEAD DETAILS |  |
| BV: 250 | CP: 02 |
| ACCEPTANCE CRITERIA Lead entry form with mandatory validation Dropdowns for product, branch, and channel Save and edit functionality |  |

| User Story No: 4 | Tasks: 4 |
| --- | --- |
| Priority: Highest |  |
| AS A SYSTEM ADMIN I WANT TO AUTO-ASSIGN LEADS BASED ON RULES SO THAT I CAN TO REDUCE LEAD ASSIGNMENT TIME |  |
| BV: 500 | CP: 05 |
| ACCEPTANCE CRITERIA Rule engine configuration screen Test rule engine against sample data Audit trail on lead assignment |  |

| User Story No: 5 | Tasks: 2 |
| --- | --- |
| Priority: Medium |  |
| AS A BRANCH MANAGER I WANT TO REVIEW ESCALATED LEADS SO THAT I CAN TO FOLLOW UP ON DELAYED RESPONSES |  |
| BV: 280 | CP: 03 |
| ACCEPTANCE CRITERIA Escalation screen listing stale leads Click to assign or close Remarks required on action |  |

| User Story No: 6 | Tasks: 1 |
| --- | --- |
| Priority: Low |  |
| AS AN ADMIN I WANT TO VIEW LEAD REPORTS SO THAT I CAN TO ANALYZE PERFORMANCE |  |
| BV: 150 | CP: 02 |
| ACCEPTANCE CRITERIA Monthly reports page Filters for region, product, and date Export PDF/Excel |  |

# Question 4: Agile PO Experience

Answer:
Product Owner Experience Summary – CRMNEXT Project

Market Analysis
I proactively analyzed market demand for CRM tools in the retail banking sector and benchmarked competitors like Salesforce and Zoho CRM. This helped identify key gaps in automation and visibility, shaping our value proposition.

Enterprise Analysis
I conducted thorough due diligence to uncover lead management improvement opportunities, estimating a potential 30% business increase through better conversion rates and reduced leakage.

Product Vision and Roadmap
I played a key role in defining a clear product vision focused on unifying and automating lead management. I developed a phased roadmap across three Agile sprints covering lead capture, dashboard creation, and system integration.

Managing Product Features
I worked closely with stakeholders to gather and prioritize requirements using MoSCoW and ROI techniques. This approach ensured alignment with business objectives and helped finalize key epics effectively.

Managing Product Backlog
I consistently maintained a prioritized product backlog, conducting regular grooming sessions. I collaborated with business analysts to break down epics into actionable, detailed user stories.

Managing Overall Iteration Progress
I actively monitored sprint progress through Agile boards and engaged in daily standups. My participation in sprint reviews and retrospectives ensured iterative improvements and alignment with team goals.

Lessons Learned from Sprint Meetings
Through facilitating sprint planning and reviews, I honed my ability to drive team alignment. I ensured backlog refinement sessions and retrospectives were focused and outcome-oriented.

User Story Creation
I contributed to drafting user stories with structured attributes such as ID, priority, business value, complexity points, and acceptance criteria. This helped in maintaining clarity and traceability for development.

Stakeholder Communication
I served as a critical bridge between stakeholders and Scrum teams. By providing timely updates and promoting transparency, I built trust and ensured consistent engagement from all parties.

Product Feature Definition and Backlog Items
I conceptualized core features like rule-based lead allocation and real-time dashboards. I also defined the Definition of Done (DoD) and broke features down into detailed backlog items to streamline delivery.

# Question 5: Product and sprint backlog and product and sprint burndown charts

Answer:

Product Backlog:

| User story ID | User story | Tasks | Priority | BV | CP | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| US-01 | View real-time dashboards | 2 | Highest | 400 | 04 | Sprint 2 |
| US-02 | Lead assignment notification | 3 | High | 350 | 03 | Sprint 1 |
| US-03 | Capture lead data | 2 | Medium | 250 | 02 | Sprint 1 |
| US-04 | Auto-assign leads | 4 | Highest | 500 | 05 | Sprint 2 |
| US-05 | Review escalated leads | 2 | Medium | 280 | 03 | Sprint 3 |
| US-06 | View lead reports | 1 | Low | 150 | 02 | Sprint 3 |

Sprint Backlog:

| User story ID | User story | Tasks | Owner | Status | Estimated effort |
| --- | --- | --- | --- | --- | --- |
| US-02 | Lead assignment notification | Design notification system | Ravi | In Progress | 5 hrs |
| US-02 | Lead assignment notification | Integrate with SMS/Email API | Anita | Not Started | 6 hrs |
| US-03 | Capture lead data | Create lead form | Karan | Completed | 4 hrs |
| US-03 | Capture lead data | Add dropdowns | Pooja | In Progress | 3 hrs |
| US-01 | View real-time dashboards | Design dashboard UI | Deepak | Not Started | 8 hrs |
| US-04 | Auto-assign leads | Rule engine backend | Vikram | In Progress | 10 hrs |
| US-05 | Review escalated leads | Escalation screen | Sonal | Not Started | 6 hrs |
| US-06 | View lead reports | Reports layout and filter | Anuj | Not Started | 4 hrs |

PRODUCT BURNDOWN TABLE

| PRODUCT BURNDOWN TABLE |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Task | Start Hours | Hours spent Day1 | Hours spent Day2 | Hours spent Day3 | Hours spent Day4 | Hours spent Day5 | Total Hours |
| US-01 | 8 | 2 | 1 | 0 | 3 | 2 | 8 |
| US-02 | 6 | 1 | 2 | 1 | 1 | 1 | 6 |
| US-03 | 4 | 1 | 0 | 1 | 1 | 1 | 4 |
| US-04 | 10 | 3 | 2 | 2 | 2 | 1 | 10 |
| US-05 | 6 | 0 | 2 | 1 | 1 | 2 | 6 |
| US-06 | 4 | 1 | 1 | 0 | 1 | 1 | 4 |
| Estimated Remaining Hours | 38 | 30.4 | 22.8 | 15.2 | 7.6 | 0 |  |
| Actual Remaining Hours | 38 | 30 | 24 | 19 | 11 | 0 |  |

SPRINT BURNOUT TABLE

| Day | Ideal Burndown (hrs) | Actual Remaining Effort (hrs) |
| --- | --- | --- |
| Day 0 | 38 | 38 |
| Day 1 | 34.2 | 35 |
| Day 2 | 30.4 | 32 |
| Day 3 | 26.6 | 29 |
| Day 4 | 22.8 | 25 |
| Day 5 | 19 | 21 |
| Day 6 | 15.2 | 17 |
| Day 7 | 11.4 | 12 |
| Day 8 | 7.6 | 8 |
| Day 9 | 3.8 | 3 |
| Day 10 | 0 | 0 |

SPRINT BURNOUT CHART

# Question 6: Sprint Meetings

Answer:
Meeting Type 1: Sprint Planning Meeting

| Date | 03/06/2025 |
| --- | --- |
| Time | 10:00 AM |
| Location | Conference Room A / MS Teams |
| Prepared By | Ritesh Nigam |
| Attendees | BA Team, CRMNEXT Team, Agile Coach |

Agenda Topics

| Topic | Presenter | Time allotted |
| --- | --- | --- |
| Backlog Review | Agile Coach | 15 mins |
| Sprint Goals Discussion | Product Owner | 20 mins |
| Task Assignment | Scrum Master | 25 mins |

Other Information

| Observers | IT Head, Business Sponsor |
| --- | --- |
| Resources | Kanban Board, Projector |
| Special Notes | Focus on integration backlog items |

Meeting Type 2: Sprint Review Meeting

| Date |  | 24/06/2025 |  |
| --- | --- | --- | --- |
| Time |  | 4:00 PM |  |
| Location |  | Zoom / Conference Room B |  |
| Prepared By |  | Ritesh Nigam |  |
| Attendees |  | All Stakeholders |  |
| Sprint status | Things to demo | Quick updates | What's next |
| Completed Sprint 2 | Dashboard, Notifications | Integration module pending | Start UAT planning |

Meeting Type 3: Sprint Retrospective Meeting

| Date | 25/06/2025 |
| --- | --- |
| Time | 11:00 AM |
| Location | MS Teams |
| Prepared By | Agile Coach |

Attendees: Scrum Team, PO, Agile Coach

| Agenda | What went well | What didn't go well | Questions / Reference |
| --- | --- | --- | --- |
| Sprint 2 Review | Daily stand-ups effective | Integration delay | Check CI/CD pipeline issues |

Meeting Type 4: Daily Stand-up Meeting

Week: 3 (from 17-06-2025 to 23-06-2025)

| Question: What did you do yesterday? | Name/Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Developer 1 | Worked on lead assignment logic | Integrated feedback notification service | Integrated feedback notification service | Refined user stories with BA | Updated CRMNEXT dashboard UI | Worked on lead assignment logic | Worked on lead assignment logic |
|  | Developer 2 | Updated CRMNEXT dashboard UI | Integrated feedback notification service | Refined user stories with BA | Refined user stories with BA | Fixed bug in lead escalation rules | Worked on lead assignment logic | Integrated feedback notification service |
|  | Developer 3 | Refined user stories with BA | Integrated feedback notification service | Updated CRMNEXT dashboard UI | Refined user stories with BA | Integrated feedback notification service | Refined user stories with BA | Integrated feedback notification service |
| Question: What will you do today? | Name/Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
|  | Developer 1 | Conduct unit testing on new modules | Sync with integration team | Prepare for sprint demo | Update sprint board and blockers | Sync with integration team | Complete UAT test cases | Complete UAT test cases |
|  | Developer 2 | Update sprint board and blockers | Sync with integration team | Complete UAT test cases | Complete UAT test cases | Complete UAT test cases | Sync with integration team | Complete UAT test cases |
|  | Developer 3 | Prepare for sprint demo | Sync with integration team | Sync with integration team | Complete UAT test cases | Update sprint board and blockers | Conduct unit testing on new modules | Prepare for sprint demo |
| Question: What (if any) is blocking your progress? | Name/Role | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday |
|  | Developer 1 | Waiting for API response mapping | Issue with environment setup | None | None | Waiting for API response mapping | None | Database access pending |
|  | Developer 2 | Need clarification on sprint goal | None | None | Issue with environment setup | Issue with environment setup | Issue with environment setup | None |
|  | Developer 3 | Need clarification on sprint goal | Waiting for API response mapping | Waiting for API response mapping | Issue with environment setup | Need clarification on sprint goal | Waiting for API response mapping | Issue with environment setup |