Question 1:  Write Agile Manifesto?

Answer: It is a foundational document for agile software development. It was created by a group of software developers and thought leaders to provide guiding principles and values that prioritize collaboration, adaptability and delivering high quality software. The Agile Manifesto reflects a shift from traditional, rigid project management approaches to more flexible and iterative development.

The 4 core values:

Agile values item on left more than those on right:

- Individuals and interaction over processes and tools.

- Working software over Comprehensive Documentation

- Customer collaboration over Contract Negotiation

- Responding to change over following a plan

The Agile Manifesto is supported by 12 Principles:

- Satisfy the customer through early and continuous delivery of valuable software.

- Welcome changing requirement even late in development. Agile process harness change for customer’s competitive advantage.

- Delivery working software frequently, from a couple of weeks to a couple of months with preference to the shorter timescale.

- Business people and developers must work together daily throughout the project.

- Build project around motivated individuals. Give them environment and support they need and trust them to get the job done.

- The most effective and efficient method of conveying information to and within a development team is face to face conversation.

- Working software is the primary measure of progress.

- Agile process promote sustainable development. The sponsors, developers and user should be able to maintain a constant pace indefinitely.

- Continuous attention to technical excellence and good design enhance agility.

- Simplicity- the art of maximising the amount of work not done is essential.

- The best Architect and designs emerge from self-organising team.

- At regular intervals, the team reflect on how to become more effective then tunes and adjust its behaviour accordingly.

Question 2: Write minimum 40 user stories and their Acceptance Criteria along with their BV and CP?

Answer:

| User Story No : 1 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO REGISTER IN SCRUM FOOD SO THAT I CAN DELIVER ORDER |  |  |  |
| BV: 500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: Registration Screen Text Boxes for Username, Password, Nation ID, Mobile Number, Email, Address, Phone Number Click on Registration button Send Registration successful message to the User |  |  |  |

| User Story No : 2 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO VIEW ORDERS SO THAT I CAN DELIVER ORDER |  |  |  |
| BV: 500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: View order, Display lists of Orders in tabular form |  |  |  |

| User Story No : 3 | Tasks:2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO ADD THE ADDRESS SO THAT I CAN GET THE ORDER TO MY ADDRESS |  |  |  |
| BV: 500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: Text Box to enter Business Rule: within the radius of 10 km |  |  |  |

| User Story No : 4 | Tasks:2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO SELECT PAYMENT MODE SO THAT I CAN MAKE PAYMENT OF MY CHOICE |  |  |  |
| BV: 500 |  | CP: 03 |  |
| ACCEPTANCE CRITERIA: Display payment mode, Radio buttons to select payment modes, payments button. Business Rule : can select only one payment mode |  |  |  |

| User Story No : 5 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO VIEW THE RESTAURANTS SO THAT I CAN APPROVE THE REGISTRATION |  |  |  |
| BV: 500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: Lists of Restaurants, select Restaurants, verify Restaurant Details, Approve button, Reject button, notification to the restaurant |  |  |  |

| User Story No :6 | Tasks: 2 |  | Priority: LOW |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIW THE RESTAURANT SO THAT I CAN ORDER THE FOOD |  |  |  |
| BV: 50 |  | CP: 01 |  |
| ACCEPTANCE CRITERIA: Display price in the lists of Menu item |  |  |  |

| User Story No : 7 | Tasks: 2 |  | Priority: LOW |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW THE CONTACT NUMBER OF DELIVERY BOY SO THAT I CAN CONTACT DELIVERY BOY FOR THE STATUS OF DELIVERY |  |  |  |
| BV: 50 |  | CP: 01 |  |
| ACCEPTANCE CRITERIA: Display delivery boy mobile number Display delivery boy name in tracking field |  |  |  |

| User Story No : 8 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO PROVIDE TIME SLOTS SO THAT CUSTOMER CAN CHECK OPENING AND CLOSING HOURS |  |  |  |
| BV: 100 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: Click on restaurant dashboard Add from time to time Click on submit Display updated successfully |  |  |  |

| User Story No : 9 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO VIEW RESTAURANT REVENUE REPORT SO THAT I CAN VIEW RESTAURANTS REVENUE |  |  |  |
| BV:200 |  | CP: 03 |  |
| ACCEPTANCE CRITERIA: Select reports Select revenue reports Select to and from date Select region ( can select all) Generate report Download report in Excel |  |  |  |

| User Story No : 10 | Tasks: 3 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A REGITERED ADMIN I WANT TO MANAGE REGIONAL RESTAURENT SO THAT I CAN TRACK THE PERFORMANCE OF REGIONAL RESTAURANT |  |  |  |
| BV: 200 |  | CP: 03 |  |
| ACCEPTANCE CRITERIA: Click on performance of restaurants Select from date to date Click on generate report which include Restaurants ID, Name, Revenue Click on download report which should be in excel |  |  |  |

| User Story No : 11 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO VIEW ORDERS SO THAT I CAN VIEW THE LIST OF ORDERS IN TABULAR FORM |  |  |  |
| BV: 500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: View orders , Display lists of orders in the tabular form |  |  |  |

| User Story No : 12 | Tasks: 2 |  | Priority: HIGH |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO CHAT WITH REG ADMIN SO THAT I CAN REQUEST FOR REFUND |  |  |  |
| BV:200 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: BR all mandatory Text box field Display order ID Text box for description Submit button generate issue ID Display successful |  |  |  |

| User Story No : 13 | Tasks:2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A ADMIN I WANT TO SEE REGIONAL REVENUE REPORTS SO THAT I CAN VIEW THE REGIONAL PERFORMANCE |  |  |  |
| BV: 500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: View orders , Display lists of orders in the tabular form |  |  |  |

| User Story No : 14 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO REGISTER IN SCRUM FOOD SO THAT I CAN LOGIN IN SCRUM FOOD APPLICATIONS |  |  |  |
| BV: 200 |  | CP: 04 |  |
| ACCEPTANCE CRITERIA: Registration screen Text boxes foe username, Password, Mobile number, Email ID, Address, Click on Register button Send successful ly registered notification to the user |  |  |  |

| User Story No : 15 | Tasks:2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO LOGIN IN SCRUM FOODS SO THAT I CAN USE THE SCRUM FOOD APPLICATION |  |  |  |
| BV: 200 |  | CP: 04 |  |
| ACCEPTANCE CRITERIA: Login screen Text boxes for username, Password, click on Login Button |  |  |  |

| User Story No : 16 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT SEARCH OPTION IN SCRUM FOOD APPLICATION SO THAT I CAN SEARCH RESTAURANTS TO ORDER FOOD |  |  |  |
| BV:200 |  | CP: 04 |  |
| ACCEPTANCE CRITERIA: Text boxes for Search menu , show restaurant details Enable Search option to display list of restaurants to order food |  |  |  |

| User Story No : 17 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW RESTAURANT MENU IN THE SCRUM FOOD APPLICATION SO THAT I CAN ORDER FOOD FROM RESPECTIVE RESTAURANT |  |  |  |
| BV: 500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: View the list of restaurants and Menu cards in tabular form Show available menu list of the restaurants |  |  |  |

| User Story No :18 | Tasks:2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO ORDER FOOD FROM RESTAURANT LISTED IN SCRUM FOOD APPLICATION SO THAT I CAN ORDER FOOD FROM RESPECTIVE RESTAURANT |  |  |  |
| BV: 200 |  | CP: 04 |  |
| ACCEPTANCE CRITERIA: Login, show the list of available restaurants Display menu cards, Enable the customer to select item and place order in application |  |  |  |

| User Story No : 19 | Tasks:3 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO MAKE ONLINE PAYMENT SO THAT I CAN PAY ONLINE ADVANCE PAYMENT |  |  |  |
| BV: 500 |  | CP:05 |  |
| ACCEPTANCE CRITERIA: Login, Show payment options Net Banking, UPI payments, Credit card Enable customer to select mode of payment and proceed with the payment option |  |  |  |

| User Story No : 20 | Tasks:3 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TOHAVE MY TRACKING ORDER SO THAT I CAN TRACK MY ORDER ONLINE |  |  |  |
| BV:500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Show status of delivery with the location detail, and expected time of delivery. Enable the customer to track the delivery of the placed order and expected time of delivery |  |  |  |

| User Story No : 21 | Tasks: 3 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT THE CANCEL OPTION SO THAT I CAN CANCEL THE ORDER IN CASE OF A REAS0N |  |  |  |
| BV: 500 |  | CP: 04 |  |
| ACCEPTANCE CRITERIA: Text box for cancel option, order can be cancelled mentioning the reason for cancellation Display the status as cancelled and process for refund to customer |  |  |  |

| User Story No : 22 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT FEEDBACK OTION SO THAT I CAN ACCEPT THE ORDER AND DELIVERY |  |  |  |
| BV: 500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Text box for feedback option, option to rate the delivery agent |  |  |  |

| User Story No : 23 | Tasks:3 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO REGISTER SO THAT I CAN ACCEPT THE ORDER AND DELIVERY |  |  |  |
| BV: 500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Text Boxes for Username, Password, Mobile Number, Email, Address, Phone Number Click on Registration button Send Registration successful message to the User |  |  |  |

| User Story No : 24 | Tasks: 3 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO LOGIN THE SCRUM FOOD APPLICTION SO THAT I CAN VIEW AND ACCEPT THE ORDER FOR DELIVERY |  |  |  |
| BV: 500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Text Boxes for Username, Password, Mobile Number, Email, Address, Phone Number Click on Login button Send successful message to the User |  |  |  |

| User Story No : 25 | Tasks:3 |  | Priority: Highest |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO UPDATE THE ORDER STATUS SO THAT I CAN VIEW AND UPDATE THE DELIVERY STATUS |  |  |  |
| BV: 500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: Text box for updating of delivery status and feedback |  |  |  |

| User Story No : 26 | Tasks: 3 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO UPDATE PAYMENT STATUS SO THAT I CANVIEW ANDUPDATE THE PAYMENT STATUS FOR COD |  |  |  |
| BV:500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Text box for updating payment status and feedback |  |  |  |

| User Story No : 27 | Tasks: 3 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO LOGIN SO THAT I CAN VIEW THE FEEDBACK FOR MY DELIVERY |  |  |  |
| BV: 500 |  | CP:05 |  |
| ACCEPTANCE CRITERIA: Text Boxes for Username, Password, Mobile Number, Email, Address, Phone Number Click on Login button Send successful message to the User and access to delivery boy |  |  |  |

| User Story No : 28 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO VIEW DETAILS SO THAT I CAN VIEW THE LISTS OF ORDERS AND RELATED FEEDBACK FROM CUSTOMER |  |  |  |
| BV: 500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Text Boxes for Username, Password, Mobile Number, Email, Address, Phone Number Click on Login button Send successful message to the User and access to restaurant owner |  |  |  |

| User Story No : 29 | Tasks: 3 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO PAYMENT SO THAT ICAN VIEW MY ORDERS AND PAYMENT RECEIPT |  |  |  |
| BV: 500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Text boxes for reports of placed orders and payments |  |  |  |

| User Story No : 30 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO REGISTER SO THAT I CAN LOGIN IN SCRUM FOOD APPLICATION |  |  |  |
| BV: 500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Text Boxes for Username, Password, Mobile Number, Email, Address, Phone Number Click on Registration button Send Registration successful message to the User |  |  |  |

| User Story No : 31 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A BUSINESS OWNER I WANT TO LOGIN SO THAT I CAN UPDATE VIEW ORDERS , THE PAYMENTS AND OTHER FOR DETAILS OF RESTAURANT |  |  |  |
| BV: 500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Text Boxes for Username, Password, Mobile Number, Email, Address, Phone Number Click on Login button Send successful message to the User |  |  |  |

| User Story No : 32 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO LOGIN SO THAT I CAN VIEW THE RESTAURANTS |  |  |  |
| BV: 500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Text Boxes for Username, Password, Mobile Number, Email, Address, Phone Number Click on Login button Send successful message to the User |  |  |  |

| User Story No : 33 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS AN ADMIN I WANT TO VIEW REPORTS SO THAT I CAN VIEW THE REGINAL REVENUES |  |  |  |
| BV:500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Generate the reports of orders and payment and calculate the revenue |  |  |  |

| User Story No : 34 | Tasks:2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO RAISE ISSUE SO THAT I CAN UPDATE THE COMPLAINTS OF DELIVERY AGENTS OR RESTAURANTS |  |  |  |
| BV: 500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: Enable to add comments for customer regarding the ratings or any complaints regarding the delivery boys or restaurants |  |  |  |

| User Story No : 35 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A DELIVERY BOY I WANT TO LOGIN SO THAT I CAN VIEW DELIVERY REPORT AND REVENUE GENERATED |  |  |  |
| BV: 500 |  | CP: 05 |  |
| ACCEPTANCE CRITERIA: Reports generated and view delivery report and view revenue generated |  |  |  |

| User Story No :36 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A RESTAURANT OWNER I WANT TO LOGIN SO THAT I CAN UPDATE THE LIST OF FOODS AND AVAILIBILITY |  |  |  |
| BV:500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: Text Boxes for Username, Password, Mobile Number, Email, Address, Phone Number Click on Login button Send successful message to the User and update the available food and status of availability |  |  |  |

| User Story No : 37 | Tasks: 2 |  | HIGHEST |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO UPDATE THE ADDRESS SO THAT I CAN UPDATE THE NEW ADDRESS AS CURRENT ADDRESS |  |  |  |
| BV: 500 |  | CP:02 |  |
| ACCEPTANCE CRITERIA: Modify the address and set as current location |  |  |  |

| User Story No : 38 | Tasks: 2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A ADMIN I WANT TO ACCESS THE FOOD APPLICATION SO THAT I CAN ADD OR DELETE THE DELIVERY BOY |  |  |  |
| BV:500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: Text box to update the addition or deletion of delivery boys |  |  |  |

| User Story No : 39 | Tasks:2 |  | Priority: HIGHEST |
| --- | --- | --- | --- |
| AS A REGIONAL ADMIN I WANT TOVIEW REPORTS SO THAT I CAN VIEW REGIONAL REVENUE |  |  |  |
| BV:500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: Generate reports region wise and view reports |  |  |  |

| User Story No : 40 | Tasks: 2 |  | Priority: MEDIUM |
| --- | --- | --- | --- |
| AS A CUSTOMER I WANT TO VIEW THE ORDER LIST SO THAT I CAN REORDER LAST ORDER |  |  |  |
| BV:500 |  | CP: 02 |  |
| ACCEPTANCE CRITERIA: Display order list and enable user to reorder if order is in the stock |  |  |  |

Question 3: What is Epic? Write two Epics?

Answer:

Epic is a large body of work that can be broken down into smaller pieces of work known as user stories. Epic can be said to be the set of User stories completed to achieve one Task. Too big to be completed in one sprint typically spans multiple sprints.   Helps organize and prioritize work. Keeps teams aligned with business goals. Makes tracking progress easier through tools like burn down charts or Kanban boards

Example:

- Registration

AS A CUSTOMER,

I WNT TOREGISTER IN SCRUM FOOD APP,

SO THAT I CAN LOGIN AND PLACE ORDER.

- Login-

AS A CUSTOMER,

I WANT TO LOGIN IN SCRUM FOOD APP,

SO THAT I CAN ORDER THE FOOD AND MAKE PAYMENTS.

Question 4: What is the difference between Business value and Complexity points?

Answer:

- Business Value: BV represent overall value that user story brings to the business or organisation.

- Assigned by product owners and stakeholder using techniques like Moscow, currency note technique.

- Helps to prioritise the backlog by focussing on what delivers the most value

- Can be influenced by factors like revenue potential, customer satisfaction, risk reduction, or market differentiation.

- Complexity Point: also known as story points, they estimate the effort, difficulty, or the time required to complete a task.

- Assigned by development team using technique like planning poker

- Helps in sprint planning and forecasting team velocity.

- Based on technical challenges, unknowns, and required resources not business impact.

| Attributes | Business Value (BP) | Complexity points (CP) |
| --- | --- | --- |
| Purpose | Prioritise by value to business/customer | Estimate effort and complexity |
| Assigned by | Product owner/ stakeholder | Development team |
| Influences | Backlog ordering | Sprint capacity planning |
| Based on | Strategic goals, ROI, Impact | Technical difficulty, time , risk |
| Unit | Often a scale (e.g., 1-100, 1-10) | Relative points(e.g., 1, 2, 3, 4) |

Question 5: Explain about Sprint?

Answer: A Sprint is a short, focused period of time (usually 1-4) during which a team works to complete a specific set of tasks or objectives. It’s most commonly used in Agile project management, especially in software development, but the concept can be applied to all kind of work.

Key features:

- Fixed time duration: a Sprint generally lasts for 1 to 4 weeks depending on the team’s preferences and project needs.

- Goal oriented: each sprint has a Sprint Goal, which is clear, achievable objective for that iteration.

- Incremental Delivery: by the end of the sprint, the team delivers the working increment of the product, adding value to overall product.

- Time-Boxing: Sprints are time boxed, meaning they cannot be extended. Any incomplete work is moved to backlog for future Sprints.

Sprint Activities-

- Sprint Planning: The team plans the sprint by selecting the items from the product backlog to work on and defining the Sprint Goal. Tasks are broken down into smaller and manageable pieces.

- Daily scrum (stand up): A short meeting to discuss what was done yesterday, what will be done today and any blocker or issues.

- Sprint Execution: the development team works collaborate to complete the tasks committed during sprint planning.

- Sprint Review: at the end of sprint, the team demonstrate the completed work to stakeholder to gather the feedback.

- Sprint Retrospective: the team reflects on the Sprint to identify areas for improvement and discuss what went well, what didn’t and how to improve in the next sprint.

Sprint Artefacts:

- Sprint Backlog: a subset of the product Backlog that the team commits to completing during the Sprint. Contain tasks and stories selected for the sprint.

- Product Increment: the output of Sprint which should be potentially shippable product increment

Benefits:

- Focused work: encourages team to work towards clear, short-term goal.

- Flexibility: Allows for iterative development and adaptation to changing requirement.

- Transparency: frequent reviews ensure stakeholders are kept informed of the progress.

- Continuous improvement; Retrospective foster an environment of ongoing enhancement in processes and teamwork.

What is sprint duration: 2 weeks your sprint value 12.

Sprint Duration: it refers to the fixed time allocated for a Sprint in the Scrum framework.

Sprint Value: it is the measurable benefit or the contribution that a sprint delivers to the overall project, stakeholder, or end-user.

What is Scrum Duration: one day, your scrum value 7.

Scrum value: topic or the team size or the numbers we are going to give to any issue or blocker while discussing during scrum call

| PBI(Product Backlog Item) | TASKS | WIP | DONE |
| --- | --- | --- | --- |
| Registration | 3 | 2 | 1 |
| Loin | 2 | 2 | 0 |
| Add restaurants | 3 | 2 | 1 |
| Order food | 3 | 0 | 3 |
| Make payment | 3 | 3 | 0 |
| Track delivery | 3 | 3 | 0 |
| Customer feedback | 3 | 3 | 0 |

- Fixed time duration: a Sprint generally lasts for 1 to 4 weeks depending on the team’s preferences and project needs.

- Goal oriented: each sprint has a Sprint Goal, which is clear, achievable objective for that iteration.

- Incremental Delivery: by the end of the sprint, the team delivers the working increment of the product, adding value to overall product.

- Time-Boxing: Sprints are time boxed, meaning they cannot be extended. Any incomplete work is moved to backlog for future Sprints.

Sprint Activities-

- Sprint Planning: The team plans the sprint by selecting the items from the product backlog to work on and defining the Sprint Goal. Tasks are broken down into smaller and manageable pieces.

- Daily scrum (stand up): A short meeting to discuss what was done yesterday, what will be done today and any blocker or issues.

- Sprint Execution: the development team works collaborate to complete the tasks committed during sprint planning.

- Sprint Review: at the end of sprint, the team demonstrate the completed work to stakeholder to gather the feedback.

- Sprint Retrospective: the team reflects on the Sprint to identify areas for improvement and discuss what went well, what didn’t and how to improve in the next sprint.

Sprint Artefacts:

- Sprint Backlog: a subset of the product Backlog that the team commits to completing during the Sprint. Contain tasks and stories selected for the sprint.

- Product Increment: the output of Sprint which should be potentially shippable product increment

Benefits:

- Focused work: encourages team to work towards clear, short-term goal.

- Flexibility: Allows for iterative development and adaptation to changing requirement.

- Transparency: frequent reviews ensure stakeholders are kept informed of the progress.

- Continuous improvement; Retrospective foster an environment of ongoing enhancement in processes and teamwork.

Question6: Explain Sprint Backlog and Product Backlog?

Answer:

Product Backlog: It is the key artefacts in the scrum framework, representing a prioritised list of work items that the scrum team needs to complete to deliver a product or project. It serves as a single source of truth for all features, enhancement, bug fixes, technical requirements, and other deliverables required to achieve the project goal.

Key characteristics

- Dynamic and Evolving: The Product backlog is not static; it evolves over time based on changing requirement, market needs or feedback from stakeholders

- Prioritized: Items are ordered by priority, with the most important and valuable items placed at the top. These usually addresses first in Sprint

- Refined: items in the backlog are regularly refined or “groomed” to ensure they are ready for future sprints.

- Owned by Product Owner: The product owner is responsible for maintaining the Backlog, ensure it align with the product vision and stakeholders need.

- Detailed as needed: Items near the top (high priority) are more detailed while those further down can remain less defined until they approach implementation.

Benefits:

- Clarity and Focus: provides a clear roadmap of work to be done.

- Transparency: keeps the team and stakeholder aligned on priority.

- Flexibility: Adapts to changing requirement or feedback.

- Facilitates Planning: helps team plan sprint effectively by pulling items from the top.

Sprint backlog: the sprint backlog is the key artefact in the scrum framework that      presents the subset of product backlog items selected for a specific sprint, along with the plan to deliver them. It is the Teams working-to-do list during the sprint and includes all the tasks required to meet the Sprint Goal.

Key characteristics

- Subset of Product Backlog:  The sprint backlog is derived from the product backlog during sprint planning. It contains only the items team commits to completing during the current sprint.

- Owned by the Development Team: the development team is responsible for managing and updating the sprint backlog throughout the sprint.

- Detailed and clear: Each backlog item is broken into smaller tasks with sufficient detail for the team to understand and work on them.

- Dynamic but Stable: the sprint backlog may evolve slightly as tasks are refined, but the scope of sprint goal should not change.

- Linked to the sprint goal:  Every item in the sprint backlog contributes directly to achieve sprint goal.

Benefits:

- Focus: provide team with clear and actionable plan for the sprint.

- Transparency: Helps everyone understand what the team is working on and the progress being made.

- Adaptability: allows the team to manage their work dynamically while maintain alignment with the Sprint Goal.

- Accountability: Ensure teams take ownership of their commitments and progress.

Question 7: What is Impediments log?

Answer:  An impediments Log in Agile is a tool or document used to track and manage obstacle, blockers, and issues that hinder the progress of agile team during a project. It helps ensure that impediments are identified, prioritise and address promptly to maintain teams productivity and alignment with the project goal.

Key Characteristics:

- Centralised Tracking: A single place to record and monitor all impediments affecting team.

- Transparency: Make impediments visible to all team members, the scrum master and stakeholders.

- Prioritization: Impediments are prioritised based on their impact on sprint Goal or team performance.

- Accountability: Each impediment is assigned an owner responsible for resolving it.

5.     Dynamic Nature: the log evolves as new impediments are identified, and existing ones are resolved.

| ID | Description | Reported by | Impact | Owner | Status | Resolution date |
| --- | --- | --- | --- | --- | --- | --- |
| 001 | Build server is down | Developer D | Cannot test new code | Scrum master | In Progress | NA |
| 002 | Lack of clarity on Requirements |  | Feature development blocked | Product owner | Resolved | 20-8-2025 |

Question 8: Explain Velocity of the team?

Answer:  Team velocity is a measure of the amount of work a team can take during a single sprint and is the key metric in scrum. When you complete a sprint, you will total the points for all fully completed user stories and over time find the average number of points you complete per sprint.

So velocity means how many Complexity points (CP) is covered in this sprint and if team has covered 8 CPs hence Velocity of team is 8.

Question 9: Draw Sprint Burn Charts and Product Burn Down Charts?

Answer: Sprint Burn Charts – It is visual tool used in Agile project management to track the progress within a sprint. It helps teams understand how much work remains and whether they are on track to meet their sprint goal.

Types of Sprint Burn charts-

- Sprint Burn charts- Tracks the remaining work overtime during a sprint. Shows a download slope as tasks are complete. Key goal is to ensure the team is completing tasks at a pace to finish the sprint on time.

- Sprint Burn up Chart- Tracks the completed work overtime during a sprint. Shows an upward slope as more tasks are completed. Key goal is to monitor progress towards the sprints total scope.

Product Burn down Chart- it is a visual tool used in agile management to track the progress of a project towards completing all works (usually in the form of user stories or tasks) in the product backlog. It helps team and stakeholders monitor the remaining work overtime, providing a clear picture of whether the project is on track to meet its deadline and goals.

Question 10: Explain about Product Grooming?

Answer: Product grooming also known as Backlog refinement is a collaborative agile practice aimed at preparing and prioritising the product backlog to ensure that it is well organised, up-to-date, and ready for upcoming sprints.

The goal include Clarify Requirement, prioritize work, Estimate Efforts, Remove obsolete Items, and break down large items.

Benefits include: Improved clarity, Smoother Sprint planning, increase productivity, Focus on value.

Question 11: Explain role of Scrum Master and Product Owner?

Answer:

Scrum Master: The Scrum Master is accountable for establishing scrum as defined in the Scrum Guide. They do this by helping everyone understand the scrum theory and practice, both within scrum team and the organisation. The scrum master is accountable for the Scrum team’s effectiveness. They do this by enabling the scrum team to improve its practices, within the scrum framework. The day-to-day activity of the scrum master involves servant leadership where they are involved in performance planning, coaching, and self-organisation, removing obstacles, resolving conflicts and serving the team. The scrum master ensures project success, by assisting the product owner and the team in using the right scrum process for creating the end product and establishing the Agile principles.

Key Responsibilities:

- Facilitating Scrum events: organise and ensure the effectiveness of daily stand-ups, sprint planning, reviews and retrospective.

- Coaching the team: Guide the development team in adopting an improving agile practices. Mentor the team on self-organisation and cross functionality.

- Promoting Collaboration: Foster communication between team member, the product owner and the stakeholder.

- Shielding the Team: Protect the team from external distraction and interruptions.

- Ensuring continuous improvements: Help the team inspect and adapt process to improve efficiency and quality.

Product owner: Product owner is accountable for maximising the value of the product resulting from the work of the Scrum team. The product Owner is one person not a committee. The product owner may represent the need of many stakeholders in product Backlog. Those wanting to change Product backlog can do so by trying to convince the Product owner. The first responsibility of product owner is customer satisfaction and this they carry out by ensuring that customer requirements are given priority and there is transparency between development team and stakeholders. The product owner interacts with user and customer, stakeholder, development team and the scrum master to deliver a successful product.

Key Responsibilities:

- Defining the Vision: clearly articulate the products goal and how they align with business objective.

- Managing the Product Backlog: create, refine, and prioritize backlog items. Ensure the backlog items are well defined, clear, and ready for development.

- Prioritize work: Decide what the team work on next, based on value, customer need, and strategic goal.

- Stakeholder Collaboration: communicate with stakeholders to gather requirements and share progress. Act as the primary liaison between the team and business.

- Acceptance of work: define and agree on acceptance criteria for backlog items. Review and accept completed work to ensure it meets requirement.

- Maximising value: Focus on delivering features and functionalities that provide highest value to customer and business.

Question 12: Explain all meetings conducted in Scrum project?

Answer:

- Sprint Planning Meeting: This meeting begins with product owner. The PO explain their vision and how the team should go about completing this step of the project. During this meeting, team member decide the amount of work they can complete within the sprint. This is also when the team moves work from product Backlog to the Sprint backlog. This step requires a lot of planning and can take several hours for the group to decide on a finalised sprint.

- Daily Scrum meeting: From the planning meeting we move into daily scrum meetings. Every single day for 15 minutes, the team gather to report any issues or progress on their tasks. Though brief, this meeting is an essential part of scrum process .it is designed to keep all group members on track in a cohesive manner. Normally the PO is present during all daily scrum meetings to assist in any way. Her they must answer three questions

a. What did you in this scrum?

b. what task will you work in next scrum?

C .Any challenges/impediments?

- Sprint Review Meeting: The meeting is used to showcase a live demonstration of the work completed. During this meeting the product owner, scrum master and stakeholders are present to review the product and suggest changes or improvements. They will see the Velocity means how many CP is covered in this sprint burn down chart.

- Sprint Retrospective Meeting: this meeting is held to facilitate a team’s reflection on their progress. The team speaks openly about their organizational concerns and teamwork. During this meeting, dialogue should remain friendly, non-judgmental and impartial. This review session is a key part of team building and development and it’s also very important for future scrum projects. In this meeting team will discuss about challenges faced and come up with lesson learned. We can use these lesson learned in Sprint planning meeting to select user stories for next sprint.

- Backlog refinement Meeting: in this team member focus on the quality and skill of work involved during sprint. This meeting is necessary for business owner to connect with development team and is used to assess the quality of the final product. This meeting involves important reflection on team backlog.

Question 13: Explain Sprint Size and Scrum Size?

Answer:

Sprint Size: Sprint size refers to amount of work that a scrum team commits to completing during a single sprint. It is typically measured in terms of:

- Story Points: A relative measure of complexity, effort, or size for backing items.

- Hours: the estimated time required to complete task.

- Number of tasks/User stories: A count of items that the team plans to complete.

Scrum Size: scrum size refers to composition and capacity of the scrum team,                         encompassing the number of team members, their role, and their collective ability to deliver    work within a sprint. While there is no strict rule for scrum team size, certain guidelines exist to ensure efficiency and collaboration.

Question 14: Explain Definition of Ready (DOR) and Definition of Done (DOD)?

Answer:  Definition of Ready (DOR):  it is a set of criteria that a user story or product item   backlog must meet before it can be considered “Ready” for the team to start working on it during a sprint. Essentially, it is a checklist that ensure that the backlog item is sufficiently clear, detailed and understood by the team so that they can begin development without any ambiguity or uncertainty.

Common criteria for DOR include Clear Acceptance, Criteria, well-Defined User story, Dependencies Identified, Estimate, Prioritized, No Blockers, and Stakeholders Availability.

Definition of Done (DOD): It is a set of criteria that must be met for a product backlog item e.g., User story, feature or an entire sprint to be considered complete. The DOD ensure that all work is fully finished, meets quality standards, and is ready for release or deployment. It provide clarity on what constitute “Done”, reducing ambiguity and ensuring consistency in quality across the Scrum team.

Common criteria for DOD include Code Complete, Peer Review, Automated Tests, Manual Testing, No critical Bugs, Integrated, Documentation complete, Performance Standard met, No pending tasks, Reviewed by product owner, Ready for Release.

Question 15: Explain Prioritization technique and MVP?

Answer:  Prioritization technique In Agile are methods used to determine the order in which work items should be completed based on their value, impact and urgency. These technique help Product owner and team focus on most important tasks, ensuring the delivery of maximum value to stakeholder.

- MoSCoW Method-it stand for must have, should have, could have, would have. This technique categorise work into 4 priority levels:

Must have: critical for success of project and essential for release.

Should have: important but not critical, can be delayed without affecting delivery.

Could have: Desirable but not necessary. Can be included if there is time and resource.

Would have: Feature that are not necessary for the current project or sprint but can be considered in future requirements.

- 100-point method: in this technique each member is given 100 point to allocate across different feature or user stories based on their perceived importance or value.

The idea is to distribute the point to indicate priority with more points allocated to higher-priority items.

- Value VS. Complex matrix: this technique help prioritize work by evaluating the value a feature delivers against the effort required to implement it.

The matrix is divided into 4 quadrants-

High value, low effect: prioritize these items as they provide maximum return for minimal effort.

Low value, low effort: consider doing these quickly if there is spare capacity

Low value, high effort: avoid prioritising these unless there is a strong reason.

- Cost of Delay: it refers to potential loss of revenue, opportunities, or business value that results from delaying a feature or decision. This technique will help prioritize feature that will have most impact on revenue or market opportunity if delayed.

Minimum Viable Product: MVP is a concept in product development that refers to simplest version of a product that can be released to user, with just enough feature to satisfy early adopters. The MVP designed to gather feedback, test hypothesis, and validate the products core assumption with minimal effort and resources, before further development and investment.

Key Characteristics:

Basic functionality: the MVP contain the core functionality that addresses the most critical user needs. Additional feature or enhancement are excluded until the product proves its value.

Quick launch: the MVP is released quickly to gather early feedback rather than waiting for fully featured product.

User feedback: The MVP is built to connect the insights from user about what works, what does not and what features they value most.

Focus on learning not Perfection: the goal of an MVP is not to create a polished product but to learn what resonate with user. The initial product may be rough, but should still deliver the primary value.

Iterative development: Based on the feedback from MVP, team can iteratively improve the product, adding new features and refining existing ones.

Benefits of MVP includes, cost effectiveness, and reduced time to market, real world validation, early user engagement, iterative improvement.

Question 16: Differentiate between Business  Analysts and Product Owner?

Answer:

Business Analysts is a professional who plays a key role in building bridge between business needs and technology solutions. They work closely with stakeholders including business leaders, project manager, developers and other team members, to understand the organisation need and translate them into technical requirement for product development or process improvement. The Basic primary goal is to ensure that the business requirement are clearly defined, understood and met through effective solutions.

Product Owner: PO is a key role in Agile framework especially in Scrum, responsible for defining and prioritizing the features, functionalities and deliverables of a product. The Product Owner act as a primary Liaison between stakeholder (such as customers, Business team and executives) and the Scrum team (which include developers, testers and scrum masters).

Question 17: Prepare a sample Resume of 3 yrs.     Experience   Product owner?

Answer:

Name: Priyanka

Mob Num: 966346660

Email: Priyankasingh4477@gmail.com

Summary

Dynamic Product Owner at Trans Union with proven track record in Agile methodologies and user story creation. Successfully prioritized backlogs to align with business goal, enhancing team productivity and delivering High-quality products. Adapt at collaborating with cross-functional teams, I excel in strategic planning and stakeholders engagement to drive project success.

Skill Highlights

| - Agile Methodology - User Story creation | - Agile Framework - Story planning |
| --- | --- |

Experience

Product Owner - 09/2022 to 05/2025

Trans Union – Bangalore, India.

- Managed Backlog Prioritization, ensuring alignment with business goal and stakeholders expectation.

- Implemented Agile Methodologies ti increase team productivity and enhance overall project outcome.

- Collaborated with cross functional teams to develop high-quality product that met customer need.

- Developed comprehensive roadmap outlining the product vision, goal, and milestone for successful execution.

Education

Bachelor of engineering (IT)  : 05/2013

Priyadarshani collage of engineering Nagpur