Nurturing Process – Waterfall Deliverables – Part -1/2- V2D2 August 2024 Waterfall Model Documents

Document 1- Business case document template

➢ Why is this project initiated?

This project is initiated to digitize the report verification process in branches. Currently, Branch staff manually check, sign and file reports physically. This leads to delays, lack of transparency, human errors, and storage issues.

By introducing the E-Call Back application, reports can be reviewed and approved online, ensuring accuracy, audit compliance, and operational efficiency.

➢ What are the current problems?

- Time-consuming manual verification process.

- Physical loss or misplacement of reports

- Delays in communication between departments.

- No centralized audit trail for reports checks.

- Resource wastage in printing, filing, and maintaining records.

- Inconsistent adherence to timelines due to manual tracking.

➢ With this project how many problems could be solved?

The E-Call Back project can solve multiple issues:

- Elimination the need for physical verification

- Provide centralized digital access to all reports

- Enable real-time tracking of reports status.

- Improve accuracy and transparency

- Enhance audit readiness

- Save time and operation costs.

➢ What are the resources required?

Project Manager, Business Analyst, IT Developers and Testing Team

Infrastructure: Backend server, secure storage and integration with core banking/reporting system

Software Licenses for development and deployment tools

Training materials and sessions for end-users

Support and maintenance team post-GO Live

➢ How much organizational change is required to adopt this technology?

- Moderate change: Basic training needed for users at branches

- Minimal infrastructure change as the solution integrates with existing systems

- Standard guidelines need to be updated

- A short transition period during pilot and final rollout

➢ Time frame to recover ROI?

The ROI can be recovered with in 6 to 12 months, depending on:

- Reduction in physical printing/stationery costs

- Increased efficiency and time saved by branch staff

- Reduction in compliance and audit penalties

- Improved operational performance

➢ How to identify Stakeholders?

Stakeholders can be identified using:

- Stakeholder analysis matrix

- Interviews and workshops with key departments

- Process flow analysis to determine who is impacted

- Key Stakeholders include:

Branch Operation Team

Internal Audit Team

Compliance Department

IT & Software Development

Project Sponsor/Top Management

End-users (Branch Managers and Staffs)

Document 2: BA Strategy

BA Approach Strategy for the given scenario using the Waterfall Methodology.

1.What Elicitation Techniques to Apply: To gather detailed and structured requirements, the following elicitation techniques used

- Document Analysis: Study existing manual report-checking processes and compliance guidelines

- Interviews: With branch operations, audit and IT teams.

- Workshop: Conduct requirement gathering workshops with multiple stakeholders

- Observation: Understand how current manual report checking is handle at branches.

2.How to do Stakeholder Analysis (RACI/ILS Matrix)

| Task/Activity | Branch Ops Team | Internal Audit | Compliance Dept | IT & Software Dev | Project Sponsor/Mgmt |
| --- | --- | --- | --- | --- | --- |
| Requirement Gathering | C | C | C | R | A |
| System Design & Development | C | I | I | R/A | I |
| Testing &UAT | C | I | I | R | A/R |
| Compliance & Audit Input | I | R | R | I | C |
| Data Security Setup | I | C | R | R | A |
| Training & User Onboarding | R | I | I | C | A/R |
| Daily Report Verification | R | I | I | I | A/R |
| Performance Monitoring | R | I | I | I | A/R |
| Project Approval/Funding | I | I | I | I | A/R |
| Change Requests/Enhancements | C | C | C | R | A |

For each activity, assign

R(Responsible): Who performs the work

A(Accountable): Who is ultimately answerable (only one per task)

C(Consulted): Who provides input

I(Informed): Who is kept up-to-date

ILS (Influence, Legitimacy, Support) Matrix to assess stakeholder impact and support level.

3. What document to write

- Business Requirement Document (BRD)

- Functional Specification Document (FSD/FRD)

- Use Case Diagrams/Process Flows

- Gap Analysis Document

- Requirement Traceability Matrix (RTM)

- UAT Test Cases/Scenarios

- Change Request Log

- Client Project Acceptance Form (Post UAT)

4. What Process to follow to Sign off on the Documents: Sign off can be taken on BRD/FSD /SRS as these primary and important documents sign off can be taken by using E-mail confirmation from client.

- Share the draft BRD/FSD with key stakeholders

- Conduct BRD review meetings and gather feedback

- Incorporate necessary changes and submit final version.

- Get formal approval via email or sing -off form

- Ensure traceability from BRD to FSD to development to UAT

5.How to take Approvals from the Client: Review with stakeholders---Validate—Submit for approval. Keep them informed and get continuous feedback

- BRD and FSD Signoff: Required before development starts

- UAT Signoff: Taken after successful testing

- Final Project Acceptance Form: Signed by Project Sponsor

6 What Communication Channels to establish n implement:

- Regular meetings/Daily Stand -ups (Internally with IT teams)

- Weekly status meeting (with stakeholders)

- Status Emails (Shared every Friday to all stakeholders)

- Use of collaboration tools: MS Teams, Outlook, Excel Tracker

7 How to Handle Change requests Change request form,

DO Impact analysis, Approval process, Documentation.

- Maintain Change Request Log

- Analyse impact on scope, timeline, and cost

- Update BRD/FSD and RTM accordingly

8 How to update the progress of the project to the Stakeholders:

- Weekly status Reports including:

Completed Activities

Pending tasks

Risks and mitigation

Change requests

- Share reports through email and Teams groups

- Monthly Review meeting /Committee meeting

9 How to take signoff on the UAT-Client Project Acceptance Form:

1.UAT Preparation: Prepare UAT test cases and scenarios based on finalized requirements. Set up the UAT environment, sample data, and ensure users (Branch Operations, Audit team) are ready testing.

2.Conduct UAT: Client -side users (such as Branch Ops and Audit Teams) execute the test cases to validate system functionality. Observations and issues are noted during the process.

3.Log & Fix Issues: Defects identified during testing are logged in a defect tracking sheet or system. Each defect is prioritized, assigned for fixing, and tracking until resolution.

4.Final Review Meeting: Hold a final meeting with business, audit, and IT teams to demonstrate fixes, validate the working solution, and ensure no open issues remain.

5, Obtain UAT Sign-off: Once all test cases pass and defects are resolved, collect sign-off through a formal UAT sign-off Email or Form from client Stakeholders.

6. Obtain Final Client Acceptance: Prepare the client Project Acceptance Form as the final approval document. The indicates full client satisfaction and approval to move the project to production/live use.

Document 3- Functional Specifications

| Project Name | E-Call Back Application |
| --- | --- |
| Customer Name | ABC Bank |
| Project Version | 1 |
| Project Sponsor | ABC Bank |
| Project Manager | Aman Verma |
| Project Initation date | 05-Jul-25 |

Functional Requirement specifications:

| Req ID | Req Name | Req Description | Priority |
| --- | --- | --- | --- |
| FR0001 | Login | User should be able to securely log into the E-Call back application using AD id creds | 10 |
| FR0002 | Report View | User should be able to view daily/monthly/fortnightly reports assigned to their branch | 9 |
| FR0003 | Report Upload | User Should be able to Upload daily transaction report done by branch | 9 |
| FR0004 | Remarks Entry | User should be able to enter remarks against reports for tracking Compliance | 9 |
| FR0005 | Dashboard Access | Regional/Admin users should have a dashboard with branch-wise Compliance summary | 8 |
| FR0006 | Audit Trail | Every action taken by a user must be logged for audit purpose | 9 |
| FR0007 | Role-Based Access | Different views and access for Branch as per role checker/maker | 10 |

Document 4- Requirement Traceability Matrix

| Req ID | Req Name | Req Description | Design | D1 | T1 | D2 | T2 | UAT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FR001 | Login | User Login functionality | Yes | Pending | No | Yes | Yes | Yes |
| FR0002 | Report View | Report viewing functionality | Yes | Yes | NO | Yes | Yes | Yes |
| FR0003 | Report Upload | Report upload capability | Yes | Yes | YES | Yes | Yes | Yes |
| FR0004 | Remarks Entry | Remarks entry for compliance | Yes | Pending | No | Yes | Yes | Yes |
| FR0005 | Dashboard Access | Dashboard for compliance summary | Yes | NO | No | Yes | Yes | Yes |
| FR0006 | Audit Trail | User audit trail logging | Yes | Yes | Yes | Yes | Yes | Yes |
| FR0007 | Role-Based Access | Role-based access control | Yes | Yes | No | Yes | Yes | Yes |

Document 5- BRD Template

Contents

1.Document Revision………………………………………………………………………….....8

2.Approvals……………………………………………………………………………………………8

3.RASCI Chart for the Document…………………………………………………………….9

Codes Used in RASCI Chart…………………………………………………………….....9

RASCI…………………………………………………………………………………………….…9

4.Introduction ……………………………………………………………………………….……...9

4.1 Business Goal………………………………………………………………………………10

4.2 Business Objective……………………………………………………………….………10

4.3 Business Rules……………………………………………………………….……………10

4.4 Background…………………………………………………………………….……………10

4.5 Project Objective………………………………………………………………………….10

4.6 Project Scope……………………………………………………………………………………10

4.6.1. In Scope Functionality…………………………………………………………….10

4.6.2 Out Scope Functionality……………………………………………………………10

5.Assumptions…………………………………………………………………………………………11

6.Constraints……………………………………………………………………………………………11

7.Risks…………………………………………………………………………………………………….11

Technological Risks………………………………………………………………………………….11

Skills Risks……………………………………………………………………………………………….11

Political Risks……………………………………………………………………………………………11

Business Risks………………………………………………………………………………………….11

Other Risks……………………………………………………………………………………………….12

8. Business Process Overview……………………………………………………………………13

8.1 Legacy System (AS IS) ……………………………………………………………………….13

8.2 Proposed Recommendations (TO-BE) ……………………………………… ………13

9.Business Requirements………………………………………………………………………….14

10. Appendices………………………………………………………………………………………….14

10.1 List of Acronyms………………………………………………………………………….14

10.2 Glossary of Terms……………………………………………………………………….14

10.3 Related Documents…………………………………………………………………….14

<E-Call Back Application>

- Document Revisions

| Date | Version Number | Document Changes |
| --- | --- | --- |
| 01/06/2025 | 0.1 | Initial Draft |
| 15/06/2025 | 0.2 | Added Functional Requirements |
| 20/06/2025 | 0.3 | Incorporated Review Comments and Stakeholders |
| 25/06/2025 | 0.4 | Update RACI Matrix, Approval Section, and Glossary |
| 07/07/2025 | 1 | Final Version Approved and Signed off |

This section helps track all updates made to the document, including drafts, revision, and approvals.

2.Approvals

| Role | Name | Tile | Signature | Date |
| --- | --- | --- | --- | --- |
| Project Sponsor | Mr. Rajesh Nair | Chief Operation Officer | Yes Signed | 07/07/2025 |
| Business Owner | Mr. Vibhu Rao | Branch Operation Head | Yes Signed | 07/07/2025 |
| Project Manager | Mr. Kunal Mehra | IT Delivery Manager | Yes Signed | 07/07/2025 |
| Business Analyst | MS. Vibha Prasad | BA | Yes Signed | 07/07/2025 |
| System Architect | Mr. Arvind Shah | Senior Solution Architect | Yes Signed | 07/07/2025 |
| Development Lead | Mr. Sanjay Rao | Java Led Developer | Yes Signed | 07/07/2025 |
| User Experience Lead | Ms Priya Jain | UI/UX Lead | Yes Signed | 07/07/2025 |
| Quality Lead | Ms. Sweta Agarwal | QA/Testing Manager | Yes Signed | 07/07/2025 |
| Content Lead | Ms. Richa Verma | BA Documentation | Yes Signed | 07/07/2025 |

3.RACI Chart for This Document: The RACI chart identifies the persons who need to be contacted whenever changes are made to this document. The codes that appear in a RACI chart, used here to describe the roles played by team members and stakeholders in the production of the BRD. They are adapted from charts used to a assign roles and responsibilities during a project.

The following describes the full list of codes used in the table:

*Authorize document

R –Responsible (owns the work/task)

A –Accountable (final decision-maker)

S – Supports document (document support)

C—Consulted (provides input)

I---Informed (kept in the loop)

| Role | Name | Responsibility |
| --- | --- | --- |
| Project Sponsor | Mr. Rajesh Nair | Accountable |
| Business Owner | Mr. Vibhu Rao | Accountable |
| Project Manager | Mr. Kunal Mehra | Responsible |
| Business Analyst | MS. Vibha Prasad | Responsible |
| System Architect | Mr. Arvind Shah | Consulted/Support |
| Development Lead | Mr. Sanjay Rao | Consulted/Support |
| User Experience Lead | Ms Priya Jain | Consulted/Support |
| Quality Lead | Ms. Sweta Agarwal | Informed |
| Content Lead | Ms. Richa Verma | Informed |
| QA/Testing Manager | Mr. Dhruv Kohli | Informed/Support |
| UI/UX Lead | Mr. Akshy Kumar | Informed/Support |
| Java Lead Developer | Mr. shyam | Informed/Support |
| IT Delivery Manager | Mr. Sumit | Consulted/Support |

4. Introduction

4.1. Business Goals: The goal of this project is to design, develop and implement a secure digital application to replace the manual report verification processing ensuring compliance, improving operation efficacy and reducing the risk of error or fraud.

The goal is to eliminate physical movement of reports and enable staff to verify branch reports through a secure digital platform ---The E-CALL Back application

4.2. Business Objectives: To provide an IT Solution for:

- Online checking of branch-wise reports by designated users BOD/EOD reports

- Reducing paper-based report movement and loss risks

- Increasing compliance and timely completion of callback processes

- Enabling secure login with ADID credentials

- Providing role-based access(maker/checker)

- Generating dashboards for branches/regional/admin/staff for compliance tracking

- Maintaining audit trails of every action

4.3. Business Rules

- Only authenticated users can access the system via ADID credentials

- Role-based access control will apply (e.g. checker, maker & BM)

- Reports must be updated and reviewed in a same day as per report type BOD/EOD

- Every action must be logged in the audit trail

- Dashboard data should reflect real-time status of callbacks completion

4.4. Background

Previously, report verification was handled manually by staff with physical reports generated by branch. This was time-consuming, prone to error, and delayed audit readiness. The E-Call Back application was proposed to address this inefficiency by enabling digital verification by staff, thus improving accuracy, traceability, cost effective and compliance.

4.5. Project Objective

To develop and implement a branch wise E-Call Back application that:

- Enables seamless online report verification

- Eliminates manual errors and physical handing

- Provides real-time status of reports acknowledgement

- Provide pending reports details

- Improves user accountability through audit trails

- Ensures compliance through dashboard tracking

- Enhances user experience through an intuitive UI

4.6. Project Scope

4.6.1. In Scope Functionality

- Secure login using Active Directory (ADID) credentials

- Upload and view/review daily/weekly/monthly reports

- Role based access(maker/checker/Bm/admin)

- Remarks entry for report tracking

- Dashboard for regional/admin users/Branch user to monitor pending reports and compliance

- Audit trail logging for every action

- UAT testing and validation by branches

- Report status updates and showing pending reports for completion

- Different colour code for reports updating/reviewed/pending/no report mark

4.6.2. Out Scope Functionality

- Integration with third-party audit tools

- Physical document uploads/scanning

- Legacy system support (manual form processing)

5.Assumptions

- All user will have ADID credentials for authentication

- Branch users will have required hardware (computer, internet access)

- Staff will be trained before the rollout

- Reports will be assigned in system as per standard compliance process

- Management will support adoption across branches

6. Constraints

- Internet dependency across all branches

- Limited tech-savvy staff at some branches may delay adoption

- UAT feedback cycle is short due to regulatory deadlines

- Application rollout limited to Windows desktop

- Changes must be approved by compliance team before implementation

7. Risks

| Risk | Type | Likelihood Impact |  | Strategy |
| --- | --- | --- | --- | --- |
| Dealy in staff adoption due to lack of training | Operational | Medium | High | Mitigate: Conduct training sessions and provide manuals |
| Application downtime during month-end | Technical | High | High | Avoid: Schedule maintained during non-peak hours |
| Misuse of role-based access rights | Security | Low | Medium | Mitigate: Enforce strict access control and regular audits |
| Dealy in report uploads from branches | Operational | High | Medium | Transfer: Escalate to branch manager for follow-up |
| User resistance to shift from manual to digital | Change Management | Medium | Medium | Accept: Handle gradually with awareness and incentives |

Technological Risks

- Potential server downtime during peak banking hours.

- Integration issues with existing Core Banking Systems (CBS)

- Compatibility limitations with older operating systems in branches.

Skills Risks

- Limited technical knowledge of branch staff may delay onboarding.

- Lack of familiarity with the E-Call Back system among senior employees

- Dependence on IT support for basic troubleshooting

Political Risks

- Delays in approvals from internal committees or regulatory bodies.

- Organizational restructuring may deprioritize the project

- Union resistance to digital transformation

Business Risks

- Non-compliance if digital verification is delayed or fails

- Operational disruption if system fails during audits

Requirements Risks

- Misinterpretation of mandatory Vs optional reports fields

- Missed updating of report and marked hardcopy without Approval

- Frequent compliance changes not captured in requirements

Other Risks

- Cybersecurity threats like phishing or credential leaks

- Data synchronization issues in branches

- Resistance from staff preferring manual processes

8. Business Process Overview

8.1. Legacy System (AS-IS)

- Reports were printed physically by branches.

- Manual cross-verification done using physical reports/checklist

- Compliance team physically verify reports during Audit

- Documentation stored in files and cabinets

- Tracking delays while searching for reports during audit.

- Wastage of Papers

- Mis out/Missing of reports during filing/binding.

8.2. Proposed Recommendations (TO-BE)

- Reports uploaded by branch staff on E-call back application

- ADID-based login ensures secure access

- Each branch uploads reports, verified by checker and add comments if required.

- Compliance team monitors dashboard in real time

- Role-based access ensures that only designated users perform maker/checker functions.

- Data retrieval easy for compliance team.

9. Business Requirements: The business requirement for the E-call Back system were gathered through interviews, documentation analysis, and workshops with keys stakeholders such as branch staff, compliance officers, and reginal heads. These requirements aim to eliminate manual report verification at branch and replace it with digital checking of reports by branch staff thru E-Call back application

| Req ID | Req Description | Priority | Functional Area |
| --- | --- | --- | --- |
| FR001 | User should be able to securely log into the E-Call back application using AD id creds | High | Authentication/Login |
| FR0002 | User should be able to view daily/monthly/fortnightly reports assigned to their branch | High | Report Viewing |
| FR0003 | User Should be able to Upload daily transaction report done by branch | High | Report Upload |
| FR0004 | User should be able to enter remarks against reports for tracking Compliance | Medium | Compliance Remarks |
| FR0005 | Regional/Admin users should have a dashboard with branch-wise Compliance summary | High | Dashboard & Monitoring |
| FR0006 | Every action taken by a user must be logged for audit purpose | High | Audit/Logging |
| FR0007 | Different views and access for Branch as per role checker/maker | High | Access Control/Security |

10. Appendices

10.1. List of Acronyms

| Acronym | Full Form |
| --- | --- |
| AD | Active Directory |
| UAT | User Acceptance Testing |
| UI | User Interface |
| UX | User Experience |
| RTM | Requirement Traceability Matrix |
| BRD | Business Requirement Document |
| MIS | Management Information System |
| QA | Quality Assurance |

10.2. Glossary of Terms

| Term | Defination |
| --- | --- |
| E-Call Back | A digital system to verify and validate daily reports online instead of manual review |
| Role-Based Access | Access granted to users based on their job roles (e.g. checker, maker) |
| Audit Trail | A log of user actions to ensure traceability and security compliance |
| Dashboard | A summary screen ensures traceability and security compliance |
| Compliance | Adherence to internal controls and regulatory standards |

10.3. Related Documents

| Document | Description |
| --- | --- |
| Project Charter | High-level summary of the E-Call Back project |
| Stakeholders Interview Summary | Notes from sessions with branch managers and IT heads |
| RTM Document | Tracks requirements through design, testing and UAT |
| Approval Sheet | Contains sign-off from key stakeholders |
| Workshop Notes | Input gathered during elicitation sessions with end users |