- Write about Agile Manifesto?

- Four main Values

- Individuals and interactions over processes and tools

- Working software over comprehensive documentation

- Customer collaboration over contract negotiation

- Responding to change over following a plan

Twelve Principles of Agile Software

- Satisfy the customer through early and continuous delivery of valuable software.

- Welcome changing requirements, even late in development. Agile processes harness change for the customer's competitive advantage.

- Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale.

- Business people and developers must work together daily throughout the project.

- Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done.

- The most efficient and effective method of conveying information to and within a development team is face-to-face conversation.

- Working software is the primary measure of progress.

- Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.

- Continuous attention to technical excellence and good design enhances agility.

- Simplicity--the art of maximizing the amount of work not done--is essential.

- The best architectures, requirements, and designs emerge from self-organizing teams.

- At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.

- Write minimum 40 User stories and their Acceptance Criteria along with their BV and CP?

- Below are some of the user stories:

SPRINT-1: USER REGISTRATION AND LOGIN

USER STORY NO: 01; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO REGISTER IN SCRUM FOODS SO THAT I CAN PLACE ORDERS BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Registration screen with fields: Name, Email, Password, Mobile - "Register" button - Error message if fields are empty - Success notification on valid registration

USER STORY NO: 02; Tasks: 2; Priority: HIGHEST. AS A DELIVERY BOY I WANT TO REGISTER IN SCRUM FOODS SO THAT I CAN DELIVER ORDERS BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Registration screen for Delivery Boy - Fields: Name, ID, Mobile, Email, Address - Validation and success message

USER STORY NO: 03; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO LOGIN TO MY ACCOUNT SO THAT I CAN ACCESS MY DASHBOARD BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Login screen with Email and Password - "Login" button - Error on wrong credentials - Redirect to dashboard on success

USER STORY NO: 04; Tasks: 2; Priority: MEDIUM. AS A DELIVERY BOY I WANT TO LOGIN TO MY PROFILE SO THAT I CAN VIEW DELIVERY ASSIGNMENTS BV: 200; CP: 01. ACCEPTANCE CRITERIA: - Login form - Success login leads to Delivery Dashboard - Session tracking

USER STORY NO: 05; Tasks: 2; Priority: HIGHEST. AS AN ADMIN I WANT TO LOGIN TO ADMIN PANEL SO THAT I CAN MANAGE USERS AND ORDERS BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Admin login screen - Email + Password fields - Redirect to Admin Panel

SPRINT-2: MENU BROWSING AND SEARCH

USER STORY NO: 06; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO BROWSE FOOD CATEGORIES SO THAT I CAN FIND DESIRED ITEMS QUICKLY BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Categories - Click category → show items - Responsive UI

USER STORY NO: 07; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO SEARCH FOR FOOD ITEMS SO THAT I CAN LOCATE MY FAVORITE DISHES BV: 500; CP: 03. ACCEPTANCE CRITERIA: - Search bar on top - Auto suggestions as user types - Display matching results

USER STORY NO: 08; Tasks: 2; Priority: MEDIUM. AS A CUSTOMER I WANT TO FILTER FOOD BY PRICE RANGE SO THAT I CAN SELECT WITHIN MY BUDGET BV: 200; CP: 01. ACCEPTANCE CRITERIA: - Slider to select min-max price - Auto refresh food list

USER STORY NO: 09; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO VIEW FOOD ITEM DETAILS SO THAT I CAN SEE INGREDIENTS AND PRICE BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Click on item → open detail page - Show image, description, price, rating

USER STORY NO: 10; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO SEE RATINGS AND REVIEWS SO THAT I CAN MAKE INFORMED CHOICES BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Star ratings - List of recent reviews

SPRINT-3: ORDER PLACEMENT AND CART

USER STORY NO: 11; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO ADD ITEMS TO CART SO THAT I CAN PLACE ORDERS IN BULK BV: 500; CP: 02. ACCEPTANCE CRITERIA: - “Add to Cart” button - Item count updates - Mini-cart shows selected items

USER STORY NO: 12; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO VIEW MY CART SO THAT I CAN REVIEW ITEMS BEFORE ORDERING BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Cart summary screen - Edit quantities - Remove items

USER STORY NO: 13; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO CHECKOUT MY ORDER SO THAT I CAN COMPLETE PAYMENT BV: 500; CP: 03. ACCEPTANCE CRITERIA: - Address + Payment selection - “Place Order” button - Show Order Confirmation

USER STORY NO: 14; Tasks: 2; Priority: MEDIUM. AS A CUSTOMER I WANT TO SAVE MY ADDRESS SO THAT I DON’T HAVE TO ENTER IT EVERY TIME BV: 200; CP: 01. ACCEPTANCE CRITERIA: - Form to enter address - Save in user profile - Auto fill during checkout

USER STORY NO: 15; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO PAY ONLINE SO THAT I CAN COMPLETE ORDER SECURELY BV: 500; CP: 03. ACCEPTANCE CRITERIA: - Payment Gateway integration - Success/Fail message

SPRINT-4: ORDER TRACKING AND DELIVERY

USER STORY NO: 16; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO TRACK MY ORDER STATUS SO THAT I KNOW WHEN TO EXPECT DELIVERY BV: 500; CP: 03. ACCEPTANCE CRITERIA: - Order status: Confirmed, Prepared, Out for Delivery, Delivered - Progress bar or step view

USER STORY NO: 17; Tasks: 2; Priority: HIGHEST. AS A DELIVERY BOY I WANT TO SEE MY ASSIGNED ORDERS SO THAT I CAN DELIVER THEM TIMELY BV: 500; CP: 02. ACCEPTANCE CRITERIA: - List of assigned orders - Pickup and delivery details

USER STORY NO: 18; Tasks: 2; Priority: HIGHEST. AS A DELIVERY BOY I WANT TO UPDATE DELIVERY STATUS SO THAT CUSTOMER CAN BE NOTIFIED BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Buttons: Picked Up, Delivered - Sync with customer view

USER STORY NO: 19; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO GET SMS NOTIFICATIONS SO THAT I STAY UPDATED BV: 500; CP: 02. ACCEPTANCE CRITERIA: - SMS on Order Placement, Out for Delivery, Delivered

USER STORY NO: 20; Tasks: 2; Priority: HIGHEST. AS AN ADMIN I WANT TO ASSIGN ORDERS TO DELIVERY BOYS SO THAT DELIVERY IS SYSTEMATIC BV: 500; CP: 03. ACCEPTANCE CRITERIA: - Admin view of unassigned orders - Assign dropdown - Save and update delivery view

SPRINT-5: USER PROFILE AND ADMIN FEATURES

USER STORY NO: 21; Tasks: 2; Priority: MEDIUM. AS A CUSTOMER I WANT TO VIEW MY ORDER HISTORY SO THAT I CAN SEE PAST ORDERS BV: 200; CP: 01. ACCEPTANCE CRITERIA: - List of previous orders - Click to view order details

USER STORY NO:22; Tasks: 2; Priority: LOW. AS A CUSTOMER I WANT TO UPDATE MY PROFILE SO THAT MY INFO IS ALWAYS CURRENT BV: 50; CP: 01. ACCEPTANCE CRITERIA: - Edit Name, Mobile, Email - Save changes

USER STORY NO: 23; Tasks: 2; Priority: LOW. AS AN ADMIN I WANT TO VIEW ALL REGISTERED CUSTOMERS SO THAT I CAN MONITOR PLATFORM USAGE BV: 50; CP: 01. ACCEPTANCE CRITERIA: - List with pagination - Filter by email, phone

USER STORY NO: 24; Tasks: 2; Priority: MEDIUM. AS AN ADMIN I WANT TO VIEW ALL ORDERS SO THAT I CAN MANAGE THE FLOW BV: 200; CP: 01. ACCEPTANCE CRITERIA: - Table of orders - Status and total amount

USER STORY NO: 25; Tasks: 2; Priority: LOW. AS AN ADMIN I WANT TO DEACTIVATE ANY USER SO THAT PLATFORM REMAINS CLEAN BV: 50; CP: 02. ACCEPTANCE CRITERIA: - Deactivate button - Show status toggle

SPRINT-6: RATING, FEEDBACK, AND PROMOS

USER STORY NO: 26; Tasks: 2; Priority: MEDIUM. AS A CUSTOMER I WANT TO RATE A DELIVERY SO THAT GOOD SERVICE IS RECOGNIZED BV: 200; CP: 01. ACCEPTANCE CRITERIA: - Star rating after order delivery

USER STORY NO: 27; Tasks: 2; Priority: LOW. AS A CUSTOMER I WANT TO WRITE FEEDBACK SO THAT I CAN SHARE MY EXPERIENCE BV: 50; CP: 01. ACCEPTANCE CRITERIA: - Textbox with Submit button

USER STORY NO: 28; Tasks: 2; Priority: LOW. AS AN ADMIN I WANT TO VIEW CUSTOMER FEEDBACK SO THAT I CAN IMPROVE SERVICES BV: 50; CP: 01. ACCEPTANCE CRITERIA: - Table of feedback entries - Sort by date

USER STORY NO: 29; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO APPLY PROMO CODES SO THAT I GET DISCOUNTS BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Promo code field - Validate and adjust total

USER STORY NO: 30; Tasks: 2; Priority: MEDIUM. AS AN ADMIN I WANT TO CREATE PROMO CODES SO THAT CUSTOMERS GET DEALS BV: 200; CP: 02. ACCEPTANCE CRITERIA: - Promo form: code, expiry, discount - Save and activate

SPRINT-7: NOTIFICATIONS, SUPPORT & MISC

USER STORY NO: 31; Tasks: 2; Priority: MEDIUM. AS A CUSTOMER I WANT TO RECEIVE EMAIL CONFIRMATION AFTER ORDER SO THAT I HAVE PROOF OF PURCHASE BV: 200; CP: 01. ACCEPTANCE CRITERIA: - Email sent after order placement - Includes order ID, items, total, delivery time

USER STORY NO: 32; Tasks: 2; Priority: HIGHEST. AS A DELIVERY BOY I WANT TO VIEW MAP TO CUSTOMER LOCATION SO THAT I CAN NAVIGATE EASILY BV: 500; CP: 03. ACCEPTANCE CRITERIA: - Show Google Map with customer location - Click to open navigation

USER STORY NO: 33; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO CHAT WITH CUSTOMER SUPPORT SO THAT I CAN RESOLVE ISSUES BV: 500; CP: 03. ACCEPTANCE CRITERIA: - Live chat box on dashboard - Agent assignment and message history

USER STORY NO: 34; Tasks: 2; Priority: HIGHEST. AS AN ADMIN I WANT TO MONITOR ACTIVE DELIVERY BOYS SO THAT I CAN TRACK OPERATIONS LIVE BV: 500; CP: 03. ACCEPTANCE CRITERIA: - List of currently online delivery personnel - Their assigned orders

USER STORY NO: 35; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO SAVE MULTIPLE ADDRESSES SO THAT I CAN CHOOSE ONE DURING CHECKOUT BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Address book feature - Select preferred address

USER STORY NO: 36; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO GET ALERT FOR DEALS AND OFFERS SO THAT I DON’T MISS DISCOUNTS BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Notification center - Push or in-app alerts

USER STORY NO: 37; Tasks: 2; Priority: HIGHEST. AS A DELIVERY BOY I WANT TO MARK MY AVAILABILITY SO THAT I RECEIVE ORDERS WHEN READY BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Toggle for availability ON/OFF - Status sync with Admin Panel

USER STORY NO: 38; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO CANCEL MY ORDER SO THAT I CAN AVOID WRONG OR DELAYED ORDERS BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Cancel button available until food is prepared - Refund logic in place

USER STORY NO: 39; Tasks: 2; Priority: HIGHEST. AS AN ADMIN I WANT TO GENERATE DAILY ORDER REPORTS SO THAT I CAN REVIEW BUSINESS PERFORMANCE BV: 500; CP: 02. ACCEPTANCE CRITERIA: - Select date range - Show order counts, revenue, cancellations

USER STORY NO: 40; Tasks: 2; Priority: HIGHEST. AS A CUSTOMER I WANT TO REORDER FROM MY HISTORY SO THAT I CAN QUICKLY PLACE FREQUENT ORDERS BV: 500; CP: 02. ACCEPTANCE CRITERIA: - “Reorder” button in order history - Cart pre-filled from past order

- What is epic? Write 2 epics?

- Epic: It is a set of related user stories. They are also considered as “ Really Big User Story”

EPIC 1: USER MANAGEMENT AND AUTHENTICATION

- Theme:  Registration, Login, Profiles

- This epic covers everything related to user creation, role-based access, and account settings.

- Included User Stories:

US 1: Register as Customer

US 2: Register as Delivery Boy

US 3: Customer Login

US 4: Delivery Boy Login

US 5: Admin Login

US 22: Update Customer Profile

US 25: Admin Deactivate User

US 23: Admin View All Customers

US 35: Save Multiple Addresses

US 37: Delivery Boy Availability Toggle

EPIC 2: MENU DISCOVERY AND ORDER PLACEMENT

- Theme: Menu, Search, Cart, Checkout

- This epic covers how users discover food, add to cart, and place an order.

- Included User Stories:

US 6: Browse Food Categories

US 7: Search Food Items

US 8: Filter by Price

US 9: View Item Details

US 10: View Ratings and Reviews

US 11: Add Items to Cart

US 12: View Cart

US 13: Checkout

US 14: Save Address

US 15: Pay Online

US 29: Apply Promo Codes

US 30: Admin Create Promo Codes

US 40: Reorder from History

EPIC 3: ORDER FULFILLMENT AND DELIVERY

- Theme: Delivery, Order Tracking, Status Updates

- This epic focuses on the full delivery flow—from placing to receiving orders.

- Included User Stories:

US 16: Track Order Status

US 17: Delivery Boy Sees Assigned Orders

US 18: Update Delivery Status

US 19: SMS Notifications

US 20: Admin Assign Orders

US 26: Rate Delivery

US 32: View Map to Customer Location

US 34: Admin Monitor Active Delivery Boys

US 38: Cancel Order

EPIC 4: FEEDBACK, SUPPORT, AND ENGAGEMENT

- Theme: Communication, Feedback, Support

- This epic includes reviews, feedback, support, and user engagement strategies.

- Included User Stories:

US 10: View Ratings and Reviews

US 26: Rate Delivery

US 27: Write Feedback

US 28: Admin View Feedback

US 31: Email Order Confirmation

US 33: Chat with Customer Support

US 36: Alerts for Deals and Offers

EPIC 5: ADMINISTRATION AND ANALYTICS

- Theme: Admin Tools, Reports, Monitoring

- This epic provides tools for the admin to monitor the app, manage users, and analyze performance.

- Included User Stories:

US 5: Admin Login

US 20: Assign Orders to Delivery

US 23: View Registered Customers

US 24: View All Orders

US 25: Deactivate Users

US 28: View Feedback

US 30: Create Promo Codes

US 34: Monitor Active Delivery Boys

US 39: Generate Daily Order Reports

- What is the difference between BV and CP?

- Below are some of the Differences between Business Value & Complexity Points:

| Aspect | Business Value | Complexity Point |
| --- | --- | --- |
| Definition | A measure of how much a task, feature, or user story will contribute to the organization's goals or Benefits the customer | A relative measure of how difficult or time-consuming a task or user story is to complete |
| Focus | "Why" the work is important | "How much" effort it will take |
| Determined by/ Estimates by | Product Owner, Stakeholders, or business representatives | The Development team |
| Purpose | Prioritization — higher business value items are often scheduled earlier | Estimating workload and sprint planning |
| Factors considered | Can be based on revenue impact, customer satisfaction, strategic alignment, etc | Technical complexity, risk, uncertainty, and effort |
| Example | A feature that enables online payments might have a high business value because it directly enables revenue | A feature that requires integrating with an unknown third-party API might have high complexity, even if it has low business value |

- Explain about Sprint?

- Definition: In project management, especially in Agile methodologies like Scrum, a Sprint is a short, time-boxed period during which a specific set of work must be completed and made ready for review or release.

Key Points About a Sprint:

- Time-Boxed Duration:

A Sprint usually lasts 1 to 4 weeks, most commonly 2 weeks.

The duration is consistent throughout the project.

- Goal-Oriented:

Each Sprint has a Sprint Goal, which defines the purpose and outcome.

The team works collaboratively to achieve this goal.

- Starts with Sprint Planning:

The team holds a Sprint Planning meeting at the beginning.

They select items from the Product Backlog to work on, forming the Sprint Backlog.

- Daily Stand ups:

Teams hold Daily Scrum (standup) meetings (usually 15 minutes).

Team members share progress, plans for the day, and any blockers.

- Ends with a Review and Retrospective:

Sprint Review: Demonstrate the work completed to stakeholders.

Sprint Retrospective: The team reflects on the Sprint to improve processes in the next one.

- Working Software Delivered:

The goal is to deliver a potentially shippable or usable product increment by the end.

Sprint Lifecycle Overview:

- Sprint Planning

- Sprint Execution (Development + Daily Scrums)

- Sprint Review

- Sprint Retrospective

Benefits of Sprints:

- Encourages frequent delivery of value.

- Provides regular feedback loops.

- Increases transparency and adaptability.

- Empowers teams to self-organize and continuously improve.

- Explain Product backlog and sprint back log?

- Product Backlog: The Product Backlog is a master list of everything that is known to be needed in the product. It is maintained by the Product Owner.

Key Features:

- Contains all features, enhancements, bug fixes, and technical work.

- Items are called Product Backlog Items (PBIs) or user stories.

- It is dynamic – constantly evolving as the product and market needs change.

- Items are prioritized (highest value or urgency at the top).

- Anyone can suggest items, but only the Product Owner can add them officially.

Example Items in a Product Backlog:

- “As a user, I want to reset my password.”

- “Fix bug causing crash on checkout page.”

- “Improve loading speed of the home screen.”

Sprint Backlog: The Sprint Backlog is a subset of the Product Backlog — it includes the items that the Scrum Team commits to complete during a specific Sprint.

Key Features:

- Created during the Sprint Planning meeting.

- Selected by the Development Team (they decide what they can deliver).

- Contains detailed tasks and estimates for implementation.

- It is fixed during the Sprint (only the team can make changes).

- Also includes a Sprint Goal, giving purpose to the chosen work.

Example in Sprint Backlog (from the above example):

- Task: Create “Forgot Password” UI.

- Task: Integrate with email service.

- Task: Write test cases for reset password

- What is impediments log? Write 2 impediments?

- Impediments Log: The Impediments Log is a centralized list where all known impediments are recorded, monitored, and managed until they are resolved.  An impediment is anything that prevents or slows down the team's ability to deliver value. Examples include:

- Technical issues

- Lack of resources or tools

- Unclear requirements

- Dependencies on other teams

- Organizational or procedural bottlenecks

Below are some Impediments log

IMPEDIMENT LOG – 1

- Date Identified: 2025-07-25

- Sprint:Sprint-3 (Order Placement and Cart)

- Impediment Title: Payment Gateway API Not Responding

- Description: The integrated third-party payment gateway (Razor pay) is intermittently failing during the checkout process. This blocks completion of US-13 and US-15.

- Impact: High – Customers cannot complete orders, halting core business functionality.

- Owner: Dev Team Lead

- Resolution Strategy:

Contacted payment provider’s support.

Fallback payment option (Cash on Delivery) temporarily enabled.

Dev added retry logic.

- Status: Resolved

- Resolution Date: 2025-07-27

IMPEDIMENT LOG – 2

- Date Identified: 2025-07-26

- Sprint: Sprint-4 (Order Tracking and Delivery)

- Impediment Title: Delivery Status Update Not Syncing for Customers

- Description: When a delivery boy marks an order as “Delivered”, the status is not updated in the customer app in real time.

- Impact: Medium – Causes confusion and increases support queries.

- Owner: Backend Developer

- Resolution Strategy:

Identified missing Web Socket event listener on the customer app.

Deployed patch to fix real-time sync issue.

- Status: Resolved

- Resolution Date: 2025-07-28

IMPEDIMENT LOG – 3

- Date Identified: 2025-07-27

- Sprint: Sprint-2 (Menu Browsing and Search)

- Impediment Title: Search API Response Too Slow

- Description: Search API takes more than 5 seconds to return results, impacting US-7 and US-8 performance.

- Impact: Medium – Affects user experience and slows down acceptance testing.

- Owner: Backend Developer

- Resolution Strategy:

Indexed key columns in database

Optimized search queries and implemented server-side pagination

- Status: Resolved

- Resolution Date: 2025-07-29

IMPEDIMENT LOG – 4

- Date Identified: 2025-07-28

- Sprint: Sprint-5 (User Profile and Admin Features)

- Impediment Title: Admin Role Permissions Not Defined

- Description: Developers are unclear on role-based access control for Admin Panel features related to US-24 and US-25.

- Impact: High – Security and feature access boundaries not implemented correctly.

- Owner: Scrum Master

- Resolution Strategy:

Conducted clarification session with Product Owner

Finalized RBAC policy and updated user roles schema

- Status: Resolved

- Resolution Date: 2025-07-29

IMPEDIMENT LOG – 5

- Date Identified: 2025-07-29

- Sprint: Sprint-6 (Rating, Feedback, and Promos)

- Impediment Title: Feedback Module UI Not Aligned Across Devices

- Description: The feedback form (US-27) layout breaks on mobile screens, making it unusable.

- Impact: Low – Non-blocking but affects UI consistency and user engagement.

- Owner: Frontend Developer

- Resolution Strategy:

Applied responsive design fixes with media queries

Conducted cross-device testing

- Status: Resolved

- Resolution Date: 2025-07-29

- Explain Velocity of the Team?

- Team Velocity is a key metric in Agile (especially Scrum) that measures how much work a team can complete during a sprint. It helps teams estimate future work capacity and plan more accurately.

- Velocity is team-specific and should not be compared across teams.

- It is not a productivity measure — changes in velocity can be due to scope complexity, not team performance.

- Needs several sprints to stabilize before it's reliable

Uses:

- Sprint Planning: Helps decide how much work to take on.

- Forecasting: Predicts how many sprints are needed to finish a product backlog.

- Performance Insight: Shows trends over time (but shouldn't be used for individual evaluation

- Draw Sprint Burn Charts n Product Burn Down Charts?

- Below showing Sprint Burn Down Chart

Product Burn down Chart

- Definition: It shows the amount of work remaining in the entire product backlog across multiple sprints.

- Purpose: To track overall progress toward project or product completion.

- X-axis: Time (e.g., number of sprints); Y-axis: Remaining work in the Product Backlog (e.g., story points)

- Audience: Product Owner, stakeholders, project managers

- Key Traits:

Long-term focus

Updated at the end of each sprint

Helps forecast delivery date

Useful in Sprint Reviews and release planning

- Explain about Product Grooming?

- Product Grooming: Product Grooming — also known as Backlog Grooming or Backlog Refinement — is a regular Agile practice where the team and Product Owner review, refine, and prioritize items in the product backlog to ensure they are ready for upcoming sprints

It’s a collaborative session to:

- Clarify and break down large user stories (epics)

- Estimate story points or effort

- Add acceptance criteria

- Re-prioritize items based on business value or urgency

- Remove outdated or irrelevant items

Participants:

- Product Owner (leads the session)

- Scrum Master (facilitates if needed)

- Development Team (provides technical insights and effort estimates)

- Sometimes stakeholders or UX designers (if input is needed)

When Does It Happen?

- Usually mid-sprint (1-2 times per sprint)

- Sessions can last 30–60 minutes, depending on backlog size

Benefits of Grooming

- Keeps the product backlog clean and organized

- Ensures stories are ready for sprint planning

- Reduces surprises and confusion during development

- Improves estimation accuracy and team collaboration

Common Pitfalls

- Over-grooming (too frequent or too long sessions)

- Not involving the right people

- Grooming too close to the sprint start (rushed planning)

- Explain the roles of Scrum Master and Product Owner?

- Scrum Master: He will monitor the performance of the Team within the Sprint. Team will raise all their issues to the Scrum Master and he will run to look for Answers. This role can be played by any person in team normally BA’s play this role

Product Owner: He will decides what needs to be in the product and will be responsible for how the product has to be. He will regularly interact with customers and BA’s. This role may be played by the BA or any person who worked for end users for a long time or customer himself.

- Explain all Meetings Conducted in Scrum Project?

- In a Scrum project, there are four key meetings designed to keep the team aligned, inspect progress, and adapt plans. These meetings are time-boxed and serve specific purposes to help teams deliver value in an iterative, collaborative way.

Sprint Planning:

- Purpose: Plan the work to be completed during the upcoming sprint.

- Attendees:

Product Owner

Scrum Master

Development Team

- Key Activities:

Select Sprint Goal

Choose backlog items to work on

Break stories into tasks

Team commits to what they can deliver

- Time-box:

Up to 8 hours for a 1-month sprint

Usually 2–4 hours for a 2-week sprint

Daily Scrum (Stand-Up)

- Purpose: A daily check-in for the team to synchronize and identify blockers.

- Attendees: Development Team (PO and Scrum Master may listen but don’t lead)

- Typical Questions:

What did I do yesterday?

What will I do today?

Are there any blockers?

- Time-box:

15 minutes, same time and place daily

Sprint Review

- Purpose: Demonstrate the work completed during the sprint and gather feedback.

- Attendees:

Development Team

Product Owner

Scrum Master

Stakeholders

- Key Activities:

Show working product increment

Discuss what was done vs. planned

Collect feedback for future planning

- Time-box:

Up to 4 hours for a 1-month sprint

Shorter for shorter sprints

Sprint Retrospective

- Purpose: Reflect on the sprint and identify ways to improve team processes.

- Attendees:

Development Team

Scrum Master

Product Owner (optional, but encouraged)

- Key Questions:

What went well?

What didn’t go well?

What can we improve?

- Time-box:

Up to 3 hours for a 1-month sprint

Usually 1–1.5 hours for a 2-week sprint

Summary Table:

| Scrum Meeting | Purpose | Time-box | Participants |
| --- | --- | --- | --- |
| Sprint Planning | Define sprint goal & work scope | Up to 8 hours | PO, Scrum Master, Team |
| Daily Scrum | Daily team sync-up | Up to 15 minutes | Development Team |
| Sprint Review | Demo and gather feedback | Up to 4 hours | Scrum Team, Stakeholders |
| Sprint Retrospective | Reflect & improve processes | Up to 3 hours | Scrum Team |

- Explain Sprint Size and Scrum Size?

- Sprint size: It refers to the duration (length) of a sprint — the fixed time box in which the team works to deliver a potentially shippable product increment

- Typically between 1 and 4 weeks.

- The most common sprint size is 2 weeks

- Keep sprint length consistent to stabilize velocity and improve predictability.

Scrum size: It refers to the size of the Scrum Team, including: Developers; Product Owner; Scrum Master. The Scrum Team is typically 10 or fewer people. Specifically:

- Developers: 3–9 members

- Product Owner: 1

- Scrum Master: 1

- Explain DOR and DOD?

- In Scrum and Agile, DOR (Definition of Ready) and DOD (Definition of Done) are important agreements that ensure clarity, quality, and shared understanding between team members. They help the team know when work can start and when it is truly complete

Definition of Ready: DOR outlines the criteria a user story or backlog item must meet before the team can start working on it in a sprint

- Purpose: Ensure that stories are well-prepared, understood, and actionable before entering a sprint

- Typical DOR Checklist:

The story is clearly defined and written

Acceptance criteria are specified

The story is estimated

Dependencies are identified and manageable

Business value is understood

UI/UX mockups (if needed) are attached

No major blockers are pending

- Think of DOR as: "Is this story ready to be worked on?"

Definition of Done: DOD defines the criteria that a product backlog item must meet to be considered complete — not just coded, but fully shippable or releasable

- Purpose: Ensure consistent quality and that work is potentially releasable at the end of the sprint

- Typical DOD Checklist:

Code is written and peer-reviewed

Unit/integration tests are passed

Code is merged and deployed to staging

No open bugs or defects

Acceptance criteria are met

Product Owner has reviewed and accepted

Documentation (if any) is complete

- Think of DOD as: "Is this story really done and deliverable?"

- Explain Prioritization Techniques and MVP?

- Prioritization Techniques:

- “MOSCOW” Technique: MOSCOW is a prioritizing technique which is used in business analysis and software development to reach a common understanding with stakeholders on the importance of each requirement

- Other Techniques are:

100 Dollars Test

- Top 10 requirements

- Numerical Assignment- Mandatory, Very important, Rather important, Not Important, does not matter

Minimum Viable Product:

- Definition: It is the simplest version of a product that delivers enough value to:

Solve the core problem

Be usable by early adopters

Allow you to gather feedback for improvement

- Use MVP:

Reduce risk by testing ideas early

Save time and cost — avoid overbuilding

Accelerate learning through real user feedback

Validate product-market fit

- MVP Is Not a:

A prototype or wireframe (it's functional)

The full product with all features

A shortcut for low quality

- MVP Example:

Full App Idea: A food delivery app with chat, GPS tracking, and loyalty programs
MVP: A web-based app that lets users order food from nearby restaurants with basic delivery options

- Difference between Business Analyst n Product Owner?

- Difference between Business Analyst n Product Owner is follows:

| Aspect | Business Analyst | Product Owner |
| --- | --- | --- |
| Focus | Understanding & documenting requirements | Maximizing product value |
| Main Goal | Ensure technical team understands business needs | Deliver the right product for users and stakeholders |
| Acts As | A bridge between business and development | Owner of the product backlog and vision |
| Requirement Gathering | Interviews, workshops, research | May assist, but typically relies on BA or users |
| Documentation | Writes user stories, process flows, specs | Reviews and accepts/refines them |
| Strategic vs. Tactical | More tactical, detail-oriented | More strategic, value-focused |
| Role in Agile | Optional/supporting | Core role (Scrum) |
| Stakeholder Communication | Gathers and translates needs | Sets expectations, negotiates priorities |
| Sprint Involvement | Supports team with clarifications | Participates fully in all Scrum ceremonies |
| Authority Level | Advises; not a decision-maker | Has decision authority on what gets built |

- Prepare a sample Resume of 3yrs exp Product Owner?

- Below for a sample Resume of 3yrs exp Product Owner

NAME: Sai Mohan Krishna Kolipaka

Hyderabad, India

+91-9014565186

mohankrishna.kolipaka@gmail.com

PROFESSIONAL SUMMARY:

Certified Product Owner with 3 years of hands-on experience in Agile environments, leading cross-functional teams to deliver high-impact software solutions. Skilled in product backlog management, stakeholder communication, and translating business needs into actionable user stories. Known for delivering value-driven features through continuous iteration and prioritization.

KEY SKILLS

- Agile/Scrum Methodologies

- Product Backlog Management

- User Story Writing & Grooming

- Sprint Planning & Review

- Jira, Trello, Confluence

- Stakeholder Management

- MVP & Roadmap Planning

- Wireframing Tools: Balsamiq, Figma, Axure, MS VISIO, Draw.io

- Data Analysis: Excel, Google Analytics, Power BI, Tableau, Python, MySQL

PROFESSIONAL EXPERIENCE

Product Owner

TCS, Hyderabad

Feb 2023 – Dec 2024

- Collaborated with stakeholders and customers to define product vision and roadmap for a B2B logistics platform.

- Owned and prioritized the product backlog for a team of 7 developers and 2 QA engineers.

- Conducted user story workshops, wrote over 150+ stories and acceptance criteria across 10 sprints.

- Led sprint planning, reviews, retrospectives, ensuring on-time delivery of all committed stories.

- Improved team velocity by 25% through backlog refinement and feedback loops.

- Coordinated UAT and release readiness with QA and business teams.

Key Achievements:

- Successfully launched 3 product features that increased customer retention by 18%.

- Reduced time-to-market by 30% by implementing feature toggling and MVP slicing.

Associate Product Owner

TCS, Hyderabad

Feb 2022 – Feb 2023

- Assisted the Senior Product Owner in gathering business requirements and creating epics and themes.

- Maintained user story mapping and release planning documentation in Confluence.

- Liaised with UI/UX teams to validate mockups before dev hand-off.

- Monitored KPIs post-deployment using Google Analytics and Mixpanel.

EDUCATION

Bachelor of Engineering (Mechanical Engineering)

Vijaya Engineering College, Khammam

2016 – 2020 | CGPA: 8.2/10

CERTIFICATIONS

Agile Product Management – Udemy

LANGUAGES

- English – Full Professional Proficiency

- Telugu – Native

- Hindi – Conversational

- Tamil – Conversational